## Engagement Log
Land Interest (Table 1 & Table 2) | Objector Reference | Sheet Number & Land Plot no(s) | Description of rights sought | Summary of negotiation status
Aaron James Howlett |  | 148/6, 148/40 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post for Aaron James Howlett 01/10/2025 - Chaser Land interest questionnaire issued via post 15/12/2025 - Land interest questionnaire issued via post for Eleanor Jean Levoir Harris 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser Offer letter issued via post 27/04/2026 - Doorknocking exercise undertaken by Savills to establish contact with the grantor and to discuss the project 30/04/2026 - Copy of offer letter emailed to grantor 05/05/2026 - Email received from grantor confirming he is looking to appoint a solicitor 07/05/2026 - Email from grantor confirming solicitor has been appointed and guidance provided 13/05/2026 - Project letter issued 18/06/2026 - Emailed to confirm solicitor details 26/06/2026 - Correspondence with solicitor 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Eleanor Jean Levoir Harris |  | 148/6, 148/40 | Overhead line rights | As Aaron James Howlett (above)
Alan Covey |  | 25/6, 25/7, 26/1, 26/2, 26/4, 27/1, 27/2, 27/3, 27/4, 27/5, 28/2, 28/4, 28/6, 29/1, 26/1a | Overhead lines rights Construction and operational access rights | 03/09/2025 - Two Land Interest Questionnaires issued via post 01/10/2025 - Chaser Land interest questionnaire issued via post 15/01/2026 - Offer Letter issued via post 19/03/2026 - Chaser offer letter issued via post 23/04/2026 - Chaser sent via email in response to offer letter 06/05/2026 - Chaser sent via email in response to offer letter 13/05/2026 - Solicitor details chased 19/05/2026 - Response from land agent 13/05/2026 - Project letter issued 01/06/2026 - Appointed land agent confirmation 04/06/2026 - Site meeting arranged 09/06/2026 - Teams meeting with agent - details discussed 17/06/2026 - Further information provided to agent 02/07/2026 - Chaser for solicitor details 13/07/2026 - Correspondence with agent 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Alan Robert Bull |  | 83/2, 83/5, 83/13, 83/14, 83/15, 83/16 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land Interest Questionnaire issued via post to both grantors 01/10/2025 - Chaser Land interest questionnaire issued via post 13/10/2025 - Grantor phoned and left a voicemail requesting a site meeting to discuss the Land Interest Questionnaire and project in further detail. 14/10/2025 - Savills contacted grantor in response to discuss Land Interest Questionnaire / offer that has been made and arrange a site meeting. Site meeting with agent arranged 17/10/2025 - Site meeting held with grantor's agent. Agent very willing to negotiate 03/11/2025 - Savills contacted grantor in response to discuss Land Interest Questionnaire / offer that has been made 15/01/2026 - Offer letter issued via post 19/02/2026 - Emails exchanged with grantors agent to discuss offer letter and project in further detail 10/03/2026 - Summary of Key Terms issued to agent via email 21/04/2026 - Email exchanged between Savills and grantor's agent regarding the Summary of Key Terms issued previously 09/06/2026 - CPO notice sent to agent 02/07/2026 - Chaser for solicitor details 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Moira Jane Bull |  | 83/2, 83/5, 83/13 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land Interest Questionnaire issued via post to both grantors 01/10/2025 - Chaser Land interest questionnaire issued via post 13/10/2025 - Grantor phoned and left a voicemail requesting a site meeting to discuss the Land Interest Questionnaire and project in further detail. 14/10/2025 - Savills contacted grantor in response to discuss Land Interest Questionnaire / offer that has been made and arrange a site meeting. Site meeting with agent arranged 17/10/2025 - Site meeting held with grantor's agent. Agent very willing to negotiate 03/11/2025 - Savills contacted grantor in response to discuss Land Interest Questionnaire / offer that has been made 15/01/2026 - Offer letter issued via post 19/02/2026 - Emails exchanged with grantors agent to discuss offer letter and project in further detail 10/03/2026 - Summary of Key Terms issued to agent via email 21/04/2026 - Email exchanged between Savills and grantor's agent regarding the Summary of Key Terms issued previously 09/06/2026 - CPO notice sent to agent 02/07/2026 - Chaser for solicitor details 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Amanda Jane French | OBJ-016 | 68/8, 69/1, 100/4, 100/5, 101/13, 101/17, 101/18 | Overhead lines rights Construction and operational access rights | 03/09/2025 - 3 Land Interest Questionnaires issued via Post 08/09/2025 - Land Interest Question issued via post 09/09/2025 - Savills received correspondence from the the grantor to discuss the Land Interest Questionnaire and project in further detail 10/09/2025 - Emails exchanged between grantor and Savills to discuss the project in further detail 06/10/2025 - Site meeting held between Savills and the grantor 22/10/2025 - Phone call and email to grantor to discuss the project in further detail 23/10/2025 - Grantor called to discuss the project in further detail 03/11/2025 - Phone call received from grantor with queries about the project 13/11/2025 - Site meeting booked with grantor to discuss project in further detail 17/11/2025 - Emails exchanged between the grantor and Savills to address queries 19/11/2025 - Phone call with grantor to discuss the project in greater detail 20/11/2025 - Phone call with grantor to discuss the project in greater detail 15/01/2026 - Offer letter issued to grantor via Post 18/01/2026 - Emails exchanged with grantor to discuss terms / project in detail 23/01/2026 - Emails exchanged with grantor to discuss terms / project in detail 16/03/2026 - National Grid correspondence with grantor 28/04/2026 - Emails exchanged with Grantors Agent 29/04/2026 - Savills confirms further project details and correspondence with National Grid 05/05/2026 - Emails exchanged between agent and Savills to address queries 13/05/2026 - Savills confirms waiting for an update 01/07/2026 - Confirmed receipt of email from Grantor/Agent 02/07/2026 - Chased for solicitor details 02/07/2026 - Email discussion with agent to address outstanding queries before solicitors can be instructed 05/08/2026 - Letter issued to grantor and agent in response to their objection
Peter John French | OBJ-016 | 100/4, 100/5, 101/13, 101/17, 101/18 | Overhead lines rights Construction and operational access rights | As Amanda Jane French (above)
Richard Alan French | OBJ-016 | 100/4, 100/5, 101/13, 101/17, 101/18 | Overhead lines rights Construction and operational access rights | As Amanda Jane French (above)
Andrew Guy Speakman |  | 115/5, 115/8, 128/1, 128/2, 128/4, 129/1, 129/2, 129/3, 129/5, 129/6, 129/8, 131/3, 131/4, 130/7, 130/8, 130/11, 130/12, 130/13 | Overhead lines rights Construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 08/09/2025 - Land interest questionnaire issued via post 08/09/2025 - Land interest questionnaire issued via post 08/09/2025 - Land Interest Questonnaire issued via post 22/09/2025 - Phone call received from grantor to discuss the project in further detail 25/09/2025 - Email exchanged from grantor to discuss the Land Interest Questionnaire / project in further detail 25/09/2025 - Phone call to grantor to discuss queries and concerns about the project 06/10/2025 - Site meeting held with grantor and land agent to discuss the project in further detail 01/12/2025 - Email to land agent to discuss the project in further detail. 12/12/2025 - Phone call exchanged with land agent to discuss queries 15/01/2026 - Offer letter issued to grantors via post 15/01/2026 - Offer letter issued 10/03/2026 - Summary of Terms issued to Agent via email 12/03/2026 - Email corrispndance revieved from the Agent regarding the summary of terms 19/03/2026 - Chaser Offer letter issued via post to grantors 28/04/2026 - Chaser email sent out to Agent re: offer letter 13/05/2026 - Chaser email sent to Agent re: offer letter 13/05/2026 - Project letter issued 08/06/2026 - Meeting scheduled with agent 09/06/2026 - Notice emailed 02/07/2026 - Chaser sent for solicitor details 02/07/2026 - Grantor/Agent receipt of details confirmed 02/07/2026 - Email sent to grantor/agent regarding CPO objection
Christopher Francis Speakman |  | 115/5, 115/8, 128/1, 128/2, 128/4, 129/1, 129/2, 129/3, 129/5, 129/6, 129/8, 131/3, 131/4, 130/7, 130/8, 130/11, 130/12, 130/13 | Overhead lines rights Construction and operational access rights | As Andrew Guy Speakman (above)
Philip William Henry Speakman | OBJ-029 | 115/5, 115/8, 128/1, 128/2, 128/4, 129/1, 129/2, 129/3, 129/5, 129/6, 129/8, 131/3, 131/4, 130/7, 130/8, 130/11, 130/12, 130/13 | Overhead lines rights Construction and operational access rights | As Andrew Guy Speakman (above)
Andrew James Buck |  | 75/3, 75/4, 75/5, 75/7, 75/9, 78/2, 78/3, 78/5, 79/3, 79/5 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land interest questionnaire issued via post 15/01/2026 - Offer letter issued via post to grantor 29/01/2026 - Email exchanged between Savills and grantors land agent to discuss the terms and project in further detail 26/02/2026 - Emails exchanged between Savills and grantors land agent to discuss the terms and project in further detail 10/03/2026 - Summary of Key Terms issued to agent via email 13/03/2026 - Emails exchanged between Savills and grantors land agent to discuss the project in further detail 06/05/2026 - Contact details for landowners chased via agent 13/05/2026 - Project letter issued 13/05/2026 - Solicitor details and status of offer letter chased 20/05/2026 - Emails exchanged regarding agent instruction and Terms of Business 16/06/2026 - Emails exchanged regarding agent instruction and Terms of Business 02/07/2026 - Solicitor details chased via agent on email 02/07/2026 - Emails exchanged between Savills and grantor's land agent to discuss the project in further detail and arrange meeting with grantor 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Andrew John Thorogood |  | 124/1, 125/1, 125/3, 125/7, 125/8, 125/9, 125/10, 125/11, 126/1, 126/2, 126/3, 127/1, 127/3, 127/4, 128/7, 128/8 | Overhead lines rights Construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land interest questionnaire issued via post 28/10/2025 - Phone call between Savills and grantor to discuss the Land Interest Questionnaire / project in further detail 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser offer letter issued via post 07/04/2026 - Chaser email regarding further details 13/05/2026 - Project letter issued 21/07/2026 - Phone call with grantor to discuss the project in further detail 21/07/2026 - Follow up email to confirm details and answer specific queries
Laura Thorogood |  | 124/1, 125/1, 125/3, 125/7, 125/8, 125/9, 125/10, 125/11, 126/1, 126/2, 126/3, 127/1, 127/3, 127/4, 128/7, 128/8 | Overhead lines rights Construction and operational access rights | As Andrew John Thorogood (above)
Andrew Simon Chapman | OBJ-047 | 115/3, 115/4, 115/6 | Overhead lines rights Construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 09/09/2025 - Emails exchanged between grantor, Savills and National Grid to discuss the project in further detail 18/11/2025 - Emails exchanged between Savills and the grantor to discuss the Land Interest Questionnaire / project in further detail 22/12/2025 - Emails exchanged between Savills and grantor to address queries and discuss project in further detail 23/12/2025 - Emails exchanged between savills and grantor to address queries and discuss project in further detail 15/01/2026 - Offer letter issued via post 16/01/2026 - Phone call between savills and the grantor to address queries about offer letter / discuss the project in further detail 19/03/2026 - Chaser offer letter issued via post 30/03/2026 - Phone and messages exchanged to discuss the terms / project in further detail 31/03/2026 - Phone and messages exchanged to discuss the terms / project in further detail 31/03/2026 - Phone and messages exchanged to discuss the terms / project in further detail 31/03/2026 - Email to grantor to discuss the terms / project in further detail, requesting a meeting 02/07/2026 - Email issued confirming receipt to CPO objection 05/08/2026 - Letter issued to grantor and agent in response to their objection
Andrew William Morton |  | 98/4, 98/6, 98/7, 98/8 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land interest questionnaire issued via post 16/10/2025 - Phone call received from grantor to discuss the Land Interest Questionnaire / project in further detail 21/10/2025 - Phone call to grantor to discuss the project in further detail 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser offer letter issued 23/04/2026 - Emails exchanged between savills and grantor to address queries and discuss project in further detail 15/05/2026 - Chaser sent for offer letter response 02/07/2026 - Correspondence from agent 02/07/2026 - Chased for solicitor details 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 29/07/2026 - Phone call received from the landowner advising they no longer own the affected land
Anglian Water Services Limited |  | 31/3, 31/8, 31/10, 31/11, 32/1, 32/2, 32/3, 32/4, 32/5, 32/6, 32/7, 45/8, 45/10, 46/2, 59/2, 59/3, 59/10, 60/2, 60/7, 64/3, 64/4, 65/1, 96/4, 96/5, 119/6, 121/2, 127/2, 128/5, 146/18, 146/30, 147/5, 147/7, 147/9, 147/10, 147/13, 147/16, 148/62, 149/13, 32/8, 32/9, 32/10 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 19/11/2025 - Phone call to grantor and agent to discuss the project in further detail 24/11/2025 - Email exchanges with agent regarding further information about the project 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser offer letter issued via post 02/04/2026 - Email exchanges with the agent to discuss the project and terms in greater detail 07/04/2026 - Email exchanges with the agent to discuss the project and terms in greater detail 05/05/2026 - Phone call with agent to discuss further details regarding the project and follow up 06/05/2026 - Proposed meeting organised with agent 13/05/2026 - Project letter issued 09/06/2026 - Meeting held to discuss the key summary of terms 02/07/2026 - Solicitor details chased 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Anneli Mabel Frances Mann |  | 140/3, 141/1, 141/14, 141/18, 141/19, 141/20 | Overhead lines rights Construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land interest questionnaire issued via post 13/10/2025 - Phone call with grantor to discuss the project and Land Interest Questionnaire in further detail 21/10/2025 - Phone call with grantor to discuss the project and Land Interest Questionnaire in further detail 22/10/2025 - Phone call with grantor to discuss the project and Land Interest Questionnaire in further detail 10/11/2025 - Meeting held with grantor to discuss the project in further detail 12/12/2025 - Email exchanges with grantors land agent about the project in further detail 15/01/2026 - Offer letter issued via post 23/01/2026 - Email exchanges with the land agent about offer letter terms and the project in greater detail 26/01/2026 - Phone call received from the grantor to discuss the project in further detail 02/02/2026 - Email exchanges with the agent to discuss queries and the project in further detail 10/03/2026 - Email exchanges with the agent about the Summary of Key Terms 11/03/2026 - Email exchanges with the agent about the Summary of Key Terms 07/04/2026 - Email exchanges with the agent to discuss the project and terms in greater detail 22/04/2026 - Phone call received from the grantor to discuss the project in further detail 05/05/2026 - Solicitor details confirmed 12/05/2026 - Information sent to National Grid and documentation sent for signature 13/05/2026 - Project letter issued 02/07/2026 - Chaser email sent for solicitor details 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Anthony John Morris |  | 148/10, 148/11, 148/26, 148/50 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 14/10/2025 - Phone call received to discuss the Land Interest Questionnaire & the project in further detail 04/11/2025 - Meeting held to discuss the project in greater detail 15/01/2026 - Offer letter issued via post 09/02/2026 - Phone call received to discuss the offer letter & the project in further detail 01/04/2026 - Emails exchanged with grantor to discuss the offer letter and the project in further detail 02/04/2026 - Emails exchanged with grantor to discuss the offer letter and the project in further detail 05/05/2026 - Solicitor details chased 13/05/2026 - Project letter issued 14/05/2026 - Phone call with grantor to confirm further details, confirmed intention to find solicitor and land agent 20/05/2026 - Signed appendix received via post 20/05/2026 - Emails exchanged with grantor to discuss the solicitor fees and the letter received in the post 26/05/2026 - Phone call from grantor to confirm details 29/06/2026 - Grantor confirms search is still going ahead for solicitor details 02/07/2026 - Solicitor details chased via email 09/07/2026 - Solicitor details received 13/07/2026 - Email confirm progress in due course & correspondence with solicitors 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Laura Ellen Morris |  | 148/10, 148/11, 148/26, 148/50 | Overhead line rights | As Anthony John Morris (above)
Antony Peter Drain | OBJ - 002 | 76/8 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land interest questionnaire issued via post 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser offer letter issued via post 27/04/2026 - Door knocking undertaken by Savills to establish contact with the grantor and to discuss the project 13/05/2026 - Project letter issued 01/06/2026 - Spoke to grantor, objection submitted and confirmed land parcel is included in CPO 02/06/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 04/06/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 05/06/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 11/06/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 01/07/2026 - Requested details of land agent to continue discussions 01/07/2026 - Email sent to grantor/agent regarding CPO objection 02/07/2026 - Emails exchanged between agent and Savills 05/08/2026 - Letter issued to grantor and agent in response to their objection
Anthony William Vernon
Cherry Stanhope Vernon
On Tower UK 2 Limited |  | 131/2, 131/5, 131/7, 131/9, 132/3, 132/10, 132/11, 146/18, 146/30, 147/5, 147/7, 147/9, 147/10 | Overhead lines rights Construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 24/09/2025 - Emails exchanged between LH and Savills to discuss the project in further detail. 24/09/2025 - Emails exchanged between LH and Savills to discuss the project in further detail. 08/04/2026 - Emails exchanged between LH and Savills to discuss the project in further detail.
On Tower UK Limited |  | 99/1, 99/2, 99/7, 99/7a, 100/1, 100/7, 130/1, 138/7 | Overhead lines rights Construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 24/09/2025 - Emails exchanged between LH party and Savills to discuss the project in further detail. 01/10/2025 - Chaser Land Interest Questionnaire Issued via post
Arthur Vernon Muskett |  | 10/14, 11/1, 11/2, 11/3, 11/3a, 11/5, 11/6, 11/7, 11/8, 11/9, 11/10, 11/11, 11/12, 12/1, 12/2, 12/3 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 13/10/2025 - Emails exchanged between Savills and grantor to answer queries and discuss the project in greater detail 22/10/2025 - Meeting held with grantor and emails exchanged between savills and grantor to answer queries and discuss the project in greater detail 15/01/2026 - Offer letter issued via post 16/01/2026 - Emails exchanged between Savills and grantor to answer queries and discuss the offer letter / terms in detail 19/01/2026 - Grantor confirmed Land agents to act on their behalf 03/02/2026 - Emails exchanged between Savills and grantor to answer queries and discuss the offer letter / terms in detail 10/03/2026 - Summary of Key Terms issued to land agent via email 13/05/2026 - Chaser regarding solicitor details 15/06/2026 - Email from land agent to confirm details 17/06/2026 - Further details requested 23/06/2026 - Confirmation of rates with land agent 02/07/2026 - Chaser regarding solicitor details 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 28/07/2026 - Solicitor details received and written confirmation requested
Katherine Girdwood Muskett |  | 10/14, 11/1, 11/2, 11/3, 11/3a, 11/5, 11/6, 11/7, 11/8, 11/9, 11/10, 11/11, 11/12, 12/1, 12/2, 12/3 | Overhead lines rights Construction and operational access rights | As Arthur Vernon Muskett (above)
Ashleigh James Lambert |  | 111/7 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 13/10/2025 - Chaser Land interest questionnaire issued via post 15/01/2026 - Offer Letter Issued via post 19/03/2026 - Chaser offer letter issued via post 27/04/2026 - Door knocking, landowner not home. Spoke to son and given contact number 30/04/2026 - Phone call received to discuss the offer letter & the project in further detail 13/05/2026 - Project letter issued 02/07/2026 - Chaser sent for solicitor details 14/07/2026 - Chaser sent for solicitor details 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 28/07/2026 - Phone call held with a family representative who confirmed they are happy to proceed
Barbara Ruth Greer |  | 58/5, 58/6 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land interest questionnaire issued via post 15/10/2025 - Phone call received from grantor to discuss the project in further detail 15/01/2026 - Offer Letter Issued via post 19/03/2026 - Chaser offer letter issued via post 29/04/2026 - Phone call received from grantor to discuss the project in further detail 06/05/2026 - Phone call with grantor to discuss details further 13/05/2026 - Project letter issued 02/07/2026 - Chaser sent for solicitor details 02/07/2026 - Discussions with agent via email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
William Greer |  | 58/5, 58/6 | Overhead line rights | As Barabara Ruth Greer (above)
Basildon Borough Council |  | 147/11, 147/17, 147/18, 147/19, 147/20, 148/1, 148/2, 148/14, 148/21, 148/30, 148/44, 148/54, 148/62, 149/2, 149/4, 149/13 | Overhead lines rights Construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire issued via post 15/01/2026 - Offer Letter Issued via post 09/02/2026 - Emails exchanged between savills and grantor to answer queries and discuss the project in greater detail 16/02/2025 - Email to grantor advising letter to be sent out 09/03/2026 - Emails exchanged between savills and grantor to answer queries and discuss the project in greater detail 26/03/2026 - Emails exchanged between savills and grantor to answer queries and discuss the project in greater detail 31/03/2026 - Emails exchanged between savills and grantor to answer queries and discuss the project in greater detail 07/04/2026 - Emails exchanged between savills and grantor to answer queries and discuss the project in greater detail 20/04/2026 - Emails exchanged between savills and grantor to answer queries and discuss the project in greater detail 24/04/2026 - Phone call received from grantor to discuss the project in further detail 05/05/2026 - Correspondence with grantor to discuss further details regarding the project 13/05/2026 - Follow up email regarding progress 13/05/2026 - Project letter issued 15/06/2026 - Confirmation that solicitors will be in touch in due course 02/07/2026 - Chase sent for solicitor details 14/07/2026 - Follow up chasing solicitor details 15/07/2026 - Solicitor details confirmed with grantor 20/07/2026 - Correspondence with grantor regarding draft agreement and project queries
Begin Braintree Limited |  | 98/2, 98/4, 98/5, 98/6, 99/6, 99/14, 98/7, 98/8 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire issued via post 15/01/2026 - Offer letter issued via post 02/03/2026 - Phone call between Savills and grantor to answer queries and discuss the project in greater detail 09/03/2026 - Emails exchanged between Savills and grantor to answer queries and discuss the project in greater detail 10/03/2026 - Summary of key terms issued to agent via email 01/04/2026 - Emails exchanged between Savills and grantor to answer queries and discuss the project in greater detail 16/04/2026 - Emails exchanged between Savills and grantor to answer queries and discuss the project in greater detail 17/04/2026 - Emails exchanged between Savills and grantor to answer queries and discuss the project in greater detail 22/04/2026 - Emails exchanged between Savills and grantor to answer queries and discuss the project in greater detail 06/05/2026 - Emails exchanged between Savills and grantor to answer queries and discuss the project in greater detail 13/05/2026 - Project letter issued 09/06/2026 - Emails exchanged between Savills and grantor to answer queries and discuss the project in greater detail 12/06/2026 - Emails exchanged between Savills and grantor to answer queries and discuss the project in greater detail 16/06/2026 - Queries from grantor answered 19/06/2026 - Emails exchanged between Savills and grantor to answer queries and discuss the project in greater detail 22/06/2026 - Emails exchanged between Savills and grantor to answer queries and discuss the project in greater detail 02/07/2026 - Chaser sent regarding solicitor details 07/07/2026 - Solicitor emails confirmed 14/07/2026 - Follow up chasing solicitor details 15/07/2026 - Solicitor details confirmed and request made to review draft agreement 15/07/2026 - Email issued confirming draft agreement will be provided by solicitors in due course 20/07/2026 - Emails exchanged between Savills and grantor to answer queries and discuss the project in greater detail
Benjamin George Hughes |  | 84/1, 84/2, 84/3, 84/5, 84/7, 84/8, 84/13, 85/8, 85/9, 85/11, 85/12, 85/13, 85/17 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser offer letter issued via post 01/04/2026 - Email exchanged between agent to discuss the project in greater detail 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Caroline Jane Kemp |  | 84/1, 84/2, 84/3, 84/5, 84/7, 84/8, 84/13, 85/8, 85/9, 85/11, 85/12, 85/13, 85/17 | Overhead lines rights Construction and operational access rights | As Benjamin George Hughes (above)
Benjamin Thomas Twinn |  | 69/2, 70/1, 70/4, 71/9, 71/11, 69/3, 69/4, 70/2, 70/3, 70/5, 70/7, 70/8, 70/9, 70/11, 71/6, 71/7, 71/15 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 08/09/2025 - Phone call received from grantor to discuss the project and concerns in greater detail 23/10/2025 - Phone call received from grantor to discuss the project and concerns in greater detail 15/01/2026 - Offer letter issued via post 28/01/2026 - Meeting held between grantor and savills to discuss the project in further detail 11/03/2026 - Summary of Key Terms issued to agent via email 22/04/2026 - Email to agent asking if further assistance is required 23/04/2026 - Emails exchanged with grantors agent about offer letter, key terms and to discuss project in further detail 13/05/2026 - Chaser regarding solicitor details 13/05/2026 - Project letter issued 15/05/2026 - Correspondence exchanged regarding land ownership 20/05/2026 - Correspondence exchanged regarding land ownership and letter address 02/07/2026 - Chaser sent regarding solicitor details 06/07/2026 - Solicitor details provided via agent 07/07/2026 - Confirmation issued that solicitor details had been captured 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Berwick Hall Farm Limited | OBJ-020 | 39/3, 39/4, 39/5, 39/6, 39/8, 39/9, 39/10, 39/11, 39/12, 39/13, 39/14, 40/1, 40/2, 41/1, 41/2, 44/6, 44/10, 44/11, 45/1, 45/2, 45/5, 45/7, 45/9, 45/10, 46/1, 46/2, 46/3, 46/5 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser offer letter issued via post 27/04/2026 - Savills had a site meeting with farm worker, contact number provided 30/04/2026 - Phone call received from grantor to discuss the project and concerns in greater detail 13/05/2026 - Project letter issued 02/07/2026 - Chaser sent regarding solicitor details 02/07/2026 - Holding email issued following receipt of CPO objection 05/08/2026 - Letter issued to grantor and agent in response to their objection
Bollington Hall Limited |  | 7/3, 7/4, 8/4, 8/6, 8/9 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued via post 05/01/2026 - Phone call received from grantor to discuss the project in greater detail 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser offer letter issued via post 09/04/2026 - Email exchange with signed appendix attached 09/04/2026 - Emails exchanged with grantors agent about offer letter, key terms and to discuss project in further detail 11/04/2026 - Emails exchanged with grantors agent about offer letter, key terms and to discuss project in further detail 17/04/2026 - Solicitor details confirmed 13/05/2026 - Project letter issued 16/06/2026 - Documentation sent to grantor 06/07/2026 - Confirmation details have been captured 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Bower Croft Limited |  | 3/3, 3/4, 4/2, 4/3, 4/4, 5/1, 6/2, 6/3, 7/1 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued via post 21/10/2025 - Email exchange with agent to discuss the project in greater detail 26/10/2025 - Email exchange with agent to discuss the project in greater detail 04/12/2025 - Email exchange with agent to discuss the project in greater detail 15/01/2026 - Offer letter issued via post 16/01/2026 - Email from grantor requesting a recommendation of a land agent 19/01/2026 - Email exchange with agent to discuss the offer letter and project in greater detail 23/01/2026 - Email from agent requesting draft access plans 13/05/2026 - Project letter issued 14/05/2026 - Solicitor details chased 22/05/2026 - Confirmation of details regarding 27/05/2026 - Email exchange with agent to discuss the project in greater detail 04/06/2026 - Email exchange with Savills to discuss the project in greater detail 02/07/2026 – Chaser sent regarding solicitor details 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Oaks Croft Limited |  | 3/3, 3/4, 4/2, 4/3, 4/4, 5/1, 6/2, 6/3, 7/1 | Overhead lines rights Construction and operational access rights | As Bower Croft Limited (above)
Braintree District Council |  | 51/3, 63/12, 63/14, 80/8, 81/6, 81/11, 81/12, 99/5, 101/1, 101/2, 101/3, 102/1, 102/4, 102/14, 102/15 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued via post 18/09/2025 - Phone call received from grantor to discuss the Land Interest Questionnaire / project in further detail 23/09/2025 - Phone call to discuss the Land Interest Questionnaire / project in further detail and address queries 15/01/2026 - Offer letter issued via post 20/02/2026 - Email from grantor advising if they will appoint an agent 03/03/2026 - Email from grantor advising they will represent themselves 05/03/2026 - Emails exchanged to discuss terms, offer letter in greater detail 02/04/2026 - Emails exchanged to discuss terms, the offer letter in further detail 07/04/2026 - Email exchanged to discuss costs 16/04/2026 - Email from grantor advising LSH has been appointed and a proposed fee cap 28/04/2026 - Email from grantor regarding fee cap and approved surveyors rate 05/05/2026 - Emails exchanged to discuss the project in further detail 13/05/2026 - Project letter issued 14/05/2026 – Chaser sent for solicitor details 14/05/2026 – Correspondence regarding appointed solicitors 19/09/2026 – Email confirming further information 21/05/2026 – Email requesting solicitor contact details 26/05/2026 – Email to grantor confirming further details 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Brett Group Properties Limited | OBJ-071 | 131/1, 131/2, 131/4, 131/5, 131/7, 131/9, 132/1, 132/3, 132/6, 132/9, 132/10, 132/11 | Overhead lines rights Construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 24/09/2025 - Emails exchanged to discuss the Land Interest Questionnaire / project in further detail 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser offer letter issued via post 30/03/2026 - Email to grantor to see if assistance is required 13/05/2026 - Project letter issued 13/05/2026 – Chaser sent for solicitor & offer letter 26/05/2026 – Email confirming land agent has been appointed 08/06/2026 - Emails exchanged to confirm instruction 09/06/2026 – Documentation sent between Savills and land agent 25/06/2026 – Phone call from land agent to discuss the project in greater detail 01/07/2026 – Email confirmation of CPO objection 02/07/2026 – Chaser sent via email or solicitor details 05/08/2026 - Letter issued to grantor and agent in response to their objection
Capital Road Safety Limited |  | 50/12, 50/13, 50/15, 51/1, 51/2, 51/4 | Overhead lines rights Construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser offer letter issued via post 27/04/2026 - Door knocking, owner has moved, new owners do not have contact details 02/07/2026 - Chaser sent for solicitor details 14/07/2026 - Chaser sent for solicitor details 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 28/07/2026 - Phone call held with the landowner who confirmed receipt of correspondence, was reviewing the information and had project queries
Caroline Gezzele White |  | 19/11, 21/1, 21/3 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser offer letter issued via post 01/04/2026 - Emails sent to grantor to discuss the project in greater detail. 28/04/2026 - Email to grantor to offer phone call. Phone call to discuss in further detail 19/03/2026 – Chaser letter sent 01/04/2026 – Chaser email sent regarding letter and checking if they have any queries or need further information 28/04/2026 – Emailed grantors and offered phone call to discuss 28/04/2026 – Phone call with grantor to establish and request further details 28/04/2026 – Follow up regarding phone call 06/05/2026 – Chaser sent for solicitor details 13/05/2026 - Chaser sent for solicitor details 02/07/2026 - Chaser sent for solicitor details 14/07/2026 - Chaser sent for solicitor details 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Caroline Rachel Boyle |  | 93/1, 93/2, 93/5, 93/7, 94/2, 94/4, 94/5, 94/8 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 03/09/2025 - Land interest questionnaire issued via post 03/09/2025 - Land interest questionnaire issued via post 09/09/2025 - Emails exchanged with grantors agent about the Land Interest Questionnaire and to discuss the project in further detail 01/10/2025 - Chaser Land Interest questionnaire Issued via post 04/10/2025 - Meeting held with grantors agent to discuss easement, Land Interest Questionnaire and project in further detail 28/10/2025 - Emails exchanged with grantors agent about Land Interest Questionnaire and to discuss the project in greater detail 15/01/2026 - Offer letter issued via post 20/01/2026 - Emails exchanged with grantors agent about offer letter and terms and to discuss the project in further detail 03/02/2026 - Emails exchanged with grantors agent about offer letter and terms and to discuss the project in further detail 10/03/2026 - Summary of key terms issued to grantors agent via email 12/03/2026 - Emails exchanged with grantors agent about offer letter, key terms and to discuss project in further detail 07/04/2026 - Email to agent to discuss project in further detail 30/04/2026 - Confirmation of solicitor details 04/06/2026 - CPO notice letter sent for review 16/06/2026 - Emailed further details and information regarding the project 02/07/2026 - Chaser email for solicitor details 03/07/2026 - Solicitor details emailed 06/07/2026 - Email confirmation that solicitor details have been captured 16/06/2026 - Email clarification requested 07/07/2026 - Email confirmation of requested details and discussion on the project in further detail 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Paul Jonathan Fosh |  | 93/1, 93/2, 93/5, 93/7, 94/2, 94/4, 94/5, 94/8 | Overhead lines rights Construction and operational access rights | As Caroline Rachel Boyle (above)
Paul George Deakin |  | 93/1, 93/2, 93/5, 93/7, 94/2, 94/4, 94/5, 94/8 | Overhead lines rights Construction and operational access rights | As Caroline Rachel Boyle (above)
Carter And Ward Of Wickford Limited |  | 147/20, 148/1, 148/2, 148/6, 148/8, 148/9, 148/10, 148/11, 148/12, 148/13, 148/14, 148/15, 148/16, 148/17, 148/18, 148/19, 148/20, 148/21, 148/23, 148/24, 148/25, 148/26, 148/27, 148/28, 148/29, 148/30, 148/31, 148/32, 148/33, 148/34, 148/35, 148/36, 148/37, 148/38, 148/39, 148/40, 148/41, 148/42, 148/43, 148/44, 148/45, 148/46, 148/48, 148/49, 148/50, 148/51, 148/52, 148/53, 148/55 | Overhead lines rights Construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser offer letter issued via post 24/03/2026 - Emails exchanged with grantors agent about offer letter and terms and to discuss the project in further detail 24/03/2026 - Summary of Key Terms issued and emails exchanged with grantors agent about offer letter and terms and to discuss the project in further detail 16/04/2026 - Email to grantor offering assistance 23/04/2026 - Email chaser offering assistance 06/05/2026 – Chaser sent for solicitor details 13/05/2026 - Project letter issued 08/06/2026 – Scheduled meeting with agent 09/06/2026 – CPO notice emailed 02/07/2026 – Chaser sent for solicitor details 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Cedric Frank George Nott |  | 59/2, 59/3, 59/10, 60/2, 60/7 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser offer letter issued via post 01/04/2026 - Email to agent asking the relationship with regard to finding correct contact details 07/04/2026 - Email from agent confirming different contact 20/04/2026 - Email to agent to confirm receipt 21/04/2026 - Voice mail left for grantor 27/04/2026 - Site meeting with grantor, he will appoint his solicitors to get in contact 13/05/2026 - Project letter issued 02/07/2026 - Chaser sent for solicitor details 14/07/2026 - Chaser sent for solicitor details 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Cemex Uk Operations Limited |  | 93/1, 93/2, 94/7, 94/8, 115/4, 115/6 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 23/10/2025 - Emails exchanged to discuss Land Interest Questionnaire and the project in further detail 15/01/2026 - Offer letter issued via post 20/01/2026 - Emails exchanged to discuss offer letter and the project in further detail 03/02/2026 - Emails exchanged to discuss offer letter and the project in further detail 10/03/2026 - Summary of Key Terms issued to agent via email 08/02/2026 - Email from grantor with completed Land interest questionnaire 17/02/2026 - Email to grantor requesting additional information 16/04/2026 - Emails exchanged to discuss Land Interest Questionnaire and the project in further detail 17/04/2026 - Emails exchanged to discuss Land Interest Questionnaire and the project in further detail 20/04/2026 - Emails exchanged to discuss Land Interest Questionnaire and the project in further detail 06/05/2026 - Chaser regarding solicitor details 13/05/2026 - Chaser sent for solicitor detail and offer letter 13/05/2026 - Project letter issued 22/05/2026 - Alternative land agent details received 09/06/2026 - CPO Notice emailed and offer letter issued 08/06/2026 - Email to agent to confirm information 15/06/2026 - Email from land agent to discuss project in further detail 17/06/2026 - Correspondence continued with Savills and Agent to confirm details 22/06/2026 - further detail and information sent to agent 02/07/2026 - Chaser regarding solicitor details 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Charles Anthony Maurice Boileau |  | 33/10, 33/11, 33/12, 34/1, 34/2, 34/4, 34/5, 34/6, 35/2, 35/3 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser offer letter issued via post 13/05/2026 - Project letter issued
Emily Jane Boileau |  | 33/10, 33/11, 33/12, 34/1, 34/2, 34/4, 34/5, 34/6, 35/2, 35/3 | Overhead lines rights Construction and operational access rights | As Charles Anthony Maurice Boileau (above)
Charmian Rose Goundry | OBJ-060/ OBJ-052 | 97/1, 97/3, 97/5, 98/8, 98/10, 98/11, 98/13 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 08/09/2025 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 09/09/2025 - Phone call held between grantor and Savills to discuss the project in further detail 09/09/2025 - Email exchanges between Savills and grantor to discuss the project in further detail 10/09/2025 - Email exchanges between Savills and grantor's agent to discuss completion of the Land Interest Questionnaire 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 02/10/2025 - Phone call held between grantor and Savills to discuss the project in further detail 27/10/2025 - Teams meeting held between Savills, grantor and agent to discuss the project in further detail 15/01/2026 - Offer letter issued via post 20/01/2026 - Email exchanges between Savills and grantor to discuss queries and the project in further detail 21/01/2026 - Email exchanges between Savills and grantor to discuss queries and the project in further detail 29/01/2026 - Email exchanges between Savills and grantor to discuss queries and the project in further detail 16/02/2026 - Email exchanges between Savills and grantor to discuss queries and the project in further detail 19/02/2026 - Chaser offer letter issued via post 10/03/2026 - Summary of key terms issued to agent via email 13/03/2026 - Email exchanges between Savills and grantor to discuss queries and the project in further detail 16/03/2026 - Email from agent regarding potential land transfer 17/04/2026 - Email exchanges between savills and grantor to discuss queries and the project in further detail 21/04/2026 - Email to agent requesting confirmation of the land transfer 13/05/2026 - Project letter issued 04/06/2026 – Grantor raised concerns and requested further detailed information and clarification 02/07/2026 – Chaser regarding solicitor details 02/07/2026 – Email sent to grantor/agent regarding CPO objection 05/08/2026 - Letter issued to grantor and agent in response to their objection
Chase Loveridge |  | 10/11 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer letter issued via post 05/02/2026 - Signed appendix received via post 24/04/2026 - Letter issued via post requesting solicitor details 13/05/2026 - Project letter issued 02/07/2026 - Chaser sent regarding solicitor details 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Chelmer Housing Partnership Limited |  | 98/1, 98/3, 99/1, 99/2, 99/7, 99/7a, 99/15, 100/1, 100/3, 100/7, 130/13 | Overhead lines rights Construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 15/01/2026 - Offer letter issued via post 21/01/2026 - Email exchanges to discuss the offer letter and the project in further detail 04/02/2026 - Email exchanges to discuss the offer letter and the project in further detail 12/03/2026 - Email exchanges to discuss the offer letter and the project in further detail 13/04/2026 - Email to grantor asking for details of solicitor 28/04/2026 - Email chaser requesting solicitors details 04/05/2026 – Solicitor details received 13/05/2026 - Project letter issued 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Christina Walther |  | 81/10 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 03/10/2025 - Email exchange to discuss the project in further detail 13/10/2025 - Phone call to grantor to arrange meeting to discuss the project in further detail 16/10/2025 - Meeting held with grantor to discuss the project in further detail 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser offer letter issued via post 13/05/2026 - Project letter issued 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
The Executor of Anthony John Walther |  | 81/10 | Overhead line rights | As Christina Walther (above)
Christopher Ernest Dellow |  | 23/8 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser offer letter issued via post 26/03/2026 - Signed appendix received via post 24/04/2026 - Letter to grantor requesting solicitors details via post 27/04/2026 - Email chaser for solicitors details 13/05/2026 - Project letter issued 02/07/2026 – Chaser sent regarding solicitor details 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Nicola Christine Dellow |  | 23/8 | Overhead line rights | As Christopher Ernest Dellow (above)
Christopher Francis Edward Hill |  | 89/1, 89/5, 89/12, 90/1, 90/2, 91/1, 91/2, 91/3, 91/4, 91/5, 91/6, 91/8, 92/1, 92/2, 92/4, 92/5, 92/6, 93/1, 93/2, 93/3, 93/5, 93/6, 93/7, 94/2, 94/4, 94/5, 94/8, 89/3, 89/4, 89/6, 89/7, 89/8 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/10/2025 - Phone call received from grantors agent to confirm their appointment and to discuss the scheme in further detail 19/11/2025 - Emails exchanged between Savills and grantors agent to discuss the project further 10/12/2025 - Emails exchanged between Savills and grantors agent to discuss the project further 15/01/2026 - Offer letter issued via post 20/01/2026 - Emails exchanged between Savills and grantors agent to discuss the offer letter 02/02/2026 - Email from agent requesting documents of existing rights 11/03/2026 - Summary of key terms issued to grantors agent via email 13/05/2026 - Project letter issued 02/07/2026 - Chaser sent regarding solicitor details 03/07/2026 – Land agent confirmed solicitor details 06/07/2026 – Confirmation from Savills confirming details have been captured 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Christopher John Blewett | OBJ-025 | 37/9, 37/10, 38/2, 38/4, 38/5, 38/6, 38/7, 38/8, 38/9, 38/10, 38/11, 38/13, 39/2 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 13/10/2025 - Phone call received to arrange a site meeting to discuss the project in further detail 30/10/2025 - Meeting held between Savills and grantor to discuss the project in further detail 04/11/2025 - Emails exchanged to discuss the project in further detail and address queries 15/01/2026 - Offer letter issued via post 20/01/2026 - Email advising they have appointed a land agent 26/01/2026 - Phone call received from grantor to discuss the project in further detail and address queries 28/01/2026 - Phone call received from grantor to discuss the project in further detail and address queries 02/02/2026 - Emails exchanged with grantor to address queries / discuss the project 03/02/2026 - Emails exchanged with grantors agent to discuss the project in further detail 05/02/2026 - Emails exchanged with grantors agent to discuss the project in further detail 02/03/2026 - Phone call received from grantors agent to discuss the project in further detail 10/03/2026 - Summary of Key Terms issued to agent via email 13/04/2026 - Email to agent requesting solicitors information 16/04/2026 - Emails exchanged with agent to discuss the project in further detail 27/04/2026 - Emails exchanged with grantors agent to discuss the project in further detail 28/04/2026 - Email to agent requesting solicitors details 13/05/2026 - Project letter issued 08/06/2026 – Email to arrange meeting 02/07/2026 - Email sent to grantor/agent regarding CPO objection 02/07/2026 – Response provided via email regarding objection and request from agent regarding amendments 05/08/2026 - Letter issued to grantor and agent in response to their objection
Jane Shelagh Blewett | OBJ-025 | 37/9, 37/10, 38/2, 38/4, 38/5, 38/6, 38/7, 38/8, 38/9, 38/10, 38/11, 38/13, 39/2 | Overhead lines rights Construction and operational access rights | As Christopher John Blewett (above)
Christopher John Clark |  | 19/7 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer letter issued via post 24/01/2026 - Emails exchanged with grantors to discuss the project in further detail 12/03/2026 - Emails exchanged with grantor to discuss the project in further detail 22/04/2026 - Emailed grantors requesting update 13/05/2026 - Project letter issued 02/07/2026 - Chaser sent regarding solicitor details 14/07/2026 - Chaser sent regarding solicitor details 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Rosemary Lawrie |  | 19/7 | Overhead line rights | As Christopher John Clark (above)
Christopher Stokes |  | 145/2 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser offer letter issued via post 01/04/2026 - Investigating further to find additional contact details due to no response to date from grantor 13/05/2026 - Project letter issued 02/07/2026 - Chaser sent regarding solicitor details
Church Commissioners For England |  | 59/6, 59/9, 60/4, 60/9, 60/12, 60/13, 60/14, 61/1, 131/6, 131/8 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser offer letter issued via post 30/03/2026 - Email received from grantor to confirm that their interest in the land only relates to the mines and minerals 07/04/2026 - Email to grantor requesting information regarding the surface owner 13/05/2026 - Project letter issued 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Clive Lodge |  | 148/60, 148/61, 149/5 | Overhead lines rights Construction and operational access rights | 08/09/2025 - Land Interest Questionnaire issued via post 01/10/2025 - Phone call received from grantor to arrange a site meeting 16/10/2025 - Site meeting held with grantor to discuss to project in further detail
Mark Neller |  | 148/60, 148/61, 149/5 | Overhead lines rights Construction and operational access rights | As Clive Lodge (above)
Alan Payne |  | 148/60, 148/61, 149/5 | Overhead lines rights Construction and operational access rights | As Clive Lodge (above)
Paul Brown |  | 148/60, 148/61, 149/5 | Overhead lines rights Construction and operational access rights | As Clive Lodge (above)
Colin David Magness |  | 18/16, 18/17, 19/1, 19/2, 19/3, 19/4, 19/13, 21/4, 21/5 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 13/10/2025 - Emails exchanged between grantor and Savills to discuss the project in greater detail 20/10/2025 - Meeting held with grantor and emails exchanged between grantor and Savills to discuss the project in greater detail 24/10/2025 - Emails exchanged between grantor and Savills to discuss the project in greater detail 29/12/2025 - Emails exchanged between grantor and Savills to discuss the project in greater detail 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser offer letter issued via post 13/05/2026 - Project letter issued 02/07/2026 - Chaser sent regarding solicitor details
Colin Gary Tarner |  | 8/6, 8/8, 8/9 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser offer letter issued via post 01/04/2026 - Emails sent to grantor to discuss the project in greater detail. 27/04/2026 - Doorknocking exercise carried out to establish contact with grantor 28/04/2026 - Email to grantor to offer phone call. Phone call to discuss in further detail 13/05/2026 - Project letter issued 15/05/2026 – Phone call with grantor to discuss project details, received confirmation of intention to sign documentation and confirm solicitor details 02/07/2026 – Chaser sent regarding solicitor details 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Colin Tunstall |  | 146/18, 146/23, 146/30, 146/31, 147/5 | Overhead lines rights Construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 13/10/2025 - Phone call received to discuss the project in further detail 27/10/2025 - Meeting held with grantor to discuss the project in further detail 15/01/2026 - Offer letter issued via post 26/01/2026 - Signed appendix received via post 28/04/2026 - Email to chase for solicitor details 13/05/2026 - Project letter issued 16/06/2026 – Agent requested documentation and further details agreed 16/06/2026 – Response from Savills to clarify project details 02/07/2026 – Email chaser sent requesting solicitor details 20/07/2026 – Sent documentation to Agent 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
The Executor of Ann Martina Tunstall |  | 146/18, 146/23, 146/30, 146/31, 147/5 | Overhead lines rights Construction and operational access rights | As Colin Tunstall (above)
Colne Valley Railway Company Limited |  | 50/12, 50/15, 51/1, 51/4, 51/6, 51/8 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 25/10/2025 - Emails exchanged between Savills and grantor to discuss the Land Interest Questionnaire / project in further detail 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser offer letter issued via post 31/03/2026 - Email to grantor to discuss the Land Interest Questionnaire / project in further detail 13/05/2026 - Chaser sent regarding solicitor details and offer letter 08/04/2026 - Emails exchanged regarding project details and deadlines 13/05/2026 - Project letter issued 18/05/2026 - Email received confirming grantor details 18/05/2026 - Email correspondence with grantor to confirm further details 15/06/2026 – Confirmation that further information will be provided 02/07/2026 – Chaser emailed regarding solicitor details 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Conor David John Black |  | 148/38 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 22/09/2025 - Phone call received to discuss the project / Land Interest Questionnaire in further detail. 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 13/10/2025 - Phone call received to discuss the project / Land Interest Questionnaire in further detail 21/10/2025 - Phone call received to discuss the project / Land Interest Questionnaire in further detail 27/10/2025 - Meeting held between Savills and grantor to discuss the project in further detail 15/01/2026 - Offer letter issued via post 10/02/2026 - Phone call received to discuss offer letter and queries 01/04/2026 - Email exchanges regarding terms, offer letter and solicitor details 21/04/2026 - Emails exchanged between grantor and Savills to discuss the project in greater detail 13/05/2026 - Project letter issued 02/07/2026 – Chaser emailed regarding solicitor details 14/07/2026 - Chaser emailed regarding solicitor details 15/07/2026 – Solicitor details received and confirmation sent regarding key dates
Erin Grace Hughes |  | 148/38 | Overhead line rights | As Conor David John Black (above)
Cornerstone Telecommunications Infrastructure Limited |  | 10/14, 11/1, 11/2, 11/3, 11/3a, 11/7, 11/12, 12/1, 12/2, 51/11, 52/1, 52/5, 52/7, 52/7a, 52/7b | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire issued via post
Countryside Properties (UK) Limited |  | 144/4, 145/1, 145/3, 145/8, 145/13, 145/14, 145/15, 145/16, 146/12, 146/34 | Overhead line rights construction and operational access rights land rights | 03/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire issued via post 07/10/2025 - Phone call and email to grantor to discuss the project in further detail. 06/11/2025 - Phone call and email to LH interest to discuss their FH part of the project in further detail. 17/11/2025 - Email received from LH intrest discussing Land Interest Questionnaire / project in further detail 20/11/2025 - Site meeting booked with LH to discuss the FH part 25/11/2025 - Email received from LH discussing Land Interest Questionnaire / project in further detail 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Countryside Zest (Beaulieu Park) LLP |  | 115/1, 116/1, 116/2, 116/3, 117/1, 117/2, 117/6, 117/7, 117/8, 117/11, 117/12, 117/13, 117/14, 117/15, 117/16, 118/1, 118/4 | Overhead line rights construction and operational access rights land rights | 08/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued 15/01/2026 - Offer letter issued 19/03/2026 - Chaser offer letter issued 23/04/2026 - Email to grantor to see whether they have any further queries / concerns regarding the project 13/05/2026 - Project letter issued 14/05/2026 – Chaser sent regarding solicitor details 21/05/2026 – Phone call regarding further queries / information regarding the project 21/05/2026 – Email confirming project information and offer letter 17/06/2026 – Correspondence with solicitor 02/07/2026 – Correspondence with agent
Crossbrook Farms Limited | OBJ-026 | 39/3, 39/4, 39/5, 39/6, 39/7, 39/8, 39/9, 39/10, 39/11, 39/12, 39/13, 39/14, 40/1, 40/2, 40/3, 41/1, 41/2 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest via post 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser offer letter issued via post 07/04/2026 - Information requested and sent offer letter 13/04/2026 - Email confirming land agent has been appointed 16/04/2026 - Email received from agent with requested documentation 27/04/2026 - Door knocking exercise carried out to establish contact with grantor 30/04/2026 - Phone call to grantor to discuss the returned appendix. No answer 08/06/2026 - Email exchanged regarding meeting with agent 18/06/2026 - Email exchanges with agent to confirm further details and discuss further meetings 02/07/2026 - Chaser email chased regarding solicitor details 02/07/2026 - Email sent to grantor/agent regarding CPO objection 02/07/2026 – Email from agent to request amendments 05/08/2026 - Letter issued to grantor and agent in response to their objection
D.A. Phillips & Co Limited |  | 145/5, 145/6 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 20/01/2025 - Phone call with grantor ref Land Interest Questionnaire 19/03/2026 - Chaser offer letter issued via post 13/05/2026 - Project letter issued 08/07/2026 – Phone call with grantor to confirm offer and intention to sign appendix
Craig Hampton |  | 145/5 | Overhead line rights | As D.A Phillips & Co Limited (above)
Curt John Hodson |  | 145/6 | Overhead line rights | As D.A Phillips & Co Limited (above)
David Clive Hedges |  | 10/5, 10/6 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter Sent via post 21/10/2025 - Letter stating who deals with the land 27/10/2025 - Site meeting arranged for 06/11/2025 06/11/2025 - Site meeting with grantor to discuss access and issues 07/11/2025 - Email sent with meeting minutes and engagement survey 19/03/2026 - Chaser offer letter sent via post 30/03/2026 - Offer letter returned via post advising they do not agree to a permanent easement 08/04/2026 - Phone call to grantor to discuss note on the returned appendix. No answer. 13/05/2026 - Project letter issued 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 27/07/2026 - Solicitor details received
Sylvia Mary Allworthy |  | 10/5, 10/6 | Overhead line rights | As David Clive Hedges (above)
The Executor of Ronald Edward Allworthy |  | 10/5, 10/6 | Overhead line rights | As David Clive Hedges (above)
David Cooper & Jacqueline Anne Watson |  | 44/9, 44/10, 44/11, 45/1, 45/5 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post 17/10/2025 - Email from family member to advise that David has passed away 27/10/2025 - Email sent proposing dates/times for a call for the agents information 17/11/2025 - Emailed phone number to discuss project in greater detail 15/11/2025 - Offer Letter sent out via post 10/03/2026 - Summary of Terms issued to agent via emai 13/05/2026 - Project letter issued 04/06/2026 – Correspondence regarding arranging a meeting 01/07/2026 – Site meeting attended and minutes sent to grantor. Queries were raised 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
David Frank Nott | OBJ079 | 57/2, 57/3, 57/4, 57/5, 58/1, 58/2, 58/3, 58/6, 58/8, 58/9, 58/11, 58/12, 59/1, 59/6, 59/9, 60/4, 60/9, 60/12, 60/14, 61/1 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter Sent via post 20/10/2025 - Phone call requesting site meeting 12/11/2025 - Site meeting held, landowner confirmed willingness to negotiate 13/11/2025 - Email sent to confirm 2 payments for the towers 19/01/2026 - Phone call with grantor to state they have received the offer letter and they are instructing a land agent 21/01/2026 - Emails exchanged between agent and Savills to discuss the project in greater detail 02/02/2026 - Emails exchanged between agent and Savills to discuss the project in greater detail 04/02/2026 - Emails exchanged between grantor and Savills to discuss the project in greater detail 10/03/2026 - Summary of Terms issued to land agent 30/03/2026 - Email to agent confirming cable and wireless are being investigated 01/04/2026 - Email from agent confirming relationship 02/04/2026 - Emails exchanged between agent and Savills to discuss the project in greater detail 08/04/2026 - Emails exchanged between agent and Savills to discuss the project in greater detail 05/05/2026 - Emails exchanged between agent and Savills to discuss the project in greater detail 13/05/2026 - Emails exchanged between agent and Savills to discuss the project in greater detail 13/05/2026 - Project letter issued 09/06/2026 – CPO notice sent to agent 18/06/2026 – Emails exchanged between agent and Savills to discuss the project in greater detail 22/06/2026 - Emails exchanged between agent and Savills to discuss the project in greater detail 24/06/2026 – Documentation issued to agent for client review 01/07/2026 - Email sent to grantor/agent regarding CPO objection 02/07/2026 – Chaser email sent regarding solicitor details 14/07/2026 – Email correspondence to arrange meeting 05/08/2026 - Letter issued to grantor and agent in response to their objection
Suzanne Janet Nott | OBJ080 | 57/2, 57/3, 57/4, 57/5, 58/1, 58/2, 58/3, 58/6, 58/8, 58/9, 58/11, 58/12, 59/1, 59/6, 59/9, 60/4, 60/9, 60/12, 60/14, 61/1 | Overhead lines rights Construction and operational access rights | As David Frank Nott (above)
David James Anstee |  | 115/10, 115/13 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post 19/03/2026 - Chaser offer letter sent via post 28/04/2026 - Door knocking exercise carried out to establish contact; previous owners have moved but current ones will contact them 13/05/2026 - Project letter issued 19/06/2026 – Phone call to establish potential details of current grantor 02/07/2026 – Discussion with agent via email regarding the project in further detail 02/07/2026 – Chaser email for solicitor details 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Doris Theresa Anstee |  | 115/10, 115/13 | Overhead line rights | As David James Anstee (above)
David John Burton |  | 44/7 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 08/09/2025 - Phone call re Land Interest Questionnaire 01/10/2025 - Chaser Letter sent via post 16/10/2025 - Site meeting held. Grantor willing to negotiate and accommodate 19/03/2026 - Chaser offer letter sent via post 27/04/2026 - Email sent to grantor to request solicitors details 28/04/2026 - Chaser email sent to grantor requesting solicitors details 13/05/2026 - Project letter issued 02/07/2026 - Chaser email sent to grantor requesting solicitors details 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 29/07/2026 - Phone call held with the grantor to confirm contact details and discuss future correspondence arrangements
Jill Margaret Burton |  | 44/7 | Overhead line rights | As David John Burton (above)
David John Grantham |  | 148/39 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 17/09/2025 - Phone call with grantor discussing the Land Interest Questionnaire 01/10/2025 - Chaser Letter sent via post 16/10/2025 - Phone call to arrange site meeting 19/03/2026 - Chaser offer letter sent via post 06/05/2026 - Phone call made to discuss the offer letter and concerns regarding the potential impact of the proposed easement on a future property sale; voicemail left 13/05/2026 - Project letter issued 13/05/2026 - Email issued chasing solicitor details and seeking an update on the offer letter 01/06/2026 - Phone call held regarding the project and progression of the matter, with confirmation that solicitor details would be provided 02/07/2026 - Agent correspondence received via email confirming representation of the landowner 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 28/07/2026 - Phone call held with the landowner who raised queries regarding the proposed deed and requested a further discussion 06/08/2026 - Follow up email issued regarding the matter
Linda Kadesh |  | 148/39 | Overhead line rights | As David John Grantham (above)
David Lawrence Bolton | OBJ-019 | 119/2, 119/4, 119/6, 119/12, 119/13, 119/14, 120/1, 120/2, 121/1, 121/2, 121/3, 121/4, 121/5, 122/1, 123/1, 123/2, 123/3, 123/4, 123/5, 123/6, 123/7, 125/2, 125/4, 125/5, 125/6, 120/4 | Overhead lines rights Construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 19/11/2025 - Phone call and email to grantor to discuss the project in further detail. 15/01/2026 - Offer Letter sent via post. 16/01/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 20/01/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 21/01/2026 - Email from agent asking for Heads of Terms 22/01/2026 - Email from agent stating hourly fee and requesting 03/02/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 06/02/2026 - Email received from agent discussing project 26/02/2026 - Email received from agent discussing project 23/03/2026 - Email received from agent discussing project 06/04/2026 – CPO Notice emailed 01/05/2026 – Correspondence with agent and Savills to setup a meeting 11/05/2026 – Online meeting with agent and Savills to discuss the project in greater detail 13/05/2026 - Project letter issued 14/05/2026 – Email from agent to confirm further details from grantor 15/05/2026 – Email from agent discussing further details and important dates 21/05/2026 - Correspondence with agent to setup a meeting with Savills 02/07/2026 – Chaser sent regarding solicitor details 02/07/2026 - Email sent to grantor/agent regarding CPO objection 05/08/2026 - Letter issued to grantor and agent in response to their objection
Stephen John Bolton | OBJ-019 | 119/2, 119/4, 119/6, 119/12, 119/13, 119/14, 120/1, 120/2, 121/1, 121/2, 121/3, 121/4, 121/5, 122/1, 123/1, 123/2, 123/3, 123/4, 123/5, 123/6, 123/7, 125/2, 125/4, 125/5, 125/6, 120/4 | construction and operational access rights Overhead line rights | As David Lawrence Bolton (above)
David Martin Peasgood |  | 19/10 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 26/01/2026 - Signed appendix received via post 28/04/2026 - Email to chase for solicitors details 29/04/2026 - Email from grantor asking for a copy of the letter, emailed across 13/05/2026 - Project letter issued 18/05/2026 – Solicitor details provided and chased up regarding offer letter 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Teresa Jane Peasgood |  | 19/10 | Overhead line rights | As David Martin Peasgood (above)
David Samuel Knox | OBJ-004 | 146/9, 146/18, 146/30, 146/31, 146/33, 147/3, 147/5, 147/7, 147/9, 147/10 | Overhead line rights construction and operational access rights | 08/09/2025- Land interest questionnaire issued via post 01/10/2025 - Chaser Letter Sent via post 13/10/2025 - Phone call grantor 14/10/2025 - Email to agent to proposed dates/times for meeting 21/01/2026 - Email from grantor stating the tower doesn't sit in his boundary 04/02/2026 - Email to grantor confirming that legs of tower sits in his boundary 13/05/2026 - Chaser sent for solicitor details and offer letter 08/06/2026 - Scheduled meeting with agent 09/06/2026 - CPO notice emailed 01/07/2026 - Email sent to grantor/agent regarding CPO objection 02/07/2026 - Chaser sent for solicitor details 30/07/2026 - Site meeting held with grantor and their agent 05/08/2026 - Letter issued to grantor and agent in response to their objection
Dean Gary Harper | OBJ-073 | 147/8 | Overhead line rights | 08/09/2025- Land interest questionnaire issued via post 11/09/2025 - Phone call grantor 01/10/2025 - Chaser letter Sent via post 05/11/2025 - Site meeting held in person 28/01/2026 - Email confirmation from agent acting on behalf of grantor, requested further details and to schedule meeting 11/02/2026 - Email correspondence regarding further details of the project 16/02/2026 - Emails exchanged between agent and Savills to discuss the project in greater detail 17/02/2026 - Emails exchanged between agent and Savills to discuss the project in greater detail and meeting setup 18/02/2026 - Emails exchanged between agent and Savills to discuss the project in greater detail 19/02/2026 - Email confirmation with National Grid providing further details 23/02/2026 - Email correspondence with agent and Savills to provide clarification 09/03/2026 - Chaser email from agent, Savills awaiting further details and assured this will be provided 12/03/2026 - Agent provided summary of key terms via email and raised queries 13/03/2026 - Emails exchanged between agent and Savills to discuss the project in greater detail 16/03/2026 - Emails exchanged between agent and Savills to discuss the project in greater detail 19/03/2026 - Chaser offer letter issued via post 07/04/2026 - Emails exchanged between agent and Savills to discuss the project in greater detail 15/04/2026 - Emails exchanged between agent and Savills to discuss the project in greater detail 28/04/2026 - Emails exchanged between agent and Savills to discuss the project in greater detail and receipt of documentation 29/04/2026 - Email from agent confirming details 13/05/2026 - Correspondence regarding scheduling a meeting 13/05/2026 - Project letter issued 15/06/2026 - Confirmation from Savills that solicitor details have been received and meeting proposed 02/07/2026 - Email sent to grantor/agent regarding CPO objection 13/07/2026 - Confirmation regarding further details 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 05/08/2026 - Letter issued to grantor and agent in response to their objection
Dean John Bezzina |  | 146/25, 146/26, 146/31 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 15/09/2025 - Phone call with grantor 17/09/2025 - Phone call with grantor re Land Interest Questionnaire 18/09/2025 - Phone call with grantor to discuss how the sag and swing fall across his property 27/10/2025 - Phone call ref Teams meeting arranged for 05/11/2025 11/11/2025 - Phone call confirming willingness to negotiate. Site meeting held 19/03/2026 - Chaser letter sent via post 13/05/2026 - Project letter issued 14/05/2026 – Chaser email sent regarding solicitor details 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 29/07/2026 - Phone call attempted to contact the grantor
Jean Pauline Gould |  | 146/25, 146/26, 146/31 | Overhead line rights construction and operational access rights | As Dean John Bezzina (above)
Dean Lowe |  | 146/1, 146/4, 146/5, 146/7, 146/10, 146/15, 146/18, 146/29, 146/30, 147/5 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Letter sent via post 17/10/2025 - Phone call with grantor re Land Interest Questionnaire and to arrange a site meeting 20/11/2025 - Site meeting held, landowner confirmed willingness to negotiate 19/03/2026 - Chaser offer letter sent via post 30/03/2026 - Phone call with grantor, the signed letter is in the post 22/04/2026 - Email to grantor with copy letter, in case previous one has got lost 23/04/2026 - Phone call from grantor confirming letter received 06/05/2026 – Chaser sent regarding solicitor details 13/05/2026 – Chaser sent regarding solicitor details and offer letter 13/05/2026 - Project letter issued 28/05/2026 – Confirmation of solicitor details 04/06/2026 – Email to confirm awaiting approval from National Grid 06/07/2026 – Email grantor to ask for alternative details 14/07/2026 – Chaser email regarding solicitor details 21/07/2026 – Email exchanges between grantor and Savills regarding further details 22/07/2026 – Email to agent to confirm requested information 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Karen Suzanne Lowe |  | 146/1, 146/4, 146/5, 146/7, 146/10, 146/15, 146/18, 146/29, 146/30, 147/5 | Overhead line rights construction and operational access rights | As Dean Lowe (above)
Direct Transportation Limited |  | 84/1, 84/3, 84/4, 84/5, 84/7, 84/8, 84/9, 84/10, 84/11, 84/12, 84/13 | construction and operational access rights Construction compound rights Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 08/09/2025 - Chaser Land Interest Questionnaire issued via Post
Donald James Dear | OBJ-044 | 143/5 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post 05/11/2025 - Landowner confirmed willingness to negotiate through in person meeting 01/04/2026 - Email to chase offer letter 09/04/2026 - Chaser letter sent via post 21/04/2026 - Phone call with grantor about the offer and sending email of confirmation of revised offer to be sent out via post 02/07/2026 - Holding email sent to grantor and agent following receipt of their objection 05/08/2026 - Letter issued to grantor and agent in response to their objection
Denise Susan Ethel Dear | OBJ-044 | 143/5 | Overhead line rights | As Donal James Dear (above)
Donna Marie Sommerford |  | 146/18, 146/21, 146/30, 146/31, 147/5 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post 21/01/2026 - Phone call with grantor to provide details on the project 13/05/2026 - Project letter issued 16/06/2026 - Agent sent over documentation and confirmed further details 16/06/2026 - Emailed key terms and offer letter to agent 16/06/2026 - Emails exchanged between agent and Savills to discuss the project in greater detail 02/07/2026 – Chaser emailed regarding solicitor details 20/07/2026 – Details sent to agent as per request 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Duncan George Deadman |  | 146/18, 146/21, 146/30, 146/31, 147/5 | Overhead line rights construction and operational access rights | As Donna Marie Sommerford (above)
Fullerhold Co Limited |  | 27/6, 27/7, 27/7a, 28/3, 28/5, 29/2, 29/4, 31/5, 31/6, 33/1, 33/2, 33/8, 33/9, 28/5a, 32/16, 32/17, 32/18 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued via post 10/10/2025 - Email from grantor, land was sold to Fuller Holdco Ltd 21/01/2026 - Email from grantor, land was sold to Fuller Holdco Ltd 16/02/2026 - Email from grantor regarding ownership 13/05/2026 - Project letter issued 02/07/2026 – Chaser email regarding solicitor details 02/07/2026 – Email from grantor confirming solicitor details 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Eastern Power Networks Plc |  | 1/1, 1/2, 1/3, 1/4, 3/3, 3/4, 4/2, 4/3, 4/4, 5/1, 25/6, 25/7, 26/1, 26/2, 26/4, 27/1, 27/4, 27/6, 27/7, 27/7a, 28/3, 28/5, 29/2, 29/4, 64/3, 64/4, 65/1, 67/7, 68/5, 99/3, 99/4, 99/8, 111/7, 117/1, 117/6, 117/15, 118/1, 118/6, 128/3, 128/6, 129/7, 130/1, 143/8, 143/12, 144/4, 145/1, 145/3, 145/8, 145/13, 145/14, 145/15, 145/16, 146/1, 146/3, 146/4, 146/5, 146/7, 146/10, 146/15, 146/29, 146/34, 147/4, 147/14, 148/57, 148/62, 149/3, 149/13, 150/6, 150/7, 150/8, 151/1, 151/6, 151/7, 151/8, 151/9, 151/10, 151/11, 151/12, 151/13, 152/2, 152/3, 152/4, 152/5, 152/6, 152/8, 26/1a, 28/5a, 67/15, 67/16, 150/9 | construction and operational access rights Overhead line rights | 03/09/2025 - Land Interest Questionnaire Issued via post 01/10/2025 - Chaser Letter Sent via post 06/10/2025 - Email from agent requesting copy of Land interest Questionnaire 22/10/2025 - Email to agent to request a meeting 10/11/2025 - Email to confirm the working areas 19/11/2025 - Phone call with grantor to confirm access 19/03/2026 - Chaser offer letter sent via post 01/04/2026 - Email to grantor asking if further assistance is required 02/04/2026 - Email grantor chasing for offer letter and if there are any queries 20/04/2026 - Email to grantor confirming the offer relates to all plans 11/05/2026 – Email to schedule a meeting with grantor 13/05/2026 - Project letter issued 18/05/2026 – Grantor requested further information regarding the project 20/05/2026 - Email to schedule a meeting with grantor 21/05/2026 – Grantor further clarification regarding documentation 15/06/2026 – Email correspondence between grantor and Savills to discuss the project in greater detail 02/07/2026 – Email from Savills to agent 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Eastern Power Networks PLC |  | 1/1, 1/2, 1/3, 1/4, 3/3, 3/4, 4/2, 4/3, 4/4, 5/1, 25/6, 25/7, 26/1, 26/2, 26/4, 27/1, 27/4, 27/6, 27/7, 27/7a, 28/3, 28/5, 29/2, 29/4, 64/3, 64/4, 65/1, 67/7, 68/5, 99/3, 99/4, 99/8, 111/7, 117/1, 117/6, 117/15, 118/1, 118/6, 128/3, 128/6, 129/7, 130/1, 143/8, 143/12, 144/4, 145/1, 145/3, 145/8, 145/13, 145/14, 145/15, 145/16, 146/1, 146/3, 146/4, 146/5, 146/7, 146/10, 146/15, 146/29, 146/34, 147/4, 147/14, 148/57, 148/62, 149/3, 149/13, 150/6, 150/7, 150/8, 151/1, 151/6, 151/7, 151/8, 151/9, 151/10, 151/11, 151/12, 151/13, 152/2, 152/3, 152/4, 152/5, 152/6, 152/8, 26/1a, 28/5a, 67/15, 67/16, 150/9 | construction and operational access rights Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued via post 16/10/2025 - Email received from LH discussing Land Interest Questionnaire / project in further detail 22/10/2025 - Email received from LH discussing Land Interest Questionnaire / project in further detail 10/11/2025 - Email received from LH discussing Land Interest Questionnaire / project in further detail 19/11/2025 - Phone call received from LH to discuss the Land Interest Questionnaire
Edmund Nott | OBJ081 | 71/8, 71/13 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter Sent via post 19/03/2026 - Chaser offer letter sent via post 01/04/2026 - Email to agent to check relationship 08/04/2026 - Email reply from grantor 13/05/2026 - Project letter issued 18/06/2026 – Chaser email sent regarding solicitor details 22/06/2026 – Email correspondence with agent regarding project details 24/06/2026 – Existing consents sent to agent for client 02/07/2026 - Email sent to grantor/agent regarding CPO objection 02/07/2026 – Chaser email regarding solicitor details 14/07/2026 – Meeting proposed between agent and National Grid to discuss project in further detail 15/07/2026 – Email to agent to confirm availability to schedule meeting 05/08/2026 - Letter issued to grantor and agent in response to their objection
Edward Albert Webb |  | 84/22 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter Sent via post 07/10/2025 - Phone call from grantor checking access 19/03/2026 - Chaser offer letter sent via post 24/03/2026 - Email from grantor with queries about the project 21/04/2026 - Email response to grantor to discuss project in further detail 22/04/2026 - Emails exchanged with grantor to discuss the project in further detail. 13/05/2026 – Chaser email regarding solicitor details and offer letter 13/05/2026 - Project letter issued 15/06/2026 – Email exchanges between Savills and agent to confirm key terms 23/06/2026 – Chaser email regarding solicitor details 25/06/2026 – Solicitor details provided 13/07/2026 – Confirmation received that negotiations have been paused pending confirmation of the undertaking 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Edward Arthur Heath |  | 102/10, 103/12, 103/15, 103/17, 103/18, 104/6 | Overhead line rights construction and operational access rights | 13/10/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer letter issued via Post 10/03/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 19/03/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 13/05/2026 - Project letter issued 13/05/2026 - Chaser sent regarding solicitor details 18/05/2026 - Details emailed regarding confirmation of land agent 02/07/2026 - Chaser sent regarding solicitor details 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Henry Andrew Heath |  | 102/10, 103/12, 103/15, 103/17, 103/18, 104/6 | Overhead line rights construction and operational access rights | As Edward Arthur Heath (above)
Elizabeth Holly Cook |  | 102/10, 103/12, 103/15, 103/17, 103/18, 104/6 | Overhead line rights construction and operational access rights | As Edward Arthur Heath (above)
Elizabeth Caroline Lloyd | OBJ-033 | 13/5, 13/6, 14/1, 14/2, 14/2a, 14/2b, 15/1, 15/2, 15/3, 15/4, 16/1, 16/2 | Overhead line rights construction and operational access rights | 03/09/2025- Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post 21/10/2025 - Phone call to arrange site meeting for 03/11/2025 03/11/2025 - Site meeting with landowners, discussed the project and easement 05/11/2025 - Email to grantor with site notes 21/01/2026 - Email from agent advising they are now acting on behalf of landowner 04/02/2026 - Email to agent with a copy of the offer letter 13/05/2026 - Project letter issued 14/05/2026 – Email to agent to check if there is anything we can assist with and the returning of the signed appendix 02/07/2026 – Chaser email regarding solicitor details 02/07/2026 - Email sent to grantor/agent regarding CPO objection 05/08/2026 - Letter issued to grantor and agent in response to their objection
Emma Louise Taylor |  | 148/8, 148/9, 148/45 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 23/01/2026 - Email from grantor to advise they are appointing a solicitor 03/02/2026 - Emails exchanged between grantor and Savills to discuss the project 13/03/2026 - Email to agent stating offer is a fixed payment 16/03/2026 - Email from agent disputing fixed payment, wanting this reviewed 28/04/2026 - Email to agent advising Injurious affection claim must be submitted prior to easements being progressed 13/05/2026 - Project letter issued 09/06/2026 – CPO Notice emailed 02/07/2026 – Chaser emailed regarding solicitor details 13/07/2026 – Email from Savills to agent to clarify various queries and provide further detailed information 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Jack Cameron Riddell |  | 148/8, 148/9, 148/45 | Overhead line rights | As Emma Louise Taylor (above)
Environment Agency |  | 10/6, 10/9, 11/5, 11/6, 11/8, 11/10, 11/11, 12/4, 14/1, 22/3, 31/8, 31/11, 32/2, 32/5, 32/7, 39/10, 40/2, 41/2, 49/2, 51/7, 72/2, 72/4, 81/3, 93/5, 93/7, 125/5, 125/6, 131/4, 132/4, 132/6, 132/7, 136/6, 137/3, 137/5, 137/6, 138/1, 138/2, 138/5, 138/8, 147/3, 147/13, 147/16, 147/17, 147/18, 147/19, 147/20, 148/1, 32/8, 32/9, 32/11, 32/12, 32/13, 32/14 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter Sent via post 19/03/2026 - Chaser offer letter sent via post 09/04/2026 - Email from grantor advised still in the process of agreeing to a wayleave 09/04/2026 - Phone call with grantor to confirm details 10/04/2026 - Email from grantor confirming they will review 16/04/2026 - Email to grantor requesting an update 13/05/2026 - Project letter issued 02/07/2026 – Chaser emailed regarding solicitor details 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Essex County Council |  | 1/2, 1/3, 1/6, 1/7, 1/8, 1/9, 2/2, 3/2, 3/3, 3/4, 4/2, 4/4, 5/1, 5/2, 5/4, 5/5, 7/2, 7/7, 7/8, 8/1, 8/2, 8/3, 8/7, 9/3, 9/4, 10/2, 10/7, 10/12, 11/1, 11/3, 11/4, 12/3, 12/6, 12/7, 13/6, 14/2, 14/2a, 14/2b, 15/1, 15/2, 15/3, 15/4, 16/1, 16/2, 16/4, 16/5, 17/2, 17/4, 17/6, 17/8, 17/10, 18/2, 18/3, 18/12, 19/8, 19/9, 19/12, 20/8, 21/3, 21/6, 21/7, 21/8, 21/9, 22/5, 22/6, 22/7, 22/8, 23/6, 24/1, 25/3, 25/5, 25/6, 25/7, 26/1, 26/2, 27/3, 27/7a, 28/1, 28/3, 28/4, 28/5, 29/2, 29/4, 30/4, 30/10, 30/11, 31/3, 31/4, 31/7, 32/6, 32/10, 32/11, 32/12, 32/15, 33/7, 33/8, 33/9, 33/12, 34/1, 34/2, 34/3, 35/1, 36/2, 36/4, 36/5, 36/6a, 36/7, 37/1, 37/3, 37/4, 37/5, 37/6, 37/7, 37/8, 38/1, 38/3, 39/5, 40/2, 41/2, 42/3, 42/5, 42/8, 44/4, 44/5, 44/6, 44/8, 44/10, 44/11, 44/12, 45/1, 45/2, 45/3, 45/6, 45/7, 45/8, 45/9, 45/10, 45/11, 46/1, 46/2, 46/3, 46/4, 46/5, 46/7, 46/8, 46/9, 47/2, 48/1, 48/2, 48/3, 48/4, 49/1, 49/3, 49/4, 49/5, 49/6, 49/7, 50/1, 50/2, 50/4, 50/8, 50/9, 51/9, 51/10, 51/11, 51/13, 52/1, 52/2, 52/3, 52/4, 52/5, 52/6, 52/7a, 52/8, 52/9, 53/3, 53/7, 54/1, 54/2, 54/3, 55/1, 55/5, 55/6, 55/7, 55/8, 55/9, 55/11, 56/1, 56/2, 56/3, 57/4, 57/5, 58/3, 58/4, 58/8, 58/9, 58/10, 59/2, 59/3, 59/4, 59/6, 59/7, 59/9, 60/4, 60/5, 60/14, 61/1, 61/2, 61/3, 61/4, 61/8, 62/2, 63/3, 63/8, 63/9, 63/10, 63/11, 63/16, 64/2, 64/3, 64/4, 65/2, 65/6, 65/9, 65/10, 65/11, 65/12, 65/13, 66/1, 66/2, 67/3, 67/5, 67/7, 67/9, 67/10, 67/12, 67/13, 67/14, 68/3, 68/12, 70/2, 70/4, 70/6, 70/10, 71/3, 71/6, 71/10, 71/11, 71/15, 72/7, 73/3, 74/1, 74/4, 74/5, 75/1, 75/2, 75/6, 75/8, 76/1, 76/2, 76/3, 76/5, 76/6, 77/1, 77/4, 78/1, 78/4, 78/6, 78/7, 79/1, 79/2, 79/6, 79/8, 79/9, 80/1, 80/2, 80/3, 80/5, 80/7, 81/1, 81/2, 81/4, 81/7, 81/9, 82/2, 82/3, 82/4, 82/5, 82/6, 82/7, 82/8, 83/1, 83/7, 83/19, 84/17, 84/20, 84/23, 84/24a, 85/1, 85/2, 85/3, 85/18, 86/1, 86/3, 86/4, 87/1, 87/2, 87/3, 88/1, 88/2, 88/3, 88/4, 89/1, 89/2, 89/9, 89/10, 89/11, 89/13, 89/14, 89/15, 90/1, 90/2, 91/4, 91/5, 91/6, 91/7, 92/1, 92/2, 92/3, 92/4, 92/6, 92/7, 93/2, 93/3, 93/4, 93/6, 93/8, 94/2, 94/3, 94/4, 94/5, 94/6, 94/7, 94/8, 95/1, 95/2, 95/3, 95/4, 95/5, 95/6, 96/3, 96/6, 96/10, 96/11, 97/1, 97/2, 97/3, 97/5, 98/4, 98/5, 98/6, 98/7, 98/10, 98/11, 98/12, 98/13, 99/1, 99/2, 99/3, 99/4, 99/5, 99/6, 99/7, 99/8, 99/10, 99/11, 99/12, 99/14, 100/1, 100/2, 100/3, 100/6, 100/7, 101/1, 101/5, 101/8, 101/15, 101/19, 102/1, 102/3, 102/4, 102/5, 102/7, 102/11, 102/12, 102/14, 103/1, 103/3, 103/4, 103/6, 103/7, 103/9, 103/11, 103/13, 103/15, 103/16, 103/17, 103/19, 103/20, 104/1, 104/2, 104/3, 104/5, 105/1, 105/2, 105/3, 105/4, 105/5, 105/6, 106/1, 106/2, 106/3, 106/4, 107/1, 107/2, 107/3, 107/4, 107/5, 107/6, 108/1, 108/2, 108/3, 108/4, 108/5, 108/6, 108/7, 108/8, 109/1, 109/2, 110/1, 110/4, 110/5, 110/6, 110/7, 110/8, 111/1, 111/2, 111/3, 111/5, 111/6, 112/1, 112/3, 112/5, 113/2, 113/3, 113/4, 113/5, 113/6, 113/7, 114/1, 114/3, 114/4, 115/1, 115/5, 115/8, 115/9, 115/11, 115/16, 115/17, 115/19, 116/1, 116/2, 116/3, 117/1, 117/2, 117/6, 117/7, 117/8, 117/9, 117/10, 117/11, 117/12, 117/13, 117/14, 117/15, 117/16, 118/1, 118/4, 118/6, 119/1, 119/2, 119/4, 119/6, 119/7, 119/14, 120/1, 121/1, 121/2, 121/3, 121/4, 121/5, 122/1, 123/1, 123/2, 123/3, 123/4, 123/5, 123/6, 124/1, 125/1, 125/2, 125/3, 125/4, 125/5, 125/6, 125/7, 125/8, 125/9, 125/10, 125/11, 125/12, 126/1, 126/2, 126/3, 126/4, 127/1, 127/3, 127/4, 128/2, 128/3, 128/6, 128/7, 128/8, 129/1, 129/4, 129/5, 129/7, 129/9, 130/2, 130/3, 130/8, 130/11, 130/13, 130/14, 131/2, 131/3, 131/7, 131/9, 132/3, 132/8, 132/11, 132/12, 133/1, 133/5, 133/8, 134/3, 134/4, 134/5, 134/6, 134/7, 134/9, 134/11, 135/6, 135/8, 137/3, 137/5, 137/6, 138/1, 138/2, 138/3, 138/4, 138/5, 138/6, 138/8, 138/9, 138/10, 138/11, 138/12, 139/1, 139/2, 139/3, 139/4, 139/5, 139/6, 140/1, 140/2, 140/3, 141/1, 141/2, 141/10, 141/14, 141/16, 141/17, 142/2, 142/3, 142/6, 143/2, 143/4, 143/10, 143/11, 143/13, 144/4, 145/1, 145/3, 145/15, 146/5, 146/8, 146/9, 146/10, 146/12, 146/13, 146/15, 146/16, 146/18, 146/28, 146/29, 146/30, 146/32, 146/34, 147/5, 147/6, 147/7, 147/9, 147/10, 147/11, 147/18, 147/19, 147/20, 148/1, 148/2, 148/14, 148/21, 148/30, 148/44, 148/54, 148/62, 149/2, 149/4, 149/6, 149/7, 149/8, 149/9, 149/12, 149/13, 150/2, 150/3, 150/4, 150/5, 150/6, 150/7, 150/8, 150/9, 150/10, 151/1, 151/4, 151/5, 151/6, 151/7, 151/9, 151/10, 151/11, 152/2, 152/3, 152/4, 67/15, 67/16, 67/17, 18/6 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post 19/03/2026 - Chaser offer letter sent via post 23/04/2026 - Email to grantor requesting the best department to deal with the offer letter 24/04/2026 - Email response from grantor putting us in contact with the best placed department for the offer letter 06/05/2026 – Email to agent with copy of offer letter and details regarding the scheme 13/05/2026 - Project letter issued 13/05/2026 – Chaser emailed for solicitor details and offer letter 20/05/2026 – Email exchanges with agent providing further context on the scheme 02/07/2026 – Chaser email regarding solicitor details 09/07/2026 – Agent confirmed solicitor details and confirmation this was captured from Savills 13/07/2026 - Email confirmation solicitor details have been captured 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Essex Wildlife Trust Limited | OBJ-043 | 26/3, 67/8 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post 19/03/2026 - Chaser offer letter sent via post 23/04/2026 - Email to grantor to see if any further assistance is required 13/05/2026 - Project letter issued 14/05/2026 – Email request from agent regarding further project details 14/05/2026 – Chaser emailed regarding solicitor details 16/06/2026 – Requested information from agent regarding terms of business and appendix 02/07/2026 – Chaser sent regarding solicitor details 02/07/2026 - Email sent to grantor/agent regarding CPO objection 06/07/2026 – Email exchanges with agent and Savills discussing key terms 07/07/2026 – Emailed documentation to agent 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 05/08/2026 - Letter issued to grantor and agent in response to their objection
Fairking Limited |  | 79/2, 79/4, 79/7, 79/8, 79/9, 80/2, 80/3, 80/5, 80/6 | construction and operational access rights Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter Sent via post 21/01/2026 - Email from grantor to advise letter received and they have appointed a land agent 01/04/2026 - Email chasing about the offer letter sent to grantor 09/04/2026 - Chaser offer letter sent via post 22/04/2026 - Emails exchanged regarding the offer letter 05/05/2026 – Email to grantor to discuss offer and offered to setup phone call meeting 13/05/2026 - Project letter issued 11/07/2026 - Solicitor information captured from land owner 05/08/2026 - Letter issued to grantor and agent in response to their objection
Fiona Alison Shaw | OBJ-014 | 4/5, 4/6, 5/2, 5/3, 5/6, 5/7, 6/1 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post 23/09/2025 - Phone call from grantor with queries in relation to what she needs to mark on the plan 27/10/2025 - Phone call to confirm site meeting arranged for 06/11/2025 15/01/2026 - Offer letter sent via post 10/03/2026 - Email from agents to confirm they are now acting on behalf of landowner 13/05/2026 - Project letter issued 31/03/2026 - Email chasing grantor for a response 04/04/2026 - Email to agent to confirm rates 14/04/2026 - Email to agent with rate proposals 21/04/2026 - Email from agent to see if the rates can be lowered for graduates 13/05/2026 – Chaser emailed regarding solicitor details 02/07/2026 - Chaser emailed regarding solicitor details 02/07/2026 - Email sent to grantor/agent regarding CPO objection 05/08/2026 - Letter issued to grantor and agent in response to their objection
James Richard Tee | OBJ-014 | 4/5, 4/6, 5/2, 5/3, 5/6, 5/7, 6/1 | Overhead line rights construction and operational access rights | As Fiona Alison Shaw (above)
Francis David Ruffel |  | 53/8, 55/3, 55/4, 55/6 | construction and operational access rights Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter Sent via post 16/10/2025 - Phone call with grantor to advise we have the wrong address 28/10/2025 - Phone call, landowner is happy with the project and no site meeting is needed 19/03/2026 - Chaser offer letter sent via post 07/04/2026 - Phone call with grantor to accept the offer letter amount and letter in post 13/05/2026 - Project letter issued 15/07/2026 - Email from grantor requesting further information on the project and clarification on whether their property was affected 16/07/2026 - Email issued providing further project information and confirming previous verbal acceptance of the offer
Deborah May Ruffel |  | 53/8, 55/3, 55/4, 55/6 | construction and operational access rights Overhead line rights | As Francis David Ruffel (above)
Garry Andrews |  | 141/4, 141/5, 141/6, 141/7, 141/8 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 21/01/2026 - Phone call with grantor requesting help with a land agent 23/01/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 09/03/2026 - Email from agent advising IA claim 11/03/2026 - Email from agent the landowner is not sure about the IA, will look more into it 13/03/2026 - Email from agent with amended Summary of Key Terms 07/04/2026 - Email to agent in relation to the comments of the Summary of Key Terms 29/04/2026 - Email from agent in relation to the injurious affection claim 30/04/2026 - Email from agent in relation to solicitor fees and the offer letter 13/05/2026 - Email exchanged between Savills and agent to answer queries and discuss the project in greater detail 13/05/2026 - Project letter issued 18/05/2026 - Email sent to agent proposing a meeting to discuss outstanding queries 09/06/2026 - CPO Notice emailed 02/07/2026 - Solicitor details chased via agent on email 03/07/2026 - Solicitor details received via agent 06/07/2026 - Confirmation issued that solicitor details had been captured
Kay Andrews |  | 141/4, 141/5, 141/6, 141/7, 141/8 | Overhead line rights | As Gerry Andrews (above)
Gary Clayton - now recorded as 'Rosemarie Samantha Everett and Jennifer May Clayton' |  | 113/3, 113/6, 113/7, 113/7a, 114/1, 114/3, 114/4, 115/19 | construction and operational access rights Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post 28/10/2025 - Phone call with grantor to invite a site meeting 19/03/2026 - Chaser offer letter sent via post 13/05/2026 - Project letter issued 13/05/2026 - Solicitor details chased via email 02/06/2026 - Email received from grantor regarding existing easement arrangements 15/06/2026 - Emails exchanged with grantor regarding existing easement arrangements 17/06/2026 - Email issued confirming queries were being investigated 02/07/2026 - Solicitor details chased via email
Jennifer May Clayton |  | 113/3, 113/6, 113/7, 113/7a, 114/1, 114/3, 114/4, 115/14, 115/18, 115/19 | construction and operational access rights Overhead line rights | As Rosemarie Samanath Everertt and Jennifer May Clayton (above)
Gary Philip Springett |  | 115/2, 115/7 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post
Nigel Alfred Barnes |  | 115/2, 115/7 | Overhead line rights | As Gary Philip Springett
Ian Stokes |  | 115/2, 115/7 | Overhead line rights | As Gary Philip Springett
Robert Bridge |  | 115/2, 115/7 | Overhead line rights | As Gary Philip Springett
Gent Fairhead Aggregates Limited |  | 93/1, 93/2, 94/7, 94/8 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer letter issued via post 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 13/05/2026 - Project letter issued 12/06/2026 - Email from grantor requesting further information on how they are affected by the project 18/06/2026 - Email issued providing further project information and offering a meeting 19/06/2026 - Email from grantor requesting a meeting regarding the project 22/06/2026 - Email exchanged regarding meeting arrangements and attendance 13/07/2026 - Email regarding arranging a site meeting 10/08/2026 - Site meeting held with grantor
Cemex UK Operations Limited |  | 93/1, 93/2, 94/7, 94/8, 115/4, 115/6 | Overhead line rights construction and operational access rights | As Gent Fairhead Aggregages Limited (above)
George Francis Caton | OBJ-034 | 23/7, 23/9, 23/11, 23/13, 24/1, 24/3, 25/3, 25/4, 25/5, 24/2 | construction and operational access rights Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter Sent via post 31/10/2025 - Phone call from grantor to decline a meeting 22/01/2026 - Phone call with grantor to advise he is the chairman for the charity 19/03/2026 - Chaser offer letter sent via post 02/07/2026 - Holding email issued following receipt of CPO objection 05/08/2026 - Letter issued to grantor and agent in response to their objection
Robert Draper Caton | OBJ-034 | 23/7, 23/9, 23/11, 23/12, 23/13, 24/1, 24/2, 24/3, 25/1, 25/2, 25/3, 25/4, 25/5 | construction and operational access rights Overhead line rights | As George Francis Caton (above)
Gillian Rachel Brock |  | 20/4, 20/7, 21/8, 21/9, 22/1 | construction and operational access rights Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter Sent via post 23/01/2026 - Email from agent confirming they are acting on behalf of the landowner 10/03/2026 - Summary of key terms sent to agent via email 24/03/2026 - Email exchanged regarding land ownership details and the project in greater detail 13/05/2026 - Project letter issued 08/06/2026 - Email from grantor regarding outstanding queries 10/06/2026 - Email confirming change of agent representation and update of records 15/06/2026 - Emails exchanged between Savills and grantor to answer queries and discuss the project in greater detail 18/06/2026 - Emails exchanged regarding the offer letter 02/07/2026 - Solicitor details chased via agent on email 15/07/2026 - Email received confirming updated ownership details 15/07/2026 – Email to confirm ownership details have been captured and solicitor details requested 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Stuart Walter Brock |  | 20/4, 20/7, 21/8, 21/9, 22/1, 22/3, 22/4, 22/5, 22/6 | Overhead line rights construction and operational access rights | As Gillian Rachel Brock (above)
Gordon Gray | OBJ-030 | 30/14, 31/1, 31/2 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 10/09/2025 - Phone call from grantor to advise he will complete the Land Interest Questionnaire and return 21/10/2025 - Phone call with grantor to offer site meeting 15/01/2026 - Offer letter issued via post 31/01/2026 - Chasing grantor for a response on the offer letter 31/03/2026 - Email issued chasing a response to the offer letter 13/05/2026 - Project letter issued 13/05/2026 - Chased for solicitor details and signed offer letter 02/07/2026 - Holding email issued following receipt of CPO objection 05/08/2026 - Letter issued to grantor and agent in response to their objection
Graham Anthony Vivian |  | 74/1, 75/1 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter Sent via post 08/09/2025 - Phone call with grantor with no issues 15/09/2025 - Phone call with grantor ref adding tenant information onto Land Interest Questionnaire 29/09/2025 - Phone call to grantor to arrange a site meeting 16/10/2025 - Email from grantor regarding access to the assets on their land 02/10/2025 - Site meeting held with grantor to discuss the project and its requirements in further detail 16/10/2025 - Email to grantor with site meeting minutes 04/02/2026 - Email from grantor to advise land agent and contractor 03/03/2026 - Email to grantor requesting terms of business 11/03/2026 - Email from agent to discuss the project in further detail 06/04/2026 - Summary of key terms issued via email 13/05/2026 - Project letter issued 15/05/2026 - Terms of business received from agent 18/05/2026 - Offer letter issued to agent and records updated 20/05/2026 - Emails exchanged between Savills and agent to discuss the project in greater detail 21/05/2026 - Emails exchanged between Savills and agent to discuss the project in greater detail 22/05/2026 - Email from agent requesting further information and documentation 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Mavis June Vivian |  | 74/1, 75/1 | Overhead line rights | As Graham Anthony Vivian (above)
Graeme Paul Wade - spelt Graeme Paul Wade on comms (also need to mark as blue as objector!) |  | 102/8 | Overhead line rights | 13/10/2025 - Land Interest Questionnaire issued via post 04/11/2025 - Phone call received from grantor to discuss the questionnaire in further detail 10/12/2025 - Phone grantor to request a site meeting. This was declined, however confirmed willingness to negotiate still 15/01/2026 - Offer letter issued via post 23/01/2026 - Phone call received from grantor to discuss the offer and to discuss payment of legal fees 26/01/2026 - Email received from grantor confirming the quote they have received from their solicitor and request absolute clarity that these will be 02/02/2026 - Emails exchanged with grantor regarding payment of legal fees. Awaiting further instruction from National Grid to progress 13/05/2026 - Project letter issued 19/03/2026 - Chaser offer letter issued via post 08/04/2026 - Email issued chasing a response to the offer letter 09/04/2026 - Email received from grantor regarding further details 28/04/2026 - Emails exchanged between agent and Savills to discuss the project in greater detail 01/07/2026 - Holding email issued following receipt of CPO objection 02/07/2026 - Solicitor details chased via email 09/07/2026 - Email received from grantor requesting further information 13/07/2026 - Emails exchanged between agent and Savills to discuss the project in greater detail 15/07/2026 – Phone call received from grantor regarding existing land rights and discussed queries on the project in greater detail
Graham Peter Brian Carter |  | 148/23, 148/26, 148/27, 148/29, 148/33 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post 26/01/2026 - Signed appendix received via post 24/04/2026 - Letter sent to landowner requesting solicitor information via post 13/05/2026 - Project letter issued 02/07/2026 - Chaser sent regarding solicitor details
Jane Marie Wickham |  | 148/23, 148/33 | Overhead line rights construction and operational access rights | As Graham Peter Brian Carter (above)
Lee David Carter |  | 148/23, 148/33 | Overhead line rights construction and operational access rights | As Graham Peter Brian Carter (above)
Gray & Sons (Chelmsford) Limited |  | 137/3, 137/5, 137/6, 138/1, 138/2, 138/4, 138/5, 138/7, 138/8, 138/10, 138/11, 138/12, 139/1, 139/2, 139/4, 139/5, 140/2 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 06/10/2025 - Site meeting held with agent acting for landowner to discuss the project in further detail and existing rights in place 20/01/2026 - Email from grantor with correspondence attached and an offer for the proposed easement 02/02/2026 - Email from agent asking for context to be provided on easement and offer 09/02/2026 - Email from agent regarding the walkovers and the access route 03/03/2026 - Email from agent confirming they act on behalf of the landowner and walkovers 05/03/2026 - Email from agent to confirm the solar farm is on a tenancy agreement 13/03/2026 - Email from agent with Heads of Terms 07/04/2026 - Email to agent requesting that any proposed amendments be provided 30/04/2026 - Email from agent in relation to summary terms and solicitor fees 13/05/2026 - Project letter issued 15/06/2026 - Emails exchanged between Savills and agent to answer queries and discuss the project in greater detail 16/06/2026 - Emails exchanged between Savills and agent to answer queries and discuss the project in greater detail 02/07/2026 - Solicitor details chased via agent on email 03/07/2026 - Solicitor details received via agent 06/07/2026 - Confirmation issued that solicitor details had been captured 07/07/2026 - Emails exchanged between Savills and agent to answer queries and discuss the project in greater detail 08/07/2026 - Emails exchanged between Savills and agent to answer queries and discuss the project in greater detail 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Hammonds Estates LLP | OBJ-049 | 124/1, 125/1, 125/3, 125/5, 125/6, 125/7, 125/8, 125/9, 125/10, 125/11, 126/1, 126/2, 126/3, 127/1, 127/3, 127/4, 128/1, 128/3, 128/4, 128/6, 128/7, 128/8, 129/2, 129/7, 129/8 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 06/10/2025 - Site meeting held with land agent to discuss the project in further detail and existing rights in place 15/01/2026 - Offer letter issued via post to grantor, copy of offer letter issued separately to land agent via email 10/03/2026 - Summary of Terms issued to agent via email 13/05/2026 - Project letter issued 14/05/2026 - Solicitor details chased via agent on email 21/05/2026 - Email from agent regarding access arrangements for the project 26/05/2026 - Email response regarding access arrangements for the project 27/05/2026 - Email from agent regarding working area requirements during construction 04/06/2026 - Emails exchanged between Savills and agent to answer queries and discuss the project in greater detail 04/06/2026 – CPO Notice letter sent for review 08/06/2026 - Email issued providing further information regarding the proposed works 15/06/2026 - Emails exchanged between Savills and agent to answer queries and discuss the project in greater detail 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Hanson Quarry Products Europe Limited | OBJ-011 | 69/2, 70/1, 70/4, 71/9, 71/11, 115/1, 115/2, 116/1, 116/2, 116/3, 117/1, 117/2, 117/6, 117/7, 117/8, 117/9, 117/10, 117/11, 117/12, 117/13, 117/14, 117/15, 117/16, 118/1, 118/4, 118/6 | overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post 23/10/2025 - Email from agent addressing concerns 22/01/2026 - Email from agent requesting Heads of Terms for the proposed easement 28/01/2026 - Email to agent with rates 29/01/2026 - Email from agent confirming rates and wants copies of relevant wayleaves/easements 16/02/2026 - Email to agent with current easement and the proposed payment 13/05/2026 - Project letter issued 19/05/2026 - Email from agent regarding existing rights and further details 15/06/2026 - Emails exchanged regarding existing rights, professional fees and the project in greater detail 01/07/2026 - Holding email issued following receipt of CPO objection 02/07/2026 - Emails exchanged regarding existing rights and the project in greater detail 02/07/2026 - Solicitor details chased via agent on email 02/07/2026 - Solicitor details provided by land agent 05/08/2026 - Letter issued to grantor and agent in response to their objection
Harriet Hull |  | 83/4, 83/7, 84/18, 84/19, 84/21, 84/23, 84/24, 84/24a, 84/25 | Overhead line rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter Sent via post 07/10/2025 - Phone call with grantor, no longer needs chaser letters sent 17/10/2025 - Phone call to grantor re site meeting 19/03/2026 - Chaser letter sent via post 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Laurence John Hull |  | 83/4, 84/25 | Overhead line rights | As Harriet Hull (above)
Oliver Harold Wass |  | 83/7, 84/18, 84/19, 84/21, 84/23, 84/24, 84/24a | Overhead line rights construction and operational access rights access rights | As Harriet Hull (above)
Harry Edward Baines | OBJ-040 | 12/3, 12/4, 12/5, 12/6, 12/7, 12/8, 12/9, 13/1, 13/3 | Overhead line rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer letter issued via post 19/01/2026 - Email from agent stating they are acting on behalf of the landowner and requesting a copy of the standard easement 23/01/2026 - Email to agent with copy of National Grid's standard compensation framework 19/02/2026 - Email from agent asking to confirm reasonable costs 09/03/2026 - Email to agent confirming benchmark fees. Email back to confirm fees are not acceptable 16/03/2026 - Email to agent reference the fees 13/05/2026 - Project letter issued 14/05/2026 - Solicitor details chased via agent on email 17/06/2026 - Phone call regarding project communications and CPO objection 02/07/2026 - Solicitor details chased via agent on email 02/07/2026 - Email sent to grantor/agent regarding CPO objection 05/08/2026 - Letter issued to grantor and agent in response to their objection
Suzanne Baines | OBJ-040 | 12/3, 12/4, 12/5, 12/6, 12/7, 12/8, 12/9, 13/1, 13/3 | Overhead line rights Construction and operational access rights | As Harry Edward Baines (above)
Hasan Salih |  | 146/22, 146/31 | Overhead line rights Construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer letter issued via Post 19/03/2026 - Chaser offer letter sent via post 01/04/2026 - Email to grantor asking if they need further assistance 13/05/2026 - Project letter issued 16/06/2026 - Summary of Key Terms and offer letter issued to agent via email 16/06/2026 - Agent confirmed instruction and Terms of Engagement, and project correspondence issued 16/06/2026 - Email from agent regarding the CPO process and notices 02/07/2026 - Solicitor details chased via agent on email 20/07/2026 – Documentation issued to agent as requested 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Hazel Kay Lock |  | 140/3, 141/1, 141/14, 141/18, 141/19, 141/20, 141/21 | Overhead line rights Construction and operational access rights | 08/09/2025 - Land interest questionnaire issued 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 06/10/2025 - Phone call stating land has been sold 21/10/2025 - Phone call with landowner to arrange a site meeting 15/01/2026 - Offer letter issued via Post 19/03/2026 - Chaser offer letter sent via post 11/05/2026 - Phone call with grantor to discuss the project in greater detail 13/05/2026 - Project letter issued 20/05/2026 - Signed appendix received via post 20/05/2026 - Phone call with grantor regarding solicitor details 02/07/2026 - Solicitor details chased via email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Hazel Pamela Cooper |  | 65/5 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/10/2025 - Phone call from grantor asking how he is affected 15/01/2026 - Offer letter issued via Post 27/02/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 23/03/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 13/05/2026 - Project letter issued 15/05/2026 - Email from agent requesting further project information 21/05/2026 - Email issued providing an update regarding project requirements 04/06/2026 - CPO notice emailed 08/06/2026 - Solicitor details provided by agent 09/06/2026 - Confirmation issued that solicitor details had been captured 17/06/2026 - Email regarding arranging a meeting with the grantor 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Patrick James Thirkell Cooper |  | 65/5 | Overhead line rights | As Hazel Pamela Cooper (above)
Helen Bryden Barr | OBJ-057 | 133/3, 133/4, 133/7, 134/1, 134/2, 134/3, 134/6, 134/7, 135/3, 135/4, 135/5, 135/6, 135/7, 135/8, 135/9, 136/10, 136/4, 136/5, 136/6, 136/9 | Overhead line rights Construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post 15/01/2026 - Offer letter issued via Post 20/01/2026 - Email from daughter stating she has POA and asked for letters to be sent to her 09/02/2026 - Email to agent advising the letters have been sent to the appropriate parties 16/02/2026 - Email to agent with plan and further clarification 17/02/2026 - Email from agent confirming titles have been sold/split 13/05/2026 - Project letter issued 18/05/2026 - Email received regarding grantor information 26/05/2026 - Email requesting supporting documentation and offering further assistance 04/06/2026 - Copy offer letter issued via email 04/06/2026 - CPO notice emailed 13/06/2026 - Email regarding updated ownership and contact details 18/06/2026 - Ownership details forwarded for records to be updated 02/07/2026 - Solicitor details chased via agent on email 02/07/2026 - Holding email issued following receipt of CPO objection 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 05/08/2026 - Letter issued to grantor and agent in response to their objection
Robert Andrew Barr |  | 133/3, 133/4, 133/7 | Overhead line rights Construction and operational access rights | As Helen Bryden Barr (above)
Helen Catherine Lavender |  | 31/3, 31/10, 32/1, 32/3, 32/4, 32/6, 32/7, 32/9, 32/10, 32/11 | Overhead line rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer letter issued via Post 20/10/2025 - Phone call with grantor, doesn't want a meeting 02/02/2026 - Email from grantor confirming he is a Trustee 03/02/2026 - Email to grantor asking them to clarify the trust situation over the land 17/02/2026 - Email from grantor requesting all correspondence to go to the Trust 01/04/2026 - Email to grantor sending offer letter and offering assistance 13/05/2026 - Project letter issued 16/06/2026 - Email received confirming agent instruction 17/06/2026 - Terms of business and information requested from agent 18/06/2026 – Correspondence between Savills and agent regarding professional fees 15/07/2026 - Solicitor details received 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Mark Anthony Lindsell |  | 31/3, 31/10, 32/1, 32/3, 32/4, 32/6, 32/7, 32/9, 32/10, 32/11 | Overhead line rights Construction and operational access rights | As Helen Catherine Lavender (above)
Caroline Vanessa Lindsell |  | 31/3, 31/10, 32/1, 32/3, 32/4, 32/6, 32/7, 32/9, 32/10, 32/11 | Overhead line rights Construction and operational access rights | As Helen Catherine Lavender (above)
Peter David Lindsell |  | 31/3, 31/10, 32/1, 32/3, 32/4, 32/6, 32/7, 32/9, 32/10, 32/11 | Overhead line rights Construction and operational access rights | As Helen Catherine Lavender (above)
Henny Holdings Limited |  | 64/3, 64/4, 65/1, 79/4, 79/7 | Overhead line rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 12/11/2025 - Site meeting held 15/01/2026 - Offer letter issued via Post 16/02/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 01/04/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 20/04/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 06/05/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail and chase for solicitor details 07/05/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 12/05/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail and requested document review 13/05/2026 - Project letter issued 13/05/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 02/07/2026 - Solicitor details confirmed and captured
Homes England |  | 144/4, 145/1, 145/3, 145/8, 145/13, 145/14, 145/15, 145/16, 146/12, 146/34 | Overhead line rights Construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer letter issued via Post 28/01/2026 - Email from grantor advising they will appoint an agent 28/01/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 19/03/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 13/05/2026 - Project letter issued 14/05/2026 - Solicitor details chased via email 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
HRG Property Investments Limited |  | 31/9 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser offer letter issued via post
Hugh Richard Edwards | OBJ-024 | 19/9, 20/2, 20/3, 21/6, 21/7, 22/2, 22/3, 22/4, 22/5, 22/6, 22/8, 23/1, 21/6a | Overhead line rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter Sent via post 21/01/2026 - Email from agent advising they are acting on behalf of landowner 02/02/2026 - Email to agent asking for terms of business. Email back from agent with terms of business and copy of offer letter 03/02/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 05/02/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 10/03/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 13/05/2026 - Project letter issued 13/05/2026 - Solicitor details and status of offer letter chased 02/07/2026 - Solicitor details chased via agent on email 02/07/2026 - Holding email issued following receipt of CPO objection 05/08/2026 - Letter issued to grantor and agent in response to their objection
Maureen Joyce Edwards | OBJ-024 | 19/9, 20/2, 20/3, 21/6, 21/7, 22/2, 22/3, 22/4, 22/5, 22/6, 22/8, 23/1, 21/6a | Overhead line rights construction and operational access rights access rights | As Hugh Richard Edwards (above)
Ian David Hart |  | 50/12, 50/15, 51/1, 51/4, 51/6, 51/7, 51/8 | Overhead line rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 26/11/2025 - Phone call, meeting arranged to discuss project 27/11/2025 - Email from grantor re site meeting 09/12/2025 - Site meeting, discussed land ownership and planning 10/12/2025 - Email to grantor with meeting minutes and engagement survey 23/01/2026 - Email from solicitor advising they are acting on behalf of landowner 09/02/2026 - Email to solicitor clarifying correspondence received from grantor 01/04/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 22/04/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 13/05/2026 - Project letter issued 21/05/2026 - Email from solicitor confirming they will review summary of key terms 02/06/2026 - Phone call and emails exchanged regarding solicitor instruction and project progress 02/06/2026 – Emailed solicitor to chase for any updates or anything Savills can help with 15/06/2026 - Email chasing agent details to allow negotiations to progress 16/06/2026 - Emails exchanged regarding agent instruction and professional fees 06/07/2026 - Email from agent confirming they are acting on behalf of the landowner 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Irene Mary Elsdon |  | 53/3 | Overhead line rights construction and operational access rights access rights | 03/09/2025 - Land interest questionnaire issued via post 10/10/2025 - Phone call to arrange meeting 14/10/2025 - Site meeting held, noted property is for sale 09/03/2026 - Email from agent asking for draft easement document 10/03/2026 - Summary of Key Terms sent via email 24/04/2026 - Letter issued requesting solicitor details via post 28/04/2026 - Email to grantor chasing solicitor details 13/05/2026 - Project letter issued 16/06/2026 - Email received confirming agent instruction 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Jack Piper Lowe |  | 146/4, 146/5, 146/7, 146/8, 146/11, 146/18, 146/29, 146/30, 147/5 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post 20/11/2025 - Site meeting held with father, he acts on their behalf 19/03/2026 - Chaser letter sent via post 30/03/2026 - Phone call to grantor to chase up off letter acceptance 23/04/2026 - Email to grantor with copy offer letter as requested, they accept the offer and are retuning signed letter via post 23/04/2026 - Email to grantor with offer letter 23/04/2026 - Signed appendix received via email, responded asking for solicitor details 23/04/2026 - Offer letter issued via email at grantor's request 13/05/2026 - Project letter issued 23/04/2026 – Signed appendix received and solicitor details requested 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Tommy Piper Lowe |  | 146/4, 146/5, 146/7, 146/8, 146/11, 146/18, 146/29, 146/30, 147/5 | Overhead line rights construction and operational access rights access rights | As Jack Piper Lowe (above)
Jack William Wright |  | 67/5, 67/9, 67/12 | Overhead line rights construction and operational access rights access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter Sent via post 15/01/2026 - Offer letter issued via post 05/03/2026 - Phone call with grantor to discuss the access surveys 19/03/2026 - Chaser offer letter sent via post 27/04/2026 - Voicemail left for grantor 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Pamela Margaret Wright |  | 67/5, 67/9, 67/12 | Overhead line rights construction and operational access rights access rights | As Jack William Wright (above)
James Harry Reay |  | 9/4, 9/5, 10/2, 10/6, 10/8, 10/9, 10/10 | Overhead line rights construction and operational access rights access rights | 03/09/2025 - Land interest questionnaire issued via post 19/03/2026 - Chaser offer letter sent via post 30/03/2026 - Signed offer letter appendix received via post 27/04/2026 - Voicemail left for grantor to request solicitor details 13/05/2026 - Project letter issued 22/06/2026 - Email from agent regarding project location and access route 23/06/2026 - Email issued providing access route information and responding to project queries 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
James Henry Howard |  | 115/10, 115/15 | Overhead line rights construction and operational access rights access rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser letter sent via post 19/03/2026 - Chaser offer letter sent via post 01/04/2026 - Email to grantor chasing up offer letter 13/05/2026 - Project letter issued 13/05/2026 - Solicitor details chased via email 02/07/2026 - Solicitor details chased via email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
James Robert Bridges |  | 141/19, 141/20, 141/21 | Overhead line rights construction and operational access rights access rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post 15/01/2026 - Offer Letter issued via post 19/03/2026 - Chaser offer letter sent via post 27/04/2026 - Email to grantor requesting solicitor information 13/05/2026 - Project letter issued 14/07/2026 - Solicitor details received 15/07/2026 - Confirmation issued that solicitor details had been captured 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Stella Denise Bridges |  | 141/19, 141/20, 141/21 | Overhead line rights construction and operational access rights access rights | As James Robert Bridges (above)
Janet Elizabeth Hill |  | 136/6, 136/8, 137/2, 137/4 | Overhead line rights construction and operational access rights access rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter issued via post 15/01/2026 - Offer Letter issued via post 19/03/2026 - Chaser Offer Letter issued via post 27/04/2026 - Doorknocking exercise carried out to establish contact 30/04/2026 - Emailed copy of offer letter to grantor and queried if they had and queries or concerns to enable progression of the easement 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 29/07/2026 - Phone call held with a family representative who advised that the matter had been passed to the appointed agent to deal with on behalf of the landowners
Janet Elizabeth Piper |  | 145/10, 145/12, 146/1, 146/2, 146/3, 146/4, 146/5, 146/6, 146/7, 146/10, 146/13, 146/15, 146/16, 146/17, 146/18, 146/19, 146/29, 146/30, 146/31, 147/5 | Overhead line rights construction and operational access rights access rights | 15/12/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser letter issued via post 15/01/2026 - Offer Letter issued via post 26/01/2026 - Phone call received from grantor confirming willingness to negotiate and to confirm acceptance of offer 27/04/2026 - Letter issued to obtain solicitor details 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Janet Elizabeth Wiseman |  | 71/2, 71/4, 71/5 | Overhead line rights construction and operational access rights access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser letter sent via post 08/10/2025 - Phone call with grantor to say she has provided all information before to National Grid 23/10/2025 - Phoned grantor; left voice mail requesting a call back 23/10/2025 - Phone call to grantor to explain the separation between P2R and BTNO scheme 23/10/2025 - Phone call received from land agent confirming their appointment and copy of land interest questionnaire emailed across 12/11/2025 - Email received from agent confirming he will complete the land interest questionnaire with the grantor at their meeting scheduled on the 20/11/2025 15/01/2026 - Offer letter issued to grantor via post and via email to land agent 28/01/2026 - Meeting held between Savills and agent to discuss the project in further detail 11/03/2026 - Summary of Key Terms issued to land agent via email 22/04/2026 - Email to agent asking if they have any queries or concerns following the issue of the summary of key terms 13/05/2026 - Project letter issued 13/05/2026 - Solicitor details chased via email 09/06/2026 - CPO Notice emailed 02/07/2026 - Solicitor details chased via agent on email 06/07/2026 - Solicitor details received via agent 07/07/2026 - Confirmation issued that solicitor details had been updated
Jeremy Adrian Hill |  | 74/2, 74/4, 74/5, 75/2 | Overhead line rights construction and operational access rights access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter Sent via post 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser offer letter issued via post 25/03/2026 - Phone call from received confirming that they do not wish to sign the offer letter 13/05/2026 - Project letter issued 14/05/2026 - Email issued to discuss the project in greater detail and offer further assistance 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 29/07/2026 - Phone call held with the landowner regarding the project and correspondence received
Virginia Ann Hill |  | 74/2, 74/4, 74/5, 75/2 | Overhead line rights construction and operational access rights access rights | As above
Jeremy James Fisher | OBJ-007 | 103/10, 103/11, 104/2, 105/5, 105/6, 104/3, 104/3a, 104/4, 104/5 | Overhead line rights construction and operational access rights access rights | 13/10/2025 - Land interest questionnaire issued via post 17/10/2025 - Phone call from grantor to state that the land parcel is not owned by him 15/01/2026 - Offer letter issued to grantor via post 25/02/2026 - Emails exchanged between Savills and grantors agent to discuss the project in further detail 12/03/2026 - Emails exchanged between Savills and grantors agent to discuss the project in further detail 13/05/2026 - Project letter issued 13/05/2026 - Chasing solicitor details and status of offer letter 08/06/2026 - Meeting scheduled with agent to discuss the project in further detail 09/06/2026 - CPO Notice emailed 09/06/2026 - Email from grantor confirming agent representation 09/06/2026 - Project documentation issued to agent and Terms of Business requested 01/07/2026 - Holding email issued following receipt of CPO objection 02/07/2026 - Solicitor details chased via agent on email
Michael John Sayer | OBJ-007 | 103/10, 103/11, 104/2, 105/5, 105/6, 104/4, 104/5 | Overhead line rights construction and operational access rights | As Jeremy James Fisher (above)
Philip James Hutley | OBJ-007 | 103/10, 103/11, 104/2, 105/5, 105/6, 104/3, 104/3a, 104/4, 104/5 | Overhead line rights construction and operational access rights | As Jeremy James Fisher (above)
Philip James Hutley | OBJ-007 | 103/10, 103/11, 104/2, 105/5, 105/6, 104/3, 104/3a, 104/4, 104/5 | Overhead line rights construction and operational access rights | As Jeremy James Fisher (above)
Jeremy Robin Sibson-Barnes | OBJ-041 | 107/2, 108/4 | Overhead line rights | 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 13/10/2025 - Land interest questionnaire issued via post 15/01/2026 - Offer letter issued via Post. 21/01/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 22/01/2026 - Phone call received from grantor with queries about the project. 26/01/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 03/02/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 09/03/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 23/03/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 01/04/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 20/04/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 22/04/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 23/04/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 27/04/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 28/04/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 01/05/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 05/05/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 11/05/2026 - Meeting held with agent to discuss the project in further detail 13/05/2026 - Project letter issued to grantor 14/05/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 04/06/2026 - CPO Notice emailed 08/06/2026 - Solicitor details received 09/06/2026 - Confirmation issued that solicitor details had been captured 02/07/2026 - Holding email issued following receipt of CPO objection 07/07/2026 - Emails exchanged regarding solicitor fees and the project in further detail 28/07/2026 - Site meeting held with grantor and their agent
Mary Christine Kemp | OBJ-041 | 107/2, 108/4 | Overhead line rights | As Jeremy Robin Sibson-Barnes (above)
Jessica Alice Westrop | OBJ-027 | 54/3, 55/9, 55/10 | Overhead line rights construction and operational access rights access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter Sent via post 15/01/2026 - Offer letter issued via post 30/01/2026 - Phone call received from grantor to discuss their queries and the rights being sought in further detail 09/02/2026 - Email received from agent confirming their appointment to act on this matter for the grantor 18/02/2026 - Emails exchanged with agent discussing the project in further detail 10/03/2026 - Summary of Key Terms issued to agent via email 16/04/2026 - Email exchange with agent to set up a meeting to discuss queries on the key terms 13/05/2026 - Project letter issued 13/05/2026 - Chasing solicitor details and status of offer letter 08/06/2026 - Meeting scheduled with agent to discuss the project in further detail 09/06/2026 - CPO Notice emailed 09/06/2026 - Email from grantor confirming agent details 09/06/2026 - Project documentation issued to agent and Terms of Business requested 01/07/2026 - Holding email issued following receipt of CPO objection 02/07/2026 - Solicitor details chased via agent on email 05/08/2026 - Letter issued to grantor and agent in response to their objection
John Alec Mcmurtrie |  | 42/6, 42/7, 42/9 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter Sent via post 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser offer letter issued via post 23/04/2026 - Email sent to grantor to discuss the project and offer letter in greater detail 24/04/2026 - Email issued requesting solicitor details 24/05/2026 - Email received requesting a call to discuss the project 26/05/2026 - Phone call with grantor to discuss the project in greater detail 26/05/2026 – Details issued to grantor via email 08/06/2026 - Signed appendix received via email 13/05/2026 - Project letter issued 16/06/2026 - Emails exchanged between grantor and Savills to discuss the project in greater detail 17/06/2026 - Emails exchanged between grantor and Savills to discuss the project in greater detail 02/07/2026 - Solicitor details chased via email 13/07/2026 - Solicitor details received 13/07/2026 - Confirmation issued that solicitor details had been captured 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
John Angus Crowther | OBJ-042 | 49/7, 50/1, 50/2, 50/4, 50/8, 50/10, 50/12, 50/13, 50/15, 51/1, 51/2, 51/4, 51/5, 51/7, 50/11 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter Sent via post 15/01/2026 - Offer letter issued via post 03/02/2026 - Email received from agent to discuss the project in further detail 05/02/2026 - Emails exchanged between Savills and grantor to discuss the project in further detail 19/03/2026 - Chaser offer letter issued via post 23/04/2026 - Emails exchanged with agent to discuss the project and offer letter in greater detail 11/05/2026 - Confirmation received agent that John Angus Crowther has passed away and his son will now be taking over 13/05/2026 - Project letter issued 14/05/2026 - Emails exchanged between Savills and grantor to discuss the project in further detail 26/05/2026 - Emails exchanged regarding meeting arrangements and the project in further detail 04/06/2026 - CPO notice emailed 08/06/2026 - Meeting held to discuss the project in further detail 02/07/2026 - Solicitor details chased via agent on email 02/07/2026 - Holding email issued following receipt of CPO objection 05/08/2026 - Letter issued to grantor and agent in response to their objection
John Everett |  | 114/2, 115/12 | Overhead line rights | 15/12/2025 - Land interest questionnaire issued via post 15/01/2026 - Offer letter issued via post 25/02/2026 - Offer letter signed appendix received in the post 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
John Fraser Mcglashan |  | 73/1 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter Sent via post 08/10/2025 - Phone call from grantor wants to know whether her land in affected by the scheme 15/01/2026 - Offer letter issued via post 19/01/2026 - Phone call from grantor to discuss the project in further detail 21/01/2026 - Phone call from grantor to discuss appointing land agent 22/01/2026 - Email received from grantor confirming appointed agent 23/01/2026 - Email sent to grantors land agent to discuss the project 26/01/2026 - Emails exchanged with agent to discuss the project in further detail. 28/01/2026 - Emails exchanged with agent to discuss the project in further detail. 29/01/2026 - Emails exchanged with agent to discuss the project in further detail. 02/02/2026 - Emails exchanged with agent to discuss the project in further detail. 09/02/2026 - Emails exchanged with agent to discuss the project in further detail. 10/03/2026 - Summary of key terms issued to agent via email 13/05/2026 - Project letter issued 13/05/2026 - Solicitor details and status of offer letter chased 13/05/2026 - Emails exchanged with agent to discuss the project in further detail 21/05/2026 - Emails exchanged with agent to discuss the project in further detail 09/06/2026 - Email sent to grantor/agent regarding CPO objection 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Sharron Louise Nichols |  | 73/1 | Overhead line rights | As John Fraser McGlashan (above)
John Frederick Strutt | OBJ-013/ OBJ-054 | 107/1, 107/3, 107/4, 107/5, 108/1, 108/2, 108/5, 108/6, 108/8, 109/1, 109/2, 109/2a, 110/1, 110/2, 110/3, 110/4, 110/5, 110/6, 110/7, 111/2, 111/3, 111/4, 111/5, 111/8, 112/1, 112/2, 112/3, 112/4, 112/5, 113/2, 113/3, 113/4, 113/5, 113/6, 113/7, 113/7a, 114/1, 114/3, 114/4, 115/19 | Overhead lines rights Construction and operational access rights | 13/10/2025 - Land interest questionnaire issued via post via Post. 1/10/2025 - Chaser Land Interest Questionnaire Issued 15/01/2026 - Offer letter issued via Post. 22/01/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 16/02/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 23/04/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 22/01/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 23/04/2026 - Emails exchanged between grantor and Savills, grantor refused to engage any further. 28/04/2026 - Email response to grantor discussing the project and rights they are looking to seek 29/04/2026 - Email received from grantor confirming that they decline to engage any further and enter an easement 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email 02/07/2026 - Email sent to grantor/agent regarding CPO objection 05/08/2026 - Letter issued to grantor and agent in response to their objection
John Hoole | OBJ-053 | 42/6, 42/7 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post via post 03/11/2025 - Site meeting, landowner are concerned with security as had trespassers in the past 07/11/2025 - Email to grantor with site meeting minutes 15/01/2026 - Offer letter issued to grantor via post 26/01/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 16/02/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 27/02/2026 - Emails exchanged between agent and Savills to discuss the project in further detail 11/03/2026 - Emails exchanged between agent and Savills to discuss the project in further detail 12/03/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 21/04/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail, summary of key terms issued via email. 13/05/2026 - Project letter issued 09/06/2026 - CPO notice emailed to agent 01/07/2026 - Holding email issued following receipt of CPO objection 02/07/2026 - Solicitor details chased via agent on email 05/08/2026 - Letter issued to grantor and agent in response to their objection
Julie Ann Hoole |  | 42/6, 42/7 | Overhead lines rights Construction and operational access rights | As John Hoole (above)
John Joseph Murphy |  | 141/2, 141/6, 141/13 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post 19/03/2026 - Chaser offer letter sent via post 30/03/2026 - Email sent to grantor chasing the offer letter 13/05/2026 - Project letter issued 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 30/07/2026 - Phone call with grantor confirming further details and contact requirements
John Michael Crowther |  | 49/7, 50/1, 50/2, 50/4, 50/8, 50/12, 50/13, 50/15, 51/1, 51/2, 51/4, 51/6, 51/8 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter Sent via post 15/01/2026 - Offer letter issued via post 07/04/2026 - Email sent to grantor chasing in relation to the offer letter
John Sidney Blackwell |  | 84/14, 84/15, 85/3, 85/5, 85/6, 85/8, 85/10, 85/11, 85/12, 85/13, 85/14, 85/15, 85/16, 87/1, 85/1 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 08/09/2025 - Chaser Land Interest Questionnaire issued via Post 13/10/2025 - Phone call received from LH with queries about the project.
Samuel John Blackwell |  | 84/14, 84/15, 85/3, 85/5, 85/6, 85/8, 85/10, 85/11, 85/14, 85/15, 85/16, 87/1, 85/1 | Overhead lines rights Construction and operational access rights | As John Sidney Blackwell (above)
Holly Patricia Blackwell |  | 84/14, 84/15, 85/3, 85/5, 85/6, 85/8, 85/10, 85/11, 85/14, 85/15, 85/16, 87/1, 85/1 | Overhead lines rights Construction and operational access rights | As John Sidney Blackwell (above)
John Winston Argent | OBJ-032 | 41/3, 41/4, 42/1, 42/2 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 15/01/2026 - Offer letter issued via post 30/03/2026 - Emails exchanged with agent in relation to the offer letter 13/05/2026 - Project letter issued 13/05/2026 - Solicitor details and status of offer letter chased 02/07/2026 - Solicitor details chased via agent on email 02/07/2026 - Holding email issued following receipt of CPO objection 05/08/2026 - Letter issued to grantor and agent in response to their objection
Gillian Argent | OBJ-032 | 41/3, 41/4, 42/1, 42/2 | Overhead lines rights Construction and operational access rights | As John Winston Argent (above)
Jonathan Charles Burchell |  | 43/4 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter Sent via post 15/01/2026 - Offer letter issued via post 23/03/2026 - Email from solicitor to confirm their client has accepted the offer 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Caroline Elizabeth Burchell |  | 43/4 | Overhead lines rights Construction and operational access rights | As Jonathan Charles Burchell (above)
Jonathan Dixon Smith | OBJ-062 | 96/1, 96/2, 96/7, 96/8, 96/9, 97/1, 97/3, 97/5, 97/6, 97/7, 98/10, 98/11, 98/13 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 15/01/2026 - Offer letter issued via post 20/01/2026 - Email received from grantor discussing the project in further detail 02/02/2026 - Emails exchanged with the landowner discussing the project in further detail 13/05/2026 - Project letter issued 14/05/2026 - Solicitor details chased via email 18/06/2026 - Email from agent requesting copies of existing agreements 22/06/2026 - Emails exchanged between Savills and agent regarding existing agreements 24/06/2026 – Further details and documentation sent to agent 01/07/2026 - Email sent to grantor/agent regarding CPO objection 02/07/2026 - Solicitor details chased via agent on email 05/08/2026 - Letter issued to grantor and agent in response to their objection
Jonathan Peter Douglas-Hughes |  | 117/2, 117/6, 117/7, 117/8, 117/12, 117/14, 117/15, 118/4, 118/6 | construction and operational access rights Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 25/09/2025 - Phone call with grantor to discuss the project in further detail 01/10/2025 - Chaser Letter sent via post 06/10/2025 - Site meeting held with grantor to discuss the project in further detail 12/12/2025 - Phone call attempted and voicemail left to discuss project with the agent 15/01/2026 - Offer letter issued via post 19/03/2025 - Chaser letter issued via post 28/04/2026 - Email sent out to land agent 13/05/2026 - Project letter issued 13/05/2026 - Email sent to land agent chasing the offer letter 02/07/2026 - Solicitor details chased via agent on email
Jonathan Peter Douglas-Hughes |  | 117/2, 117/6, 117/7, 117/8, 117/12, 117/14, 117/15, 118/4, 118/6 | Overhead line rights construction and operational access rights | As Jonathan Peter Douglas-Hughes (above)
Josephine Greta Adams | OBJ-055 | 71/12, 72/1, 72/5, 72/8 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 15/01/2026 - Offer letter issued via post 16/01/2026 - Email received from agent about the project 20/01/2026 - Emails exchanged with the agent about the project 16/02/2026 - Emails exchanged with the agent 13/05/2026 - Project letter issued 09/06/2026 - CPO notice emailed to agent 02/07/2026 - Solicitor details chased via agent on email 02/07/2026 - Email sent to grantor/agent regarding CPO objection 05/08/2026 - Letter issued to grantor and agent in response to their objection
Julia Verity Hughes |  | 84/1, 84/3, 84/4, 84/5, 84/7, 84/8, 84/9, 84/10, 84/11, 84/12, 84/13 | construction and operational access rights Construction compound rights Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter Sent via post 15/01/2026 - Offer letter sent via post 19/03/2026 - Chaser offer letter sent via post 25/03/2026 - Email received from agent in relation to the project 11/05/2026 - Emails exchanged between agent and Savills to discuss the project in further detail 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Julian Barry Paul | OBJ-028 | 53/2 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter Sent via post 15/01/2026 - Offer letter sent via post 19/03/2026 - Chaser offer letter sent via post 13/05/2026 - Project letter issued 13/05/2026 - Solicitor details and status of offer letter chased 02/07/2026 - Solicitor details chased via agent on email 02/07/2026 - Email sent to grantor/agent regarding CPO objection 02/07/2026 - Email from agent regarding the Summary of Terms and project in further detail 05/08/2026 - Letter issued to grantor and agent in response to their objection
Jacqueline Paul | OBJ-028 | 53/2 | Overhead line rights | As Julian Barry Paul (above)
Julian Philip Newton |  | 53/5, 53/6, 53/7, 54/1, 55/1, 55/2, 55/5, 55/11, 56/1, 56/2 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 21/10/2025 - Phone call to landowner to offer site meeting 15/01/2026 - Offer letter issued via post 18/02/2026 - Emails exchanged to discuss the project in further detail 13/05/2026 - Project letter issued 14/05/2026 - Solicitor details chased via email 09/06/2026 - CPO notice sent to grantor 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Gillian Clare Newton |  | 53/5, 53/6, 53/7, 54/1, 55/1, 55/2, 55/5, 55/11, 56/1, 56/2 | Overhead line rights construction and operational access rights | As Julian Philip Newton (above)
Elizabeth Mary Newton |  | 53/5, 53/6, 53/7, 54/1, 55/1, 55/2, 55/5, 55/11, 56/1, 56/2 | Overhead line rights construction and operational access rights | As Julian Philip Newton (above)
June Beatrice Drysdale |  | 132/13, 133/2 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post 15/01/2026 - Offer letter sent via post 19/03/2026 - Chaser offer letter sent via post 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email
John Drysdale |  | 132/13, 133/2 | Overhead line rights | As June Beatrice Drysdale (above)
Karen Suzanne Lowe |  | 146/1, 146/4, 146/5, 146/7, 146/10, 146/15, 146/18, 146/29, 146/30, 147/5 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 17/11/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 20/11/2025 - Meeting held with the landowner to discuss the project in further detail 15/01/2026 - Offer letter was sent via post 19/03/2026 - Chaser Offer letter issued via post 30/03/2026 - Phone call with grantor to discuss the offer letter 22/04/2026 - Email sent to grantor to chase up the offer letter 23/04/2026 - Phone call from grantor confirming receipt of offer letter and that he will send it back in due course 08/09/2025 - Land interest questionnaire issued via post 17/11/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire and offer 20/11/2025 - Meeting held with the landowner to discuss the project in further detail 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser offer letter issued via post 30/03/2026 - Phone call with grantor to discuss the offer letter 22/04/2026 - Email sent to grantor to chase up the offer letter 23/04/2026 - Phone call from grantor confirming receipt of the offer letter and intention to return signed documentation 06/05/2026 - Solicitor details requested 13/05/2026 - Project letter issued 13/05/2026 - Solicitor details and status of offer letter chased 28/05/2026 - Solicitor details confirmed 04/06/2026 - Emails exchanges regarding solicitors with National Grid 06/07/2026 - Phone call and email correspondence regarding solicitor details and legal fee arrangements 14/07/2026 – Alternative solicitor details chased via email 21/07/2026 - Emails exchanged regarding solicitor appointment and legal fee arrangements 22/07/2026 - Email issued regarding progression of solicitor instruction
Dean Lowe |  | 146/1, 146/4, 146/5, 146/7, 146/10, 146/15, 146/18, 146/29, 146/30, 147/5 | Overhead line rights construction and operational access rights | As Karen Suzanne Lowe (above)
Katy Emily Shadbolt |  | 76/5 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 17/11/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire 20/11/2025 - Emails exchanged with grantors to discuss project in further detail 15/01/2026 - Offer letter was sent via post 19/03/2026 - Chaser Offer letter issued via post 13/05/2026 - Project Update letter issued 08/04/2026 - Site meeting held with grantors to discuss the project in further detail 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Paul John Shadbolt |  | 75/8, 76/2, 76/3, 76/5 | Overhead line rights construction and operational access rights | As Katy Emily Shadbot (above)
Keith Trevor Ripper |  | 45/7, 45/9, 45/10, 46/1, 46/2, 46/3, 46/4, 46/5, 46/6, 46/7, 47/3, 47/4, 49/1, 49/2, 49/6, 49/7, 50/1, 50/2, 50/4, 50/8 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 15/01/2026 - Offer letter was sent. 19/03/2026 - Chaser Offer letter issued via post 27/04/2026 - Site door knocked to obtain contact information 30/04/2026 - Email sent to grantor to discuss the offer letter 13/05/2026 - Project letter issued 13/05/2026 - Email sent to grantor chasing the offer letter and solicitor details 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Kellie Jane Longman (Thomas) |  | 148/35 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post via post. 23/10/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 24/10/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 15/01/2026 - Offer letter was sent. 06/02/2026 - Emails exchanged with the grantor about the offer letter and easement 16/02/2026 - Emails exchanged with agent about the project 10/03/2026 - Summary of key terms was sent 11/03/2026 - Emails exchanged with agent regarding the Summary of Key Terms and project in further detail 07/04/2026 - Emails exchanged with agent regarding the Summary of Key Terms and project in further detail 30/04/2026 - Emails exchanged with agent regarding the Summary of Key Terms and project in further detail 13/05/2026 - Project letter issued 18/05/2026 - Email sent to agent suggesting a meeting to discuss project queries 27/05/2026 - Email from agent regarding meeting arrangements 09/06/2026 - CPO Notice emailed 09/06/2026 - Email regarding meeting arrangements 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Kent & Sussex (Runwell) Limited |  | 145/12, 146/6, 146/13, 146/14, 146/16, 146/31 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 15/01/2026 - Offer letter was sent. 19/03/2026 - Chaser Offer letter issued via post 13/05/2026 - Project letter issued
Kent & Sussex Properties Limited |  | 145/12, 146/6, 146/13, 146/14, 146/16, 146/31 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 15/01/2026 - Offer letter was sent. 19/03/2026 - Chaser Offer letter issued via post 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 03/08/2026 - Email received regarding a winding up order and informed of new 05/08/2026 - Call to discuss the right peopke we need to now liaise with regarding this land
Michael George Hutley |  | 145/12, 146/6, 146/13, 146/16, 146/31 | Overhead line rights construction and operational access rights | As Kent & Sussex Properties Limited (above)
Laurence John Hull |  | 83/4, 84/25 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 07/10/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 17/10/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 15/01/2026 - Offer letter was sent. 19/03/2026 - Chaser offer letter issued via post 13/05/2026 - Project letter issued 02/07/2026 - Correspondence with agent and Savills
Harriet Hull |  | 83/4, 83/7, 84/18, 84/19, 84/21, 84/23, 84/24, 84/24a, 84/25 | Overhead line rights construction and operational access rights | As Laurence John Hull (above)
Leann Claire Burridge |  | 45/10, 46/2 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 09/09/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 15/01/2026 - Offer letter was sent. 27/01/2026 - Phone call received from grantor about solicitors 01/04/2026 - Email sent to grantor chasing up the offer letter 27/04/2026 - Email sent chasing for solicitor details 13/05/2026 - Project letter issued 14/05/2026 - Phone call received confirming appointment of an agent and intention to appoint a solicitor 08/06/2026 - Meeting scheduled with agent to discuss the project in further detail 09/06/2026 - CPO Notice emailed 29/06/2026 - Email received from solicitor regarding legal documentation 30/06/2026 - Email exchanged regarding legal fees and progression of legal documentation 02/07/2026 - Solicitor details chased via agent on email 13/07/2026 - Email received regarding legal fee undertaking and progression of the matter 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Leila Dawn Smithers |  | 148/17, 148/24, 148/26, 148/31, 148/48 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 15/01/2026 - Offer letter was sent. 19/03/2026 - Chaser Offer letter issued via post 13/05/2026 - Project letter issued 13/05/2026 - Solicitor details and status of offer letter chased 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 28/07/2026 - Phone call received from the landowner confirming receipt of correspondence 06/08/2026 - Follow up email issued regarding the matter
Lesley Ann Rush | OBJ-037 | 41/5, 42/4 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 15/01/2026 - Offer letter was sent via post. 24/01/2026 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 19/03/2026 - Chaser Offer letter issued via post 02/04/2026 - Email sent to chase up in relation to the offer letter 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email 02/07/2026 - Email sent to grantor/agent regarding CPO objection 05/08/2026 - Letter issued to grantor and agent in response to their objection
Liam Lynam |  | 143/1, 143/3 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 04/10/2026 - Email received from landowner to discuss the Land Interest Questionnaire 16/10/2026 - Email received from landowner to discuss the project in further detail
Linda Joy Hardisty |  | 148/19, 148/31, 148/41, 148/49 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 16/10/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 03/11/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 15/01/2026 - Offer letter was sent via post 19/03/2026 - Chaser Offer letter issued via post 01/04/2026 - Email sent to chase up for a response on the offer letter 02/04/2026 - Emails exchanged regarding solicitor details and the offer letter 16/04/2026 - Email sent offering further assistance to progress matters 17/04/2026 - Emails exchanged between Savills and grantor to discuss the project in greater detail 20/04/2026 - Email issued providing further project information and offer letter details 06/05/2026 - Solicitor details chased 13/05/2026 - Project letter issued 13/05/2026 - Solicitor details and status of offer letter chased 22/05/2026 - Email from grantor regarding documentation arrangements and legal fees 26/05/2026 - Email response regarding easement arrangements and legal fees 02/07/2026 - Solicitor details chased via agent on email 14/07/2026 - Solicitor details chased via email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 28/07/2026 - Phone call made regarding the project; voicemail left requesting a call back 05/08/2026 - Email received from an appointed agent confirming instruction on behalf of the landowner 05/08/2026 - Email issued requesting authority to act and availability for a telephone discussion regarding the matter 06/08/2026 - Follow up email issued requesting the landowner contact the project team by telephone or email
Paul Edward Hardisty |  | 148/19, 148/31, 148/41, 148/49 | Overhead line rights | As Linda Joy Hardisty (above)
Links Solar Farm Limited | OBJ-068 | 94/2, 94/4, 93/1, 94/5 | construction and operational access rights Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post via Post. 01/10/2025 - Chaser Land Interest Questionnaire Issued 05/08/2026 - Letter issued to grantor and agent in response to their objection
Lord Rayleigh's Farms Limited | OBJ-021 | 105/1, 105/2, 105/4, 106/1, 106/2, 106/3, 107/1, 107/3, 107/4, 107/5, 107/6, 108/1, 108/2, 108/5, 108/6, 108/8, 109/1, 109/2, 109/2a, 110/1, 110/2, 110/3, 110/4, 110/5, 110/6, 110/7, 111/2, 111/3, 111/4, 111/5, 111/8, 112/1, 112/2, 112/3, 112/4, 112/5, 113/2, 113/3, 113/4, 113/5, 113/6, 113/7, 113/7a, 114/1, 114/3, 114/4, 115/19 | Overhead line rights construction and operational access rights | 13/10/2025 - Land interest questionnaire issued via post 15/01/2026 - Offer letter was sent 22/01/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 16/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 13/03/2026 - Summary of key terms was sent 01/04/2026 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made 16/04/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 23/04/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 28/04/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 29/04/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email 02/07/2026 - Email sent to grantor/agent regarding CPO objection 05/08/2026 - Letter issued to grantor and agent in response to their objection
Louise Suzanne Humphreys | OBJ-006 | 101/1, 101/2, 102/1, 102/3, 102/4, 102/7, 103/3, 103/5, 103/6, 103/8, 103/14, 102/14, 102/15, 103/16 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 10/12/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made 15/01/2026 - Offer letter was sent via post 19/03/2026 - Chaser Offer letter issued via post 13/05/2026 - Project letter issued 13/05/2026 - Solicitor details chased via email 01/07/2026 - Email sent to grantor/agent regarding CPO objection 02/07/2026 - Solicitor details chased via agent on email 29/07/2026 - Site meeting held with grantor 05/08/2026 - Letter issued to grantor and agent in response to their objection 10/08/2026 - Site meeting held with grantor and their agent
Alison Jayne Lucas |  | 101/1, 101/2, 102/1, 102/3, 102/4, 102/7, 103/3, 103/5, 103/6, 102/14, 102/15, 103/8, 103/14, 103/16 | Overhead line rights construction and operational access rights | As Louise Suzanne Humphreys (above)
Malcolm Keith Mckenzie |  | 145/9, 145/11 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post via post. 10/09/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire 21/10/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire
Mark Anthony Sinfield |  | 149/10, 149/11, 150/1 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 15/01/2026 - Offer letter was sent via post 19/03/2026 - Chaser Offer letter issued via post 22/04/2026 -Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 29/04/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 13/05/2026 - Project letter issued 09/06/2026 - CPO Notice emailed to agent 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Gary Thomas Willats |  | 149/10, 149/11, 150/1 | Overhead line rights construction and operational access rights | As Mark Anthony Sinfield (above)
Lesley Caroline Willats |  | 149/10, 149/11, 150/1 | Overhead line rights construction and operational access rights | As Mark Anthony Sinfield (above)
Jill Louise Sinfield |  | 149/10, 149/11, 150/1 | Overhead line rights construction and operational access rights | As Mark Anthony Sinfield (above)
Mark Cannon |  | 30/2, 30/3 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 08/09/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire and Project in further detail 15/09/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made 27/10/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made 19/11/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made 15/01/2026 - Offer letter was sent via post 19/03/2026 - Chaser Offer letter issued via post 30/03/2026 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made 22/04/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email 14/07/2026 - Solicitor details chased via email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 28/07/2026 - Phone call held with the landowner who confirmed required information and that any outstanding matters could be discussed by telephone
Mark Treanor Thomasin-Foster |  | 132/4, 132/6, 132/7 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 09/09/2025 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 15/01/2026 - Offer letter was sent via post 19/03/2026 - Chaser Offer letter issued via post 30/03/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 13/05/2026 - Project letter issued 21/07/2026 - Emails exchanged between Savills and grantor to discuss solicitor fees and the project in further detail 22/07/2026 - Emails exchanged between Savills and grantor to discuss solicitor fees and the project in further detail 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Monica Jane Wilkinson |  | 132/4, 132/6, 132/7 | Overhead line rights | As Mark Treanor Thomasin-Foster (above)
The Official Custodian For Charities on behalf of the trustees of the Marks Hall Estate |  | 84/14, 84/15, 85/1, 85/2, 85/3, 85/4, 85/5, 85/6, 85/8, 86/1, 86/2, 86/3, 87/1, 87/2, 88/1, 88/2, 88/3, 85/10, 85/11, 85/14, 85/15, 85/16, 86/4, 87/3, 88/4, 89/14, 89/15 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 16/10/2025 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 21/10/2025 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 28/10/2025 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 29/10/2025 - Meeting was held to discuss the project in greater detail. 15/01/2026 - Offer letter was sent via post 19/01/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 29/01/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 10/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 23/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 03/03/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 05/03/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 13/05/2026 - Project letter issued 20/05/2026 - Agent confirmed instruction and professional fee proposal 21/05/2026 - Emails exchanged regarding professional fees and agent instruction 11/06/2026 - Emails exchanged regarding professional fees and existing agreements 02/07/2026 - Solicitor details chased via agent on email 21/07/2026 - Emails exchanged regarding proposed amendments and meeting arrangements 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 27/07/2026 - Meeting held with agent to discuss the project in greater detail 28/07/2026 - Email issued with draft deed and follow up actions from the meeting
Martin Grant (Holdings) Limited | OBJ-039 | 148/57, 148/60, 148/61, 149/3, 149/5 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 11/09/2025 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 18/09/2025 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 22/10/2025 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 31/10/2025 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 10/12/2025 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 15/01/2026 - Offer letter was sent via post 20/01/2026- Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 20/01/2026 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made 23/01/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 10/03/2026 - Summary of key terms was sent 13/03/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 13/05/2026 - Project letter issued 13/05/2026 - Solicitor details chased via email 09/06/2026 - CPO Notice emailed 09/06/2026 - Meeting proposed to discuss the project in further detail 15/06/2026 - Meeting arrangements discussed with agent 17/06/2026 - Email regarding meeting availability 29/06/2026 - Email regarding meeting availability 02/07/2026 - Solicitor details chased via agent on email 02/07/2026 - Email sent to grantor/agent regarding CPO objection 06/07/2026 - Emails exchanged between Savills and agent to discuss the project in further detail 06/07/2026 - Meeting provisionally arranged 10/07/2026 - Meeting invitation issued 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 05/08/2026 - Letter issued to grantor and agent in response to their objection
Mary Christine Earey |  | 101/1, 101/2, 101/3, 102/1, 102/4, 102/2, 102/14, 102/15 | Overhead line rights construction and operational access rights | 13/10/2025 - Land interest questionnaire issued via post 10/12/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser Offer letter issued via post 01/04/2026 Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 22/04/2026 Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 05/05/2026 - Solicitor details requested 05/05/2026 - Email received from landowner confirming they would not sign the offer letter and that their agent would be making contact 07/05/2026 - Email sent requesting agent details 12/05/2026 - Agent details received 12/05/2026 - Agent contacted and solicitor details requested 13/05/2026 - Project letter issued 08/06/2026 - Meeting scheduled with agent to discuss the project in further detail 02/07/2026 - Solicitor details chased via agent on email 02/07/2026 - Email sent to grantor/agent regarding CPO objection 06/07/2026 - CPO Notice emailed
Mary June Mortlock |  | 42/10, 42/11, 42/12, 42/13, 43/1, 43/2, 43/3, 43/4, 44/1, 44/2 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 25/09/2025 - Email received from landowner to discuss the Land Interest Questionnaire 13/10/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire 20/10/2025 - Phone call received from landowner to discuss the project in further detail 15/01/2026 - Offer letter was sent via post 16/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 10/03/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 13/05/2026 - Project letter issued 09/06/2026 - CPO Notice emailed to agent 02/07/2026 - Solicitor details chased via agent on email
Robert Mortlock |  | 42/10, 42/11, 42/12, 42/13, 43/1, 43/2, 43/3, 43/4, 44/1, 44/2, 48/4, 49/2, 49/3, 49/4, 48/1, 48/2, 48/3 | Overhead line rights construction and operational access rights | As Mary June Mortlock (above)
Betty Mortlock |  | 42/10, 42/11, 42/12, 42/13, 43/1, 43/2, 43/3, 43/4, 44/1, 44/2 | Overhead line rights construction and operational access rights | As Mary June Mortlock (above)
Thomas James Mortlock |  | 42/10, 42/11, 42/12, 42/13, 43/1, 43/2, 43/3, 43/4, 44/1, 44/2, 48/1, 48/2, 48/3, 48/4, 49/2, 49/3, 49/4, 49/5 | Overhead line rights construction and operational access rights | As Mary June Mortlock (above)
Mary-Anne Louise Barron |  | 77/4, 78/1, 78/4 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 08/09/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire 02/10/2025 - Site meeting held with grantor to discuss the project and its requirements in further detail 15/01/2026 - Offer letter was sent via post 26/01/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 09/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 13/05/2026 - Project letter issued 13/05/2026 - Solicitor details and status of the offer letter chased 09/06/2026 - CPO notice sent to landowner 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
James Paul Borges |  | 77/4, 78/1, 78/4 | Overhead line rights construction and operational access rights | As Mary-Anne Louise Barron
Matthew Benjamin Blackwell |  | 68/8, 69/1 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 09/09/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made 10/09/2025 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 10/10/2025 - Meeting with Scott Properties discussing Development. 22/10/2025 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 13/11/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made 20/11/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made 23/11/2025 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 13/01/2026 - Meeting with Scott Properties discussing Development 15/01/2026 - Offer letter was sent via post 08/04/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 23/04/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 28/04/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 13/05/2026 - Project letter issued 11/06/2026 - Email received regarding legal fees and project documentation 15/06/2026 - Email response regarding legal fees and project documentation 02/07/2026 - Solicitor details chased via agent on email 02/07/2026 - Email sent to grantor/agent regarding CPO objection 05/08/2026 - Letter issued to grantor and agent in response to their objection
Amanda Jane French | OBJ-016 | 68/8, 69/1, 100/4, 100/5, 101/13, 101/17, 101/18 | Overhead lines rights Construction and operational access rights | As Matthew Benjamin Blackwell (above)
Maureen Sonia Carter |  | 148/23, 148/26, 148/27, 148/28, 148/29, 148/31, 148/32, 148/33, 148/41 | Overhead lines rights Construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 15/01/2026 - Offer letter was sent via post 19/03/2026 - Offer Letter chaser was sent via post 26/03/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 31/03/2026 -Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 16/04/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 23/04/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 06/05/2026 - Solicitor details chased 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email
Michael Anthony Hope | OBJ-59 | 65/12, 65/14, 65/15, 66/2, 67/2, 67/3, 67/4 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 27/10/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire 15/01/2026 - Offer letter was sent via post 19/03/2026 - Offer Letter chaser was sent via post 28/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 10/03/2026 - Summary of key terms was issued via email 20/03/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 16/04/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 21/04/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 3/05/2026 - Project letter issued 13/05/2026 - Solicitor details and status of offer letter chased 02/07/2026 - Solicitor details chased via agent on email 02/07/2026 - Email sent to grantor/agent regarding CPO objection 05/08/2026 - Letter issued to grantor and agent in response to their objection
Jillian Mary Hope |  | 65/12, 65/14, 65/15, 66/2, 67/2, 67/3, 67/4 | Overhead lines rights Construction and operational access rights | As Michael Anthony Hope (above)
Michael George Watson | OBJ-015 | 1/1, 1/2, 1/5, 1/8, 1/9, 2/1, 2/2, 2/2a, 2/3, 3/1 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 27/10/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire 27/10/2025 - Email received from landowner to discuss the Land Interest Questionnaire 06/11/2025 - Email received from landowner to discuss the project in further detail 15/01/2026 - Offer letter was sent via post 28/01/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 11/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 17/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 10/03/2026 - Summary of key terms was sent 13/05/2026 - Project letter issued 09/06/2026 - CPO Notice emailed to land agent 01/07/2026 - Email sent to grantor/agent regarding CPO objection 02/07/2026 - Solicitor details chased via agent on email 16/07/2026 - Site meeting held with agent and landowner representatives to discuss the project in greater detail 16/07/2026 - Summary of Key Terms re-issued to agent for review 21/07/2026 - Emails exchanged regarding agent fees and meeting minutes 22/07/2026 - Draft easement issued to agent for review 22/07/2026 - Emails exchanged regarding agent fees and project progression 05/08/2026 - Letter issued to grantor and agent in response to their objection
Ian Christopher Watson | OBJ-015 | 1/1, 1/2, 1/5, 1/8, 1/9, 2/1, 2/2, 2/2a, 2/3, 3/1 | Overhead lines rights Construction and operational access rights | As Michael George Watson (above)
Michael Gordon Lindsell |  | 29/5, 30/7, 30/8, 30/10, 30/11, 30/13 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 20/10/2025 - Email received from landowner to discuss the Land Interest Questionnaire 15/01/2026 - Offer letter was sent via post 19/03/2026 - Offer Letter chaser was sent via post 27/04/2026 - Door knocks were undertaken on the project to contact landowner 30/04/2026 - Voicemail was left for landowner 13/05/2026 - Project letter issued 04/06/2026 - CPO Notice emailed 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 29/07/2026 - Phone call received requesting a call back on 30/07/2026 31/07/2026 - Phone call received advising the landowner was unavailable and requesting a call back the following week
Michael Ivan Andrew Goodbody | OBJ-012 | 60/6, 60/8, 60/10, 60/11 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 17/09/2025 - Phoned grantor to arrange a site meeting to discuss the project in further detail 30/09/2025 - Site meeting held with grantor to discuss to project and its requirements in further detail 29/12/2025 - Email received from landowner to discuss the Land Interest Questionnaire 15/01/2026 - Offer letter was sent via post 21/01/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 11/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 19/02/2026 - Email sent to agent regarding National Grid requirements and project intentions 02/04/2026 - Emails exchanged between Savills and agent to discuss the project in further detail 08/04/2026 - Emails exchanged between Savills and agent to discuss the project in further detail 07/05/2026 - Email and phone call with agent to discuss the project in further detail 11/05/2026 - Email issued summarising discussions with agent and seeking client instructions 13/05/2026 - Project letter issued 13/05/2026 - Solicitor details chased via email 27/05/2026 - Email received from agent regarding access to CPO documents 03/06/2026 - Email issued providing alternative access to CPO documents 09/06/2026 - CPO Notice emailed 01/07/2026 - Email sent to grantor/agent regarding CPO objection 02/07/2026 - Solicitor details chased via agent on email 05/08/2026 - Holding response issued to grantor and agent via email following receipt of their objection
Susannah Elizabeth Goodbody | OBJ-012 | 60/6, 60/8, 60/10, 60/11 | Overhead lines rights Construction and operational access rights | As Michael Ivan Andrew Goodbody (above)
Michael James Hodge | OBJ-056 | 132/8, 133/1, 133/5, 134/4, 134/5, 134/9, 134/11 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 13/10/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire 21/10/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire 15/01/2026 - Offer letter was sent via post 16/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 03/03/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email 02/07/2026 - Email sent to grantor/agent regarding CPO objection 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 05/08/2026 - Letter issued to grantor and agent in response to their objection
Andrew Robert Hodge |  | 132/8, 133/1, 133/5, 134/4, 134/5, 134/9, 134/11 | Overhead line rights | As Michael James Hodge (above)
Robert James Hodge |  | 132/8, 133/1, 133/5, 134/4, 134/5, 134/9, 134/11 | Overhead line rights | As Michael James Hodge (above)
Michael John Graham |  | 147/12 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 15/01/2026 - Offer letter was sent via post 26/01/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 16/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 17/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 13/05/2026 - Project letter issued 14/05/2026 - Solicitor details chased via email 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 29/07/2026 - Phone call made to the landowner; voicemail left requesting a call back 30/07/2026 - Phone call received from the landowner who raised queries regarding the project
Samantha Jayne Graham |  | 147/12 | Overhead line rights | As Michael John Graham (above)
Michael Peter Foy |  | 101/9, 101/11 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser offer letter issued via post 27/04/2026 - Doorknocks were undertaken on the project to contact landowner. 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 29/07/2026 - Phone call received from the landowner confirming receipt of correspondence and return of the signed documentation
Kerry Jane Foy |  | 101/9, 101/11 | Overhead line rights | As Michael Peter Foy (above)
Tara Elisa Marian Sherlock |  | 101/9, 101/11 | Overhead line rights | As Michael Peter Foy (above)
Michael Robert Moser |  | 101/10 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 24/09/2025 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 29/09/2025 - Site meeting held with grantor to discuss project 15/01/2026 - Offer letter issued via post 17/01/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 02/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 03/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 20/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 01/04/2026 - Summary of key terms issued via email 01/04/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 21/04/2026 - Email issued clarifying the purpose of the offer letter and progression of the easement process 11/05/2026 - Emails exchanged with landowner regarding easement rights, solicitor fees and project requirements 13/05/2026 - Project letter issued 22/06/2026 - Emails exchanged regarding solicitor appointment and legal representation 23/06/2026 - Solicitor details chased via email 29/06/2026 - Emails exchanged regarding solicitor and agent appointments 30/06/2026 - Emails exchanged regarding solicitor fees, legal representation and project documentation 01/07/2026 - Email issued providing project information and confirming agent appointment 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 25/07/2026 - Email received regarding project correspondence 27/07/2026 - Email issued confirming previous correspondence had been sent in error
Sophia Annabel Moser |  | 101/10 | Overhead line rights | As Michael Robert Moser (above)
Miles William Roberts |  | 72/2, 72/4, 73/4, 74/3 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 16/10/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 15/01/2026 - Offer letter was sent via post 22/01/2026 - Email received from landowner regarding the offer letter and project in further detail 28/01/2026 - Meeting to discuss Project 03/02/2026 - Email received from landowner regarding the offer letter and project in further detail 05/02/2026 - Agent appointed to act on behalf of the landowner 11/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 10/02/2026 - Email received from agent regarding existing access arrangements and project requirements 16/02/2026 - Revised offer issued following review of existing land rights 16/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 27/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 03/03/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 11/03/2026 - Summary of Key Terms was issued via email 22/04/2026 - Email sent to agent regarding progression of the easement and solicitor instruction 23/04/2026 - Email received from agent regarding the Summary of Key Terms and project requirements 03/05/2026 - Detailed comments received from agent on the Summary of Key Terms 13/05/2026 - Project letter issued via post 13/05/2026 - Solicitor details chased via email 09/06/2026 - CPO Notice issued via email 02/07/2026 - Solicitor details chased via agent on email 06/07/2026 - Solicitor details received from agent 07/07/2026 - Email confirmation issued that solicitor details had been captured 13/07/2026 - Emails exchanged regarding deed provisions and project requirements 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Gillian Janet Roberts |  | 72/2, 72/4, 73/4, 74/3 | Overhead line rights construction and operational access rights | As Miles William Roberts (above)
Miriam Graves | OBJ-031 | 16/3, 16/5, 16/6, 16/7, 16/8, 16/9, 17/1, 17/2, 17/3, 17/5, 17/7, 17/8, 17/9, 18/1, 18/4, 18/5, 18/7, 18/10, 18/2 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 22/09/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 15/01/2026 - Offer letter was sent via post 21/01/2026 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 27/03/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 30/03/2026 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 01/04/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 24/04/2026 - Email issued requesting solicitor details to enable progression of the easement 13/05/2026 - Project letter issued 14/05/2026 - Solicitor details chased via email 01/07/2026 - Agent confirmed further details regarding documentation 02/07/2026 - Solicitor details chased via agent on email 02/07/2026 - Email sent to grantor/agent regarding CPO objection 05/08/2026 - Letter issued to grantor and agent in response to their objection
Peter Jonathan Graves | OBJ-031 | 16/3, 16/5, 16/6, 16/7, 16/8, 16/9, 17/1, 17/2, 17/3, 17/5, 17/7, 17/8, 17/9, 18/1, 18/4, 18/5, 18/7, 18/10, 18/2 | Overhead line rights construction and operational access rights | As Miriam Graves (above)
Anne Elizabeth Graves | OBJ-031 | 16/3, 16/5, 16/6, 16/7, 16/8, 16/9, 17/1, 17/2, 17/3, 17/5, 17/7, 17/8, 17/9, 18/1, 18/4, 18/5, 18/7, 18/10, 18/2 | Overhead line rights construction and operational access rights | As Miriam Graves (above)
Mortlock Brothers (Toppesfield) Limited |  | 42/10, 42/11, 42/12, 42/13, 43/1, 43/2, 43/3, 43/4, 44/1, 44/2, 44/10, 44/11, 45/1, 45/5 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 25/09/2025 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 20/10/2025 - Meeting to Discuss Project. 20/10/2025 - Phone call received from landowner to discuss Land Interest Questionnaire / offer that has been made. 15/01/2026 - Offer letter was sent via post 16/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 13/05/2026 - Project letter issued 09/06/2026 - CPO Notice emailed to agent 02/07/2026 - Solicitor details chased via agent on email 02/07/2026 - Email sent to grantor/agent regarding CPO objection 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Mountview Estates Plc |  | 119/9 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 15/01/2026 - Offer letter was sent via post 16/01/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 13/05/2026 - Project letter issued 13/05/2026 - Solicitor details chased via email 02/07/2026 - Solicitor details chased via email 14/07/2026 - Solicitor details received 15/07/2026 - Confirmation issued that solicitor details had been captured 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
National Highways Limited |  | 10/3, 10/4, 117/4, 119/3, 119/5, 120/2, 127/2, 128/5, 132/1, 132/2, 132/5, 132/6, 120/3, 120/4 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 15/01/2026 - Offer letter was sent via post 19/03/2026 - Chaser offer letter issued via post 23/04/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 29/04/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 13/05/2026 - Project letter issued 13/05/2026 - Email sent chasing the offer letter response and solicitor details 08/06/2026 - Emails exchanged regarding project requirements and highways matters 02/07/2026 - Solicitor details chased via agent on email 13/07/2026 - Emails exchanged regarding a meeting to discuss highways matters and the project 21/07/2026 - Meeting held to discuss highways matters and project requirements 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
National Highways Limited |  | 10/3, 10/4, 117/4, 119/3, 119/5, 120/2, 127/2, 128/5, 132/1, 132/2, 132/5, 132/6, 120/3, 120/4 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 15/01/2026 - Offer letter was sent via post 19/03/2026 - Chaser offer letter issued via post 23/04/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 29/04/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 13/05/2026 - Project letter issued 13/05/2026 - Email sent chasing the offer letter response and solicitor details 08/06/2026 - Emails exchanged regarding project requirements and highways matters 02/07/2026 - Solicitor details chased via agent on email 13/07/2026 - Emails exchanged regarding a meeting to discuss highways matters and the project 21/07/2026 - Meeting held with National Highways to discuss the project and associated works
Nicholas James Gray Robinson |  | 32/12, 32/13 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 27/10/2025 - Voice mail for grantor asking to arrange a site meeting 10/12/2025 - Phone call to landowner to arrange a site meeting 15/01/2026 - Offer letter was sent via post 04/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 06/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 09/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 10/03/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 11/03/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 13/05/2026 - Project letter issued 09/06/2026 - CPO Notice emailed to land agent 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Melissa Elizabeth Robinson |  | 32/12, 32/13 | Overhead line rights construction and operational access rights | As Nicholas James Gray Robinson (above)
Anna Frances Wilson |  | 32/12, 32/13 | Overhead line rights construction and operational access rights | As Nicholas James Gray Robinson (above)
Clare Patricia Douglas |  | 32/12, 32/13 | Overhead line rights construction and operational access rights | As Nicholas James Gray Robinson (above)
Nicholas John Cousins | OBJ-061 | 98/1, 98/3, 99/1, 99/2, 99/6, 99/7, 99/7a, 99/10, 99/13, 99/15, 100/1, 100/2, 100/3, 100/7 | Overhead line rights construction and operational access rights | 08/09/2025 - Land Interest Questionnaire issued via post 15/01/2026 - Offer letter issued via Post. 19/03/2026 - Chaser offer letter issued via Post. 23/04/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 13/05/2026 - Project letter issued 01/07/2026 - Email sent to grantor/agent regarding CPO objection 02/07/2026 - Solicitor details chased via agent on email 05/08/2026 - Letter issued to grantor and agent in response to their objection
Nicholas John Karmy |  | 130/3 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued via post
Vicki Ann Kohler |  | 130/3 | Overhead line rights | As Nicholas John Karmy (above)
Antony Richardson |  | 130/3 | Overhead line rights | As Nicholas John Karmy (above)
Nicholas Owen Thomas Temple |  | 67/4, 67/6, 67/7, 67/11, 68/4, 68/5, 67/15, 67/16 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 22/09/2025 - Phone call to say they are point owners and not to send any further comms to his wife 01/10/2025 - Chaser Letter sent via post 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser offer letter issued via post 13/05/2026 - Project letter issued 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 29/07/2026 - Phone call held with the landowner who advised they required additional time to review letter 04/08/2026 - Phone call received from landowner requesting additional copy of the letter
Elizabeth Frances Temple |  | 67/4, 67/6, 67/7, 67/11, 68/4, 68/5, 67/15, 67/16 | Overhead line rights construction and operational access rights | As Nicholas Owen Thomas Temple (above)
Nicholas Stephen Debnam | OBJ078 | 38/12, 38/14, 39/1 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 10/11/2025 - Phone call with grantor to discuss the project in further detail 15/01/2026 - Offer letter issued via post 30/03/2026 - Email sent to grantor chasing the offer letter response 08/04/2026 - Email sent to grantor to discuss the project in further detail. 13/05/2026 - Project letter issued 09/06/2026 - CPO Notice emailed to land agent 18/06/2026 - Email received from agent requesting further documentation 22/06/2026 - Emails exchanged regarding existing agreements and project records 24/06/2026 - Existing consents issued to agent 01/07/2026 - Email sent to grantor/agent regarding CPO objection 02/07/2026 - Solicitor details chased via agent on email 14/07/2026 - Email received from agent requesting a meeting to discuss the proposed works 15/07/2026 - Email sent regarding availability for a project meeting 28/07/2026 – Documentation issued to agent 05/08/2026 - Letter issued to grantor and agent in response to their objection
Northumbrian Water Limited |  | 139/3, 140/1 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post via post 01/10/2025 - Chaser Letter sent via post 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser offer letter issued via post 23/04/2026 - Email sent to grantor to chase the offer letter response 13/05/2026 - Project letter issued 15/05/2026 - Agent confirmed instruction and requested project documentation 02/06/2026 - Project documentation issued to agent and Terms of Business requested 04/06/2026 - CPO Notice letter sent 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Oliver Harold Wass |  | 83/7, 84/18, 84/19, 84/21, 84/23, 84/24, 84/24a | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter Sent via post 07/10/2025 - Phone call with grantor 17/10/2025 - Phone call to grantor re site meeting 19/03/2026 - Chaser offer letter sent via post 02/06/2026 - Agent appointment confirmed and details regarding future correspondence 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email
Harriett Hull |  | 83/4, 83/7, 84/18, 84/19, 84/21, 84/23, 84/24, 84/24a, 84/25 | Overhead line rights construction and operational access rights | As Oliver Harold Wass (above)
On Tower UK 2 Limited - Not on comms and repeated |  | 131/2, 131/5, 131/7, 131/9, 132/3, 132/10, 132/11, 146/18, 146/30, 147/5, 147/7, 147/9, 147/10 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 24/09/2025 - Email received from LH discussing Land Interest Questionnaire / project in further detail 01/10/2025 - Chaser Land Interest Questionnaire Issued via post
Paul John Shadbolt |  | 75/8, 76/2, 76/3, 76/5 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post 15/01/2026 - Offer letter issued via post 10/03/2026 - Emails exchanged to discuss project in further detail 02/07/2026 - Chaser email sent regarding solicitor details 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Pegasi Limited |  | 7/5, 7/7, 7/9, 8/1, 8/2, 8/3, 8/5, 9/3, 10/1 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 16/10/2025 - Phone call declined, email sent to arrange a meeting 15/01/2026 - Offer letter issued via post 26/01/2026 - Emails exchanged to discuss the project in further detail 02/02/2026 - Emails exchanged to discuss the project in further detail 01/04/2026 - Emails exchanged to discuss the project and offer letter in further detail 07/04/2026 - Emails sent to landowner to discuss project works in further detail 08/04/2026 - Email chaser sent to follow up on the offer letter 13/05/2026 - Project letter issued 26/05/2026 - Solicitor details chased via email 01/07/2026 - Solicitor details received from appointed solicitor 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Persimmon Homes Limited |  | 98/2, 98/4, 98/5, 98/6, 99/14, 99/16, 99/17, 101/17 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post 16/10/2025 - Email to grantor to arrange a meeting 15/01/2026 - Offer letter issued to grantor via post 23/01/2026 - Emails exchanged to discuss project in further detail 09/02/2026 - Emails exchanged to discuss project in further detail 01/04/2026 - Emails exchanged to discuss project in further detail 22/04/2026 - Emails exchanged to discuss project in further detail 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via email 14/07/2026 - Email issued chasing solicitor details to enable progression of the legal documentation 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 28/07/2026 - Phone call made to the landowner; voicemail left requesting a call back via the project helpline
Peter Brian Silver Carter |  | 148/23, 148/27, 148/28, 148/32, 148/33, 148/37 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post 15/01/2026 - Offer letter was sent via post 26/01/2026 - Signed appendix received in the post 24/04/2026 - Letter was posted to the landowner to discuss the project 27/04/2026 - Doorknocking to discuss the project with the landowner. 30/04/2026 - Phone call with grantor but went to voicemail 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
The Executor of Eileen Catherine Carter |  | 148/23, 148/33, 148/37 | Overhead line rights construction and operational access rights | As Peter Brian Silver Carter (above)
Peter Davies |  | 146/18, 146/24, 146/30, 146/31, 147/5 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post 15/01/2026 - Offer letter was sent via post 25/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 28/04/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 13/05/2026 - Project letter issued 16/06/2026 - Email received from an agent confirming instruction on behalf of the landowner, provided documentation 16/06/2026 - Offer letter and Summary of Key Terms issued to the agent via email 16/06/2026 - Emails exchanged between Savills and agent confirming further details regarding the project and providing copies of relevant documentation 02/07/2026 - Solicitor details chased via agent on email 20/07/2026 - Draft deed issued to the agent via email for review 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Pauline Kay Davies |  | 146/18, 146/24, 146/30, 146/31, 147/5 | Overhead line rights construction and operational access rights | As Peter Davies (above)
Peter Edmund Gross Wheeler |  | 63/7, 63/8, 63/9, 63/10, 63/11, 63/16, 64/2, 63/13 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 08/09/2025 - Phone call from grantor, his agent will look through the paperwork 01/10/2025 - Chaser Letter sent via post 15/01/2026 - Offer letter was sent via post 23/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 10/03/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 28/04/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made 13/05/2026 - Project letter issued 16/06/2026 - Agent appointed and Terms of Engagement received 16/06/2026 - Offer letter and Summary of Key Terms issued to agent 16/06/2026 - Emails exchanged regarding the CPO process and project in further detail 02/07/2026 - Solicitor details chased via agent on email 20/07/2026 - Draft deed issued to agent for review 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Susan Elizabeth Wheeler |  | 63/7, 63/8, 63/9, 63/10, 63/11, 63/16, 64/2, 63/13 | Overhead line rights construction and operational access rights | As Peter Edmund Gross Wheeler (above)
| OBJ076 | 79/2, 79/4, 79/7, 79/8, 79/9, 80/2, 80/5, 80/6 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post 15/01/2026 - Offer letter was sent via post 23/01/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 25/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 13/05/2026 - Project letter issued 14/05/2026 - Email issued chasing solicitor details 09/06/2026 - CPO Notice issued via email 01/07/2026 - Holding email sent to grantor/agent following receipt of CPO objection 02/07/2026 - Solicitor details chased via agent on email 15/07/2026 – Emails exchanged between agent and Savills regarding clarification and further details regarding the project 20/07/2026 – Emails exchanged regarding clarification on the Summary of Key Terms and recovery of legal fees 28/07/2026 - Email issued requesting confirmation to complete the required project documentation
Penelope Ann Fairs |  | 79/2, 79/4, 79/7, 79/8, 79/9, 80/2, 80/5, 80/6 | Overhead line rights construction and operational access rights | As Peter John Fairs (above)
Peter John Nott | OBJ082 | 71/1, 71/8, 71/13 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 16/09/2025 - Phone call to grantor to arrange a site meeting 01/10/2025 - Chaser Letter sent via post 02/10/2025 - Site meeting held with grantor to discuss the questionnaire and the project in further detail 15/01/2026 - Offer letter was sent via post 19/03/2026 - Chaser offer letter issued via post 30/03/2026 - Signed appendix has been received from landowner. 13/05/2026 - Project letter issued 18/06/2026 - Email received from agent requesting copies of existing agreements 22/06/2026 - Emails exchanged regarding further details regarding the project 24/06/2026 – Documentation emailed to agent 02/07/2026 - Solicitor details chased via agent on email 14/07/2026 - Email received from agent requesting a meeting to discuss the proposed works 15/07/2026 - Email sent regarding availability for a project meeting 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 28/07/2026 - Sanitised deed issued to agent
Peter Mads Hogsbjerg |  | 72/3, 73/2 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 15/01/2026 - Offer letter was sent via post 28/01/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 11/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 16/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 27/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 03/03/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 10/03/2026 -Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 13/05/2026 - Project letter issued 13/05/2026 - Solicitor details chased via email 20/05/2026 - Email received from agent regarding the payment schedule 09/06/2026 - CPO Notice emailed 10/06/2026 - Email received from agent regarding the CPO notice 15/06/2026 - Emails exchanged regarding the CPO process, Summary of Key Terms and payment schedule 02/07/2026 - Solicitor details chased via agent on email 02/07/2026 - Emails exchanged with agent regarding the Summary of Key Terms and progression of the matter 02/07/2026 – Email confirmation from Savills that their queries will be discussed with National Grid and request to arrange site meeting with agent and grantor 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Ann Mary Hogsbjerg |  | 72/3, 73/2 | Overhead line rights | As Peter Mads Hogsbjerg (above)
Peter McMillan |  | 44/6, 45/2 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post 26/11/2025 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 15/01/2026 - Offer letter was sent via post 20/01/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 21/01/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 05/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 28/04/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 13/05/2026 - Project letter issued 08/06/2026 - Email sent to agent regarding availability for a Teams meeting 09/06/2026 - CPO Notice emailed 11/06/2026 - Emails exchanged regarding the CPO notice and project in further detail 02/07/2026 - Solicitor details chased via agent on email 02/07/2026 - Email from agent regarding the Summary of Terms and project in further detail 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Angela Irene Mary McMillan |  | 44/6, 45/2 | Overhead line rights | As Peter McMillan (above)
Peter Scantlebury Philp |  | 51/7, 51/9, 51/10, 51/11, 52/1, 52/3, 52/4, 52/5, 52/7, 52/7a, 52/7b, 52/8, 52/9, 52/10, 52/11, 53/1 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post 27/10/2025 - Email to request a site meeting 15/01/2026 - Offer letter was sent via post 26/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 13/05/2026 - Project letter issued 09/06/2026 - CPO notice sent to landowner 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
John Philp |  | 51/7, 51/9, 51/10, 51/11, 52/1, 52/3, 52/4, 52/5, 52/7, 52/7a, 52/7b, 52/8, 52/9, 52/10, 52/11, 53/1 | Overhead line rights construction and operational access rights | As Peter Scantlebury Philip (above)
Aubrey Philp |  | 51/7, 51/9, 51/10, 51/11, 52/1, 52/3, 52/4, 52/5, 52/7, 52/7a, 52/7b, 52/8, 52/9, 52/10, 52/11, 53/1 | Overhead line rights construction and operational access rights | As Peter Scantlebury Philip (above)
Philp Farm Contracts Limited |  | 53/7, 54/1, 55/1, 55/5, 55/11, 56/1, 56/2, 56/4, 56/5, 56/6, 57/1 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post 27/10/2025 - Email to request a site meeting 15/01/2026 - Offer letter was sent via post 26/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Pivoted Power Llp |  | 99/3, 99/4, 99/8 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post
Places for People and Homes Limited | OBJ-072 | 119/2, 119/4, 119/9, 119/10, 119/13, 119/14, 120/1, 121/3, 121/4, 121/5, 122/1, 123/1, 123/2, 123/3, 123/4, 123/5, 123/6, 125/2, 125/4, 117/5, 119/8 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 27/10/2025 - Phoned grantor to arrange a site meeting to discuss the project in further detail; left a voicemail 15/01/2026 - Offer letter issued via post 05/02/2026 - Email received confirming agreement in principle to the offer and intention to appoint a land agent 12/04/2026 - Email sent chasing a response to the offer letter and offering further assistance 14/04/2026 - Email sent chasing a response to the offer letter and offering further assistance 13/05/2026 - Project letter issued 13/05/2026 - Solicitor details chased via email 20/05/2026 - Phone call with land agent to discuss the project, fees and further details 21/05/2026 - Project information, Summary of Key Terms and further context regarding project 04/06/2026 - Emails exchanged regarding injurious affection and project matters 09/06/2026 - CPO Notice emailed 15/06/2026 - Emails exchanged regarding fees and representation arrangements 16/06/2026 - Email issued regarding injurious affection enquiries 17/06/2026 - Email update issued regarding injurious affection enquiries 18/06/2026 - Emails and phone calls exchanged regarding agent fees and injurious affection enquiries 19/06/2026 - Attempted call and email issued regarding fees 29/06/2026 - Emails exchanged regarding ongoing fee discussions 02/07/2026 - Solicitor details chased via agent on email 08/07/2026 - Update received regarding development clause and injurious affection enquiries 22/07/2026 - Emails exchanged regarding injurious affection enquiries and project matters 05/08/2026 - Letter issued to grantor and agent in response to their objection
Principality Properties Limited |  | 76/4, 76/7, 77/2, 77/3 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post 27/10/2025 - Email to request a site meeting 15/01/2026 - Offer letter issued via Post 19/03/2026 - Chaser offer letter issued via post 23/04/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 13/05/2026 - Project letter issued 09/06/2026 - CPO notice sent to landowner 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Richard Arthur Ramsey |  | 83/2, 83/5, 83/6, 83/8, 83/10, 83/11, 83/13, 83/14, 83/15, 83/16, 84/26 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 14/10/2025 - Phone call for arranged site meeting on 17/10/2025 21/10/2025 - Site meeting, very happy to negotiate 15/01/2026 - Offer letter issued via Post 20/01/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 09/02/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 19/03/2026 - Chaser offer letter issued via post 13/05/2026 - Project letter issued 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Kate Alexandra Ramsey |  | 83/2, 83/5, 83/6, 83/8, 83/10, 83/11, 83/13, 83/14, 83/15, 83/16, 84/26 | Overhead line rights construction and operational access rights | As Richard Alexandra Ramsey (above)
Richard David Fordham |  | 68/2, 68/7, 68/10, 75/8, 76/2, 76/3 | Overhead line rights construction and operational access rights | 08/09/2025 - Emails exchanged between grantor and Savills to discuss the project in further detail 11/09/2025 - Emails exchanged between grantor and Savills to discuss the project in further detail 13/09/2025 - Land interest questionnaire issued via post 22/10/2025 - Phone call received from grantor with queries about the project 15/01/2026 - Offer letter issued via Post 19/01/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 20/01/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 24/01/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 08/04/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 16/04/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 13/05/2026 - Project letter issued 11/06/2026 - Email received regarding legal fees and Heads of Terms 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Richard George Boland |  | 146/18, 146/24, 146/26, 146/27, 146/30, 146/31, 147/5, 150/9, 150/6, 150/7, 150/8, 151/1, 151/6, 151/7, 151/8, 151/9, 151/10, 151/11, 152/2, 152/3, 152/4 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post 15/01/2026 - Offer letter issued via Post 26/01/2026 - Signed appendix has been received 28/04/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 13/05/2026 - Project letter issued 16/06/2026 - Agent appointed and Terms of Engagement received 16/06/2026 - Offer letter and Summary of Key Terms issued to agent 16/06/2026 - Emails exchanged regarding the CPO process and project in further detail 02/07/2026 - Solicitor details chased via agent on email 20/07/2026 - Draft documentation issued to agent for review 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Sandra Elizabeth Boland |  | 146/18, 146/24, 146/26, 146/27, 146/30, 146/31, 147/5 | Overhead line rights construction and operational access rights | As Richard George Boland (above)
Richard Hermon |  | 83/3, 83/9, 83/10, 83/11, 83/12 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer letter issued via Post 19/03/2026 - Offer Letter chaser issued via post 12/05/2026 - Email received from landowner confirming receipt of the offer letter and intention to seek professional advice 13/05/2026 - Project letter issued 10/06/2026 - Copy of offer letter issued to landowner 11/06/2026 - Emails exchanged regarding solicitor instruction and legal undertakings 15/06/2026 - Emails exchanged regarding solicitors and National Grid queries 20/07/2026 - Email received confirming the matter is on hold pending confirmation of legal undertakings 24/07/2026 - Email received requesting a project update 28/07/2026 - Email sent requesting written confirmation to proceed 29/07/2026 - Email issued confirming National Grid's solicitors will be in contact
Richard Holmsted Speakman | OBJ-046 | 115/1, 115/5, 115/8, 116/1, 116/2, 116/3, 117/1, 117/2, 117/6, 117/7, 117/8, 117/11, 117/12, 117/13, 117/14, 117/15, 117/16, 118/4, 118/6, 128/1, 128/2, 128/4, 129/1, 129/2, 129/3, 129/5, 129/6, 129/8, 131/3, 131/4, 130/7, 130/8, 130/11, 130/12, 130/13 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 25/09/2025 - Phone call with grantor to discuss the project in further detail 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 06/10/2025 - Site meeting held with grantor to discuss the project in further detail 12/12/2025 - Phone call attempted and voicemail left to discuss project with the agent 15/01/2026 - Offer letter issued via post 20/01/2026 - Email received from LH intrest discussing Land Interest Questionnaire / project in further detail 02/02/2026 - Email received from LH interest discussing Land Interest Questionnaire / project in further detail 19/03/2025 - Chaser letter issued via post 28/04/2026 - Email sent out to land agent 13/05/2026 - Project letter issued 13/05/2026 - Email sent to land agent chasing the offer letter 02/07/2026 - Solicitor details chased via agent on email 02/07/2026 - Email sent to grantor/agent regarding CPO objection 05/08/2026 - Letter issued to grantor and agent in response to their objection
Christopher Francis Speakman | OBJ-046 | 115/5, 115/8, 128/1, 128/2, 128/4, 129/1, 129/2, 129/3, 129/5, 129/6, 129/8, 131/3, 131/4, 130/7, 130/8, 130/11, 130/12, 130/13 | Overhead line rights construction and operational access rights | As Richard Holmstead Speakman (above)
Andrew Guy Speakman | OBJ-046 | 115/5, 115/8, 128/1, 128/2, 128/4, 129/1, 129/2, 129/3, 129/5, 129/6, 129/8, 131/3, 131/4, 130/7, 130/8, 130/11, 130/12, 130/13 | Overhead line rights construction and operational access rights | As Richard Holmstead Speakman (above)
Philip William Henry Speakman | OBJ-046 | 115/5, 115/8, 128/1, 128/2, 128/4, 129/1, 129/2, 129/3, 129/5, 129/6, 129/8, 131/3, 131/4, 130/7, 130/8, 130/11, 130/12, 130/13 | Overhead line rights construction and operational access rights | As Richard Holmstead Speakman (above)
Richard Peter Hingston |  | 19/9, 20/2, 20/3, 21/6, 21/7, 22/2, 22/3, 22/4, 22/5, 22/6, 21/6a | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 05/09/2025 - Email received from landowner discussing Land Interest Questionnaire / project in further detail. Site meeting also arranged 06/09/2025 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 09/10/2025 - Site meeting held with grantor to discuss the project and its requirements in further detail 20/11/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer Letter sent via post 09/03/2025 - Email received from landowner discussing project in further detail 13/03/2025 - Email received from landowner discussing offer letter issued 16/03/2025 - Email received from landowner with further queries on the offer letter / project 21/04/2025 -Email received from landowner with further queries on the offer letter / project 29/04/2026 - Email received from landowner with further queries on the offer letter / project 13/05/2026 - Project letter issued 13/05/2026 - Solicitor details and status of offer letter chased 02/07/2026 - Solicitor details chased via agent on email 03/07/2026 - Solicitor details received from agent 06/07/2026 - Confirmation issued that solicitor details had been captured 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Gillian Kathleen Hingston |  | 19/9, 21/6, 21/7, 22/2, 22/3, 22/4, 22/5, 22/6, 21/6a, 20/2, 20/3 | Overhead line rights construction and operational access rights | As Richard Peter Hinston (above)
Richard Robert Browning | OBJ-010 | 80/4, 80/8, 81/5, 81/12 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/10/2025 - Phone call and email to grantor to discuss the project in further detail 15/01/2026 - Offer Letter sent via Post 16/02/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 25/02/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 10/03/2025 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 19/03/2026 - Chaser offer letter issued via post 13/05/2026 - Project letter issued 14/05/2026 - Solicitor details chased via email 18/05/2026 - Email received requesting a meeting to discuss the project 21/05/2026 - Email issued requesting Terms of Business and availability for a meeting 30/05/2026 - Correspondence received from agent confirming representation and requesting project documentation 15/06/2026 - Email issued requesting Terms of Business and confirmation of instruction 17/06/2026 - Authorisation received from agent and discussions held regarding professional fees 06/07/2026 - Agent requested Summary of Key Terms and asked for further information 06/07/2026 - Summary of Key Terms issued to agent via email 23/07/2026 - Site meeting held with grantor and their agent 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 05/08/2026 - Letter issued to grantor and agent in response to their objection
Elizabeth Margaret Xenakis |  | 80/4, 80/8, 81/5, 81/12 | Overhead line rights construction and operational access rights | As Richard Margaret Xenakis (above)
Richard Rutherford Maynard |  | 148/20, 148/25, 148/29, 148/46 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post via Post. 15/01/2026 - Offer Letter sent via Post. 19/03/2026 - Offer Letter Chaser sent via Post. 28/04/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
RJL Properties Limited |  | 148/15, 148/16, 148/52, 148/55 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post via Post 1/10/2025 - Chaser Land Interest Questionnaire Issued 15/01/2026 - Offer letter issued via Post 19/03/2026 - Chaser Offer Letter Issued via post 30/03/2026 - Signed appendix from landowner was received in the post 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Robert Charles Gerard Foster |  | 115/10, 115/15 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer letter issued via Post 19/03/2026 - Chaser Offer Letter Issued via post 27/03/2026 - Doorknocked site and left a letter through mailbox 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Robert Draper Caton | OBJ-034 | 23/7, 23/9, 23/11, 23/12, 23/13, 24/1, 24/2, 24/3, 25/1, 25/2, 25/3, 25/4, 25/5 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter Sent via post 31/10/2025 - Phone call from grantor to decline a meeting 22/01/2026 - Phone call with grantor to advise he is the chairman for the charity 19/03/2026 - Chaser offer letter sent via post 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Robert Edward Jones |  | 30/12, 30/13 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued 15/01/2026 - Offer letter issued via post 09/02/2026 - Phone call from grantor to discuss the project in greater detail 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Sarah Jane Jones |  | 30/12, 30/13 | Overhead line rights construction and operational access rights | As Robert Edward Jones (above)
Robert Howard Wilson |  | 68/2, 68/6 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 13/10/2025 - Phone call held between grantor and Savills to discuss the project in further detail. 15/01/2026 - Offer letter issued via Post 19/03/2026 - Chaser Offer Letter Issued via post 30/03/2026 - Signed appendix received via post 24/04/2026 - Letter issued to grantor to request solicitor details 13/05/2026 - Project letter issued 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Anne Deborah Wilson |  | 68/2, 68/6 | Overhead line rights construction and operational access rights | As Robert Howard Wilson (above)
Robert John Stacey | OBJ-058 | 136/6, 136/7, 137/1 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer letter issued via Post 19/03/2026 - Chaser Offer Letter Issued via post 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email 02/07/2026 - Email sent to grantor/agent regarding CPO objection 05/08/2026 - Letter issued to grantor and agent in response to their objection
Robert Michael Prestney |  | 81/1, 81/2, 81/3, 82/4, 82/7, 82/8 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer letter issued via Post 19/03/2026 - Chaser Offer Letter Issued via post 13/05/2026 - Project letter issued 14/05/2026 - Solicitor details chased via email 18/05/2026 - Agent confirmed instruction on behalf of the landowner 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Robert Peter Bolton |  | 132/6, 132/7, 132/9 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 09/09/2025 - Emails exchanged between grantor and Savills to discuss the project in further detail. 15/01/2026 - Offer letter issued via Post 19/03/2026 - Chaser Offer Letter Issued via post 01/04/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 16/04/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 27/05/2026 - Meeting held in person with landowner to discuss the project in further detail. Landowner signed the appendix and confirmed a solicitor would be instructed 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via email 14/07/2026 - Solicitor details chased via email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 05/08/2026 - Letter issued to grantor and agent in response to their objection
Robert Thomas Speakman |  | 94/1, 95/1, 95/2, 95/3, 95/7, 95/8, 96/10, 96/11 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 08/09/2025 - Phone call held between grantor and Savills to discuss the project in further detail. 21/09/2025 - Site meeting booked with grantor to discuss project in further detail 02/10/2025 - Site meeting held with grantor to discuss the project and its requirements in further detail 15/01/2026 - Offer letter issued via Post 10/03/2026 - Summary of key terms emailed to agent 12/03/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 13/05/2026 - Project letter issued 13/05/2026 - Solicitor details and status of offer letter chased 04/06/2026 - Agent requested documentation for grantor 15/06/2026 - Offer plans and CPO documentation issued to agent 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Thomas William Speakman |  | 94/1, 95/1, 95/2, 95/3, 95/7, 95/8, 96/10, 96/11 | Overhead line rights construction and operational access rights | As Robert Thomas Speakman (above)
Robina Sandeman Gray |  | 32/14 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued via post 08/09/2025 - Phone call held between grantor and Savills to discuss the project in further detail. 21/10/2025 - Site meeting booked with grantor to discuss project in further detail. 15/01/2026 - Offer letter issued via post 11/03/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 23/01/2026 - Phone call held between grantor and Savills to discuss the project in further detail. 10/03/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 07/04/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 13/05/2026 - Project letter issued 14/05/2026 - Solicitor details and status of offer letter chased 23/06/2026 - Phone call with grantor regarding solicitor appointment, CPO concerns and project requirements 25/06/2026 - Email issued to agent providing an update following discussions with the grantor 02/07/2026 - Solicitor details chased via agent on email 03/07/2026 - Agent confirmed no solicitor had yet been appointed 06/07/2026 - Confirmation issued that agent update had been recorded 10/07/2026 - Email received from agent regarding solicitor arrangements 13/07/2026 - Email issued clarifying solicitor arrangements and next steps 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 27/07/2026 – Further details confirmed with agent 28/07/2026 - Solicitor details received and request made for National Grid legal team to make contact 28/07/2026 - Confirmation issued to agent that solicitor details had been passed on 28/07/2026 - Meeting arrangements initiated with project engineers to discuss the project in further detail 07/08/2026 - Phone call with grantor to arrange a site meeting 10/08/2026 - Site meeting held with grantor and their agent
Jennifer May Clayton |  | 113/3, 113/6, 113/7, 113/7a, 114/1, 114/3, 114/4, 115/14, 115/18, 115/19 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post 28/10/2025 - Phone call with grantor to invite a site meeting 19/03/2026 - Chaser offer letter sent via post 13/05/2026 - Project letter issued 13/05/2026 - Solicitor details chased via email 02/06/2026 - Email received from grantor regarding existing easement arrangements 15/06/2026 - Emails exchanged with grantor regarding existing easement arrangements 17/06/2026 - Email issued confirming queries were being investigated 02/07/2026 - Solicitor details chased via email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Jennifer May Clayton |  | 113/3, 113/6, 113/7, 113/7a, 114/1, 114/3, 114/4, 115/14, 115/18, 115/19 | Overhead line rights construction and operational access rights | As Jennifer May Clayton (above)
Roy Howard Hart |  | 141/4, 141/5, 141/7, 141/8, 141/11, 141/13, 141/15, 141/17, 142/1, 142/5, 142/6, 141/22, 143/13 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 16/10/2025- Phone call held between grantor and Savills to discuss the project in further detail. 15/01/2026 - Offer letter issued via Post 19/03/2026 - Chaser Offer Letter Issued via post 23/04/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 13/05/2026 - Project letter issued 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 29/07/2026 - Phone call held with a third party regarding the matter, who advised that the landowner would return the call 29/07/2026 - Phone call received from the landowner confirming receipt of correspondence, and indicated that a meeting may be beneficial following further discussions
Justin Hart |  | 141/4, 141/5, 141/7, 141/8, 141/11, 141/13, 141/15, 141/17, 142/1, 142/5, 142/6, 141/22, 143/13 | Overhead line rights construction and operational access rights | As Justin Hart (above)
Roy John Brett |  | 96/5 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest questionnaire Issued via post 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser Offer Letter Issued via post 27/04/2026 – Door knock site and left a letter at the property 13/05/2026 - Project letter issued 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Roy Leslie Carter |  | 148/23, 148/27, 148/31, 148/33, 148/41 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued 15/01/2026 - Offer letter issued via Post 19/03/2026 - Chaser Offer Letter Issued via post 26/03/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 30/03/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 16/04/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 23/04/2026 - Email sent to grantor to chase up on the offer letter 06/05/2026 - Solicitor details chased via email 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email
Maureen Sonia Carter |  | 148/23, 148/26, 148/27, 148/28, 148/29, 148/31, 148/32, 148/33, 148/41 | Overhead line rights construction and operational access rights | As Roy Leslie Carter (above)
Roy Philip Chapman |  | 28/7, 29/3, 30/1 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 13/10/2025- Phone call held between grantor and Savills to discuss the project in further detail. 15/01/2026 - Offer letter issued via Post 27/04/2026- Phone call held between grantor and Savills to discuss the project in further detail. 27/04/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Runningwell Equestrian Centre Limited |  | 143/6, 143/8, 143/12 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued via post 14/10/2025- Phone call held between grantor and Savills to discuss the project in further detail. 15/01/2026 - Offer letter issued via Post 05/03/2026 - Emails exchanged between grantor and Savills to discuss project in further detail 09/03/2026 - Emails exchanged with agent to discuss the project in further detail 10/03/2026 - Summary of key terms sent to agent via email 13/03/2026 - Emails exchanged about the summary of key terms 07/04/2026 - Emails exchanged about the summary of key terms 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email 03/07/2026 - Solicitor details received from agent 06/07/2026 - Confirmation issued that solicitor details had been captured 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Russel John Fone |  | 148/12, 148/13, 148/53 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 13/10/2025- Phone call held between grantor and Savills to discuss the project in further detail. 28/10/2025 - Site meeting booked with grantor to discuss project in further detail. 15/01/2026 - Offer letter issued via Post 28/04/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Teresa Barbara Fone |  | 148/12, 148/13, 148/53 | Overhead line rights construction and operational access rights | As Russel John Fone (above)
Ruth Mavis Tatam |  | 83/2, 83/3, 83/5, 83/14, 83/15 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer letter issued via Post 26/01/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 03/02/2026 - Emails exchanged between grantor and Savills to discuss the project in further detai 13/05/2026 - Project letter issued 10/06/2026 - Phone call held with landowner to discuss the project and CPO correspondence. Updated contact details obtained and offer documentation reissued 13/07/2026 - Email received confirming progression of the matter was on hold pending confirmation of legal undertakings 24/07/2026 - Email received requesting an update on the matter 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 29/07/2026 - Email issued confirming National Grid will be in contact
Mary Roberta Wright |  | 83/2, 83/3, 83/5, 83/14, 83/15 | Overhead line rights construction and operational access rights | As Ruth Mavis Tatam (above)
Anne Dora Williams |  | 83/14, 83/15 | Overhead line rights construction and operational access rights | As Ruth Mavis Tatam (above)
Alan Robert Bull |  | 83/2, 83/5, 83/13, 83/14, 83/15, 83/16 | Overhead line rights construction and operational access rights | As Ruth Mavis Tatam (above)
Sandon Parish Council |  | 130/3, 130/4 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 08/09/2025 - Email received from LH discussing Land Interest Questionnaire / project in further detail 10/09/2025 - Phone call and email to LH to discuss the project in further detail. 15/09/2025 - Email received from LH discussing Land Interest Questionnaire / project in further detail
Sarah Elizabeth Coleman |  | 80/1, 81/3, 81/4, 81/6, 81/7, 81/9, 81/11 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 15/01/2026 - Offer letter issued via Post 19/03/2026 - Chaser Offer Letter Issued via post 13/05/2026 - Project letter issued 18/05/2026 - Agent confirmed instruction on behalf of the landowner 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Simon Francis Latham | OBJ-036 | 23/2, 23/3, 23/4, 23/5 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer letter issued via Post 19/03/2026 - Chaser Offer Letter Issued via post 23/04/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 06/05/2026 – Email from agent confirming details 12/05/2026 - Email sent to land agent requesting the signed appendix and an update on the offer letter 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email 02/07/2026 - Email sent to grantor/agent regarding CPO objection 05/08/2026 - Letter issued to grantor and agent in response to their objection
Hazel Marion Latham | OBJ-036 | 23/2, 23/3, 23/4, 23/5 | Overhead line rights construction and operational access rights | As Simon Francis Latham (above)
SJR Farming Limited | OBJ-045 | 143/14, 143/15, 144/1, 144/2, 144/3, 144/5, 149/10, 149/11, 150/1, 150/2, 150/3, 150/4, 150/5, 150/6, 150/7, 150/8, 150/10, 151/1, 151/4, 151/5, 151/6, 151/7, 151/8, 151/9, 151/10, 151/11, 151/13, 152/2, 152/3, 152/4, 152/5, 152/6, 150/9 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 21/11/2025 - Phone call held between grantor and Savills to discuss the project in further detail 27/11/2025 - Phone call held between grantor and Savills to discuss the project in further detail 14/01/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 28/01/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 26/03/2026 - Offer letter issued via Post 31/03/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 10/04/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 23/04/2026 - Offer letter and Summary of Key Terms reissued to agent and project queries answered 24/04/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 13/05/2026 - Project letter issued 13/05/2026 - Solicitor details chased via email 15/06/2026 - Email issued confirming solicitor details and progression of Summary of Key Terms 02/07/2026 - Solicitor details chased via agent on email 05/08/2026 - Letter issued to grantor and agent in response to their objection
Sonya Mitchell |  | 148/18, 148/37, 148/41, 148/51 | Overhead lines rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued 15/01/2026 - Offer letter issued via Post 19/03/2026 - Chaser Offer Letter Issued via post 27/04/2026 - Door knocking exercise carried out to establish contact with grantor; contact established 30/04/2026 - Email sent to landowner to chase up on the offer letter 27/05/2026 - Email received from landowner regarding solicitor appointment options 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 28/07/2026 - Phone call held with the landowner who advised they had previously sent an email regarding the matter and requested assistance with progression.
Stephen James Kendal |  | 101/4 | Overhead lines rights | 08/09/2025 - Land interest questionnaire issued via post 09/09/2025 - Emails exchanged between grantor and Savills to discuss the project in further detail. Site meeting arranged with grantor 29/09/2025 - Site meeting held with grantor to discuss the project in further detail 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser Offer Letter Issued via post 13/05/2026 - Project letter issued 14/05/2026 - Emails exchanged regarding the offer letter, correspondence address and project in further detail 11/06/2026 - Offer letter and CPO Notice reissued to landowner via email 02/07/2026 - Solicitor details chased via email 09/07/2026 - Agent details received 13/07/2026 - Confirmation issued to landowner and project information forwarded to agent 14/07/2026 - Agent confirmed willingness to attend a meeting 15/07/2026 - Emails exchanged regarding meeting arrangements 17/07/2026 - Agent circulated available meeting dates 20/07/2026 - Proposed meeting date issued to agent 23/07/2026 - Site meeting held to discuss the project in further detail 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 28/07/2026 - Sanitised deed and meeting minutes issued to agent
Mary Teresa Kendal |  | 101/4 | Overhead line rights construction and operational access rights | As Stephen James Kendal (above)
Stephen John Bolton | OBJ-019 | 119/2, 119/4, 119/6, 119/12, 119/13, 119/14, 120/1, 120/2, 121/1, 121/2, 121/3, 121/4, 121/5, 122/1, 123/1, 123/2, 123/3, 123/4, 123/5, 123/6, 123/7, 125/2, 125/4, 125/5, 125/6, 120/4 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 19/11/2025 - Phone call and email to grantor to discuss the project in further detail. 15/01/2026 - Offer Letter sent via post. 16/01/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 20/01/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 21/01/2026 - Email from agent asking for Heads of Terms 22/01/2026 - Email from agent stating hourly fee and requesting 03/02/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 06/02/2026 - Email received from agent discussing project 26/02/2026 - Email received from agent discussing project 23/03/2026 - Email received from agent discussing project 06/04/2026 – CPO Notice emailed 01/05/2026 – Correspondence with agent and Savills to setup a meeting 11/05/2026 – Online meeting with agent and Savills to discuss the project in greater detail 13/05/2026 - Project letter issued 14/05/2026 – Email from agent to confirm further details from grantor 15/05/2026 – Email from agent discussing further details and important dates 21/05/2026 - Correspondence with agent to setup a meeting with Savills 02/07/2026 – Chaser sent regarding solicitor details 02/07/2026 - Email sent to grantor/agent regarding CPO objection 05/08/2026 - Letter issued to grantor and agent in response to their objection
David Lawrence Bolton | OBJ-019 | 119/2, 119/4, 119/6, 119/12, 119/13, 119/14, 120/1, 120/2, 121/1, 121/2, 121/3, 121/4, 121/5, 122/1, 123/1, 123/2, 123/3, 123/4, 123/5, 123/6, 123/7, 125/2, 125/4, 125/5, 125/6, 120/4 | Overhead line rights | As Stephen John Bolton (above)
Stephen John Taylor |  | 148/36, 148/43 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued 09/09/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made 15/01/2026 - Offer letter issued via post 19/01/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 17/02/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 27/04/2026 - Phone call held between grantor and Savills to discuss the project in further detail 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 29/07/2026 - Emails exchanged regarding solicitor details, project progression and delays in the legal process 29/07/2026 - Confirmation issued that the signed appendix had been located and that National Grid's solicitors had been chased for an update
Stuart Walter Brock |  | 20/4, 20/7, 21/8, 21/9, 22/1, 22/3, 22/4, 22/5, 22/6 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 22/10/2025 - phone call held between grantor and Savills to discuss the project in further detail 19/11/2025 - phone call held between grantor and Savills to discuss the project in further detail 15/01/2026 - Offer letter issued via post 23/01/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 10/03/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 24/03/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 02/06/2026 - Email received regarding plot references and land ownership queries 08/06/2026 - Follow up email correspondence received regarding outstanding queries 10/06/2026 - Agent advised that a colleague would be taking over conduct of the matter and records were updated accordingly 15/06/2026 - Email issued providing clarification on the rights sought, existing rights and project requirements 15/06/2026 - Email received regarding the offer letter and ownership records 18/06/2026 - Email issued regarding updated land ownership records and agent fee arrangements 23/06/2026 – Email correspondence between Savills and agent to confirm further details regarding the project 02/07/2026 - Solicitor details chased via agent on email 15/07/2026 - Updated title information received from agent confirming land ownership 15/07/2026 - Confirmation issued that ownership details had been recorded and solicitor details requested
Gillian Rachel Brock |  | 20/4, 20/7, 21/8, 21/9, 22/1 | Overhead line rights construction and operational access rights | As Stuart Walter Brock (above)
Susan Rosalinde Blackie | OBJ-064 / OBJ-065 | 46/4, 46/6, 46/7, 46/8, 46/9, 47/1, 47/2, 47/3, 47/4, 49/1, 49/6 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 28/10/2025 - Emails exchanged between grantor and Savills to discuss the project in further detail 15/01/2026 - Offer letter issued via post 26/01/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 03/02/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 05/03/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 10/03/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 18/06/2026 - Email received from agent requesting documentation 22/06/2026 - Email issued to agent providing documentation 24/06/2026 - Existing consents issued to agent via email 01/07/2026 - Holding email sent to grantor/agent following receipt of CPO objection 02/07/2026 - Solicitor details chased via agent on email 14/07/2026 - Email received from agent requesting a meeting with OTW and National Grid to discuss the proposed works 15/07/2026 - Email issued requesting agent and client availability for a meeting 28/07/2026 - Sanitised deed issued to agent via email 05/08/2026 - Letter issued to grantor and agent in response to their objection
James George Blackie | OBJ-064 | 46/4, 46/6, 46/7, 46/8, 46/9, 47/1, 47/2, 47/3, 47/4, 49/1, 49/6 | Overhead line rights construction and operational access rights | As Susan Rosalinde Blackie (above)
Telefonica O2 Uk Limited |  | 10/10 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post
Telmara Farm Limited |  | 17/10, 18/3, 18/6 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued 27/10/2025 - Phone call held between grantor and Savills to discuss the project in further detail. 06/11/2025 - Site meeting with grantor to discuss project in further detail. 16/02/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 09/03/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 01/06/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Tesco Stores Limited |  | 142/2, 142/3, 143/2, 143/4 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued 15/01/2026 - Offer letter issued via Post 19/03/2026 - Chaser offer letter issued via Post 22/04/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 24/04/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 27/04/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via email 03/07/2026 - Email received advising that the matter remained under review by the relevant team and querying why solicitor details were required 06/07/2026 - Email issued explaining why solicitor details were required to progress the matter 07/07/2026 - Email received requesting further information about the project and confirmation of whether solicitor costs would be covered 07/07/2026 - Email issued providing the requested information 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
The Chelmsford Diocesan Board Of Finance | OBJ-070 | 8/11, 9/1, 25/6, 25/7, 26/1, 26/2, 26/4, 27/1, 27/4, 33/5, 33/6, 57/2, 60/6, 60/8, 60/11, 131/4, 131/6, 131/8, 147/3, 26/1a, 130/3, 130/4, 130/5 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued 15/01/2026 - Offer letter issued via Post 19/03/2026 - Chaser offer letter issued via Post 21/04/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 23/04/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 30/04/2026 - Email received regarding completion of Land Interest Questionnaires for multiple land holdings 12/05/2026 - Email issued answering queries regarding the Land Interest Questionnaire 12/05/2026 - Email issued proposing a Teams meeting to discuss occupier details 13/05/2026 - Project letter issued 14/05/2026 - Land consent documentation issued via email 18/05/2026 - Email received requesting clarification on the project 26/05/2026 - Email issued reattaching correspondence, requesting any queries or concerns, and offering a project meeting 04/06/2026 - CPO Notice issued via email 24/06/2026 - Meeting held with agent to the project in further detail 02/07/2026 - Solicitor details chased via agent on email 14/07/2026 - Email issued asking whether any further information was required to progress matters 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 05/08/2026 - Letter issued to grantor and agent in response to their objection
The County Council Of Essex |  | 1/2, 1/3, 1/6, 1/7, 1/8, 1/9, 2/2, 3/2, 3/3, 3/4, 4/2, 4/4, 5/1, 5/2, 5/4, 5/5, 7/2, 7/7, 7/8, 8/1, 8/2, 8/3, 8/7, 9/3, 9/4, 10/2, 10/7, 10/12, 11/1, 11/3, 11/4, 12/3, 12/6, 12/7, 13/6, 14/2, 14/2a, 14/2b, 15/1, 15/2, 15/3, 15/4, 16/1, 16/2, 16/4, 16/5, 17/2, 17/4, 17/6, 17/8, 17/10, 18/2, 18/3, 18/12, 19/8, 19/9, 19/12, 20/8, 21/3, 21/6, 21/7, 21/8, 21/9, 22/5, 22/6, 22/7, 22/8, 23/6, 24/1, 25/3, 25/5, 25/6, 25/7, 26/1, 26/2, 27/3, 27/7a, 28/1, 28/3, 28/4, 28/5, 29/2, 29/4, 30/4, 30/10, 30/11, 31/3, 31/4, 31/7, 32/6, 32/10, 32/11, 32/12, 32/15, 33/7, 33/8, 33/9, 33/12, 34/1, 34/2, 34/3, 35/1, 36/2, 36/4, 36/5, 36/6a, 36/7, 37/1, 37/3, 37/4, 37/5, 37/6, 37/7, 37/8, 38/1, 38/3, 39/5, 40/2, 41/2, 42/3, 42/5, 42/8, 44/4, 44/5, 44/6, 44/8, 44/10, 44/11, 44/12, 45/1, 45/2, 45/3, 45/6, 45/7, 45/8, 45/9, 45/10, 45/11, 46/1, 46/2, 46/3, 46/4, 46/5, 46/7, 46/8, 46/9, 47/2, 48/1, 48/2, 48/3, 48/4, 49/1, 49/3, 49/4, 49/5, 49/6, 49/7, 50/1, 50/2, 50/4, 50/8, 50/9, 51/9, 51/10, 51/11, 51/13, 52/1, 52/2, 52/3, 52/4, 52/5, 52/6, 52/7a, 52/8, 52/9, 53/3, 53/7, 54/1, 54/2, 54/3, 55/1, 55/5, 55/6, 55/7, 55/8, 55/9, 55/11, 56/1, 56/2, 56/3, 57/4, 57/5, 58/3, 58/4, 58/8, 58/9, 58/10, 59/2, 59/3, 59/4, 59/6, 59/7, 59/9, 60/4, 60/5, 60/14, 61/1, 61/2, 61/3, 61/4, 61/8, 62/2, 63/3, 63/8, 63/9, 63/10, 63/11, 63/16, 64/2, 64/3, 64/4, 65/2, 65/6, 65/9, 65/10, 65/11, 65/12, 65/13, 66/1, 66/2, 67/3, 67/5, 67/7, 67/9, 67/10, 67/12, 67/13, 67/14, 68/3, 68/12, 70/2, 70/4, 70/6, 70/10, 71/3, 71/6, 71/10, 71/11, 71/15, 72/7, 73/3, 74/1, 74/4, 74/5, 75/1, 75/2, 75/6, 75/8, 76/1, 76/2, 76/3, 76/5, 76/6, 77/1, 77/4, 78/1, 78/4, 78/6, 78/7, 79/1, 79/2, 79/6, 79/8, 79/9, 80/1, 80/2, 80/3, 80/5, 80/7, 81/1, 81/2, 81/4, 81/7, 81/9, 82/2, 82/3, 82/4, 82/5, 82/6, 82/7, 82/8, 83/1, 83/7, 83/19, 84/17, 84/20, 84/23, 84/24a, 85/1, 85/2, 85/3, 85/18, 86/1, 86/3, 86/4, 87/1, 87/2, 87/3, 88/1, 88/2, 88/3, 88/4, 89/1, 89/2, 89/9, 89/10, 89/11, 89/13, 89/14, 89/15, 90/1, 90/2, 91/4, 91/5, 91/6, 91/7, 92/1, 92/2, 92/3, 92/4, 92/6, 92/7, 93/2, 93/3, 93/4, 93/6, 93/8, 94/2, 94/3, 94/4, 94/5, 94/6, 94/7, 94/8, 95/1, 95/2, 95/3, 95/4, 95/5, 95/6, 96/3, 96/6, 96/10, 96/11, 97/1, 97/2, 97/3, 97/5, 98/4, 98/5, 98/6, 98/7, 98/10, 98/11, 98/12, 98/13, 99/1, 99/2, 99/3, 99/4, 99/5, 99/6, 99/7, 99/8, 99/10, 99/11, 99/12, 99/14, 100/1, 100/2, 100/3, 100/6, 100/7, 101/1, 101/5, 101/8, 101/15, 101/19, 102/1, 102/3, 102/4, 102/5, 102/7, 102/11, 102/12, 102/14, 103/1, 103/3, 103/4, 103/6, 103/7, 103/9, 103/11, 103/13, 103/15, 103/16, 103/17, 103/19, 103/20, 104/1, 104/2, 104/3, 104/5, 105/1, 105/2, 105/3, 105/4, 105/5, 105/6, 106/1, 106/2, 106/3, 106/4, 107/1, 107/2, 107/3, 107/4, 107/5, 107/6, 108/1, 108/2, 108/3, 108/4, 108/5, 108/6, 108/7, 108/8, 109/1, 109/2, 110/1, 110/4, 110/5, 110/6, 110/7, 110/8, 111/1, 111/2, 111/3, 111/5, 111/6, 112/1, 112/3, 112/5, 113/2, 113/3, 113/4, 113/5, 113/6, 113/7, 114/1, 114/3, 114/4, 115/1, 115/5, 115/8, 115/9, 115/11, 115/16, 115/17, 115/19, 116/1, 116/2, 116/3, 117/1, 117/2, 117/6, 117/7, 117/8, 117/9, 117/10, 117/11, 117/12, 117/13, 117/14, 117/15, 117/16, 118/1, 118/4, 118/6, 119/1, 119/2, 119/4, 119/6, 119/7, 119/14, 120/1, 121/1, 121/2, 121/3, 121/4, 121/5, 122/1, 123/1, 123/2, 123/3, 123/4, 123/5, 123/6, 124/1, 125/1, 125/2, 125/3, 125/4, 125/5, 125/6, 125/7, 125/8, 125/9, 125/10, 125/11, 125/12, 126/1, 126/2, 126/3, 126/4, 127/1, 127/3, 127/4, 128/2, 128/3, 128/6, 128/7, 128/8, 129/1, 129/4, 129/5, 129/7, 129/9, 130/2, 130/3, 130/8, 130/11, 130/13, 130/14, 131/2, 131/3, 131/7, 131/9, 132/3, 132/8, 132/11, 132/12, 133/1, 133/5, 133/8, 134/3, 134/4, 134/5, 134/6, 134/7, 134/9, 134/11, 135/6, 135/8, 137/3, 137/5, 137/6, 138/1, 138/2, 138/3, 138/4, 138/5, 138/6, 138/8, 138/9, 138/10, 138/11, 138/12, 139/1, 139/2, 139/3, 139/4, 139/5, 139/6, 140/1, 140/2, 140/3, 141/1, 141/2, 141/10, 141/14, 141/16, 141/17, 142/2, 142/3, 142/6, 143/2, 143/4, 143/10, 143/11, 143/13, 144/4, 145/1, 145/3, 145/15, 146/5, 146/8, 146/9, 146/10, 146/12, 146/13, 146/15, 146/16, 146/18, 146/28, 146/29, 146/30, 146/32, 146/34, 147/5, 147/6, 147/7, 147/9, 147/10, 147/11, 147/18, 147/19, 147/20, 148/1, 148/2, 148/14, 148/21, 148/30, 148/44, 148/54, 148/62, 149/2, 149/4, 149/6, 149/7, 149/8, 149/9, 149/12, 149/13, 150/2, 150/3, 150/4, 150/5, 150/6, 150/7, 150/8, 150/9, 150/10, 151/1, 151/4, 151/5, 151/6, 151/7, 151/9, 151/10, 151/11, 152/2, 152/3, 152/4, 67/15, 67/16, 67/17, 18/6 | Overhead line rights construction and operational access rights access rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post 19/03/2026 - Chaser offer letter sent via post 23/04/2026 - Email to grantor requesting the best department to deal with the offer letter 24/04/2026 - Email response from grantor putting us in contact with the best placed department for the offer letter 06/05/2026 – Email to agent with copy of offer letter and details regarding the scheme 13/05/2026 - Project letter issued 13/05/2026 – Chaser emailed for solicitor details and offer letter 20/05/2026 – Email exchanges with agent providing further context on the scheme 02/07/2026 – Chaser email regarding solicitor details 09/07/2026 – Agent confirmed solicitor details and confirmation this was captured from Savills 13/07/2026 - Email confirmation solicitor details have been captured
The Executor of Alan Covey |  | 25/6, 25/7, 26/1, 26/2, 26/4, 27/1, 27/2, 27/3, 27/4, 27/5, 28/2, 28/4, 28/6, 29/1, 26/1a | Overhead line rights construction and operational access rights | 03/09/2025 - Two Land Interest Questionnaires issued via post 01/10/2025 - Chaser Land interest questionnaire issued via post 15/01/2026 - Offer Letter issued via post 19/03/2026 - Chaser offer letter issued via post 23/04/2026 - Chaser sent via email in response to offer letter 06/05/2026 - Chaser sent via email in response to offer letter 13/05/2026 - Solicitor details chased 19/05/2026 - Response from land agent 13/05/2026 - Project letter issued 01/06/2026 - Appointed land agent confirmation 04/06/2026 - Site meeting arranged 09/06/2026 - Teams meeting with agent - details discussed 17/06/2026 - Further information provided to agent 02/07/2026 - Chaser for solicitor details 13/07/2026 - Correspondence with agent 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Valerie Susan Timmons |  | 16/3, 16/4, 16/5, 16/6, 16/7, 16/8, 16/9, 17/1, 17/2, 17/3, 17/4, 17/5, 17/6, 17/7, 17/8, 17/9, 18/1, 18/2 | Overhead line rights | As The Executor of Alan Covey (above)
The Executor of Sheila Kathleen Cannon |  | 30/2, 30/3 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 08/09/2025 - Phone call received from grantor with queries about the project. 15/01/2026 - Offer letter issued via post. 19/03/2026 - Chaser offer letter issued via post. 08/04/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 22/04/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email 14/07/2026 - Email issued chasing solicitor details 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 28/07/2026 - Phone call held with the landowner who confirmed they were happy to proceed and did not require a meeting. Further project details were discussed
The Executor of Silva Lesley Carter |  | 148/27 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer letter issued via post. 19/03/2026 - Chaser offer letter issued via post. 27/04/2026 - Door knocking undertaken by Savills with aim to discuss project in further detail 30/04/2026 - Phone call attempted to discuss the land ownership position; unable to make contact and advised to call back at a later date 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email
The Governing Body Of Beauchamps |  | 147/20, 148/1 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 14/10/2025 - Phone call received from LH to discuss the Land Interest Questionnaire
The JE Lindsell Trust & Mrs E Lindsell Trust |  | 16/3, 16/4, 16/5, 16/6, 16/7, 16/8, 16/9, 17/1, 17/2, 17/3, 17/4, 17/5, 17/6, 17/7, 17/8, 17/9, 18/1, 18/2 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer letter issued via post. 21/01/2026 - Email from agent advising they are now acting for the land owner 02/02/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 17/02/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 01/04/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail 13/05/2026 - Project letter issued 10/06/2026 - Email received from agent confirming that a colleague would take over conduct of the matter, and records were updated accordingly 23/06/2026 - Email exchanged regarding agent rates 02/07/2026 - Solicitor details chased via agent on email 15/07/2026 - Solicitor details received via email from agent 15/07/2026 - Email issued confirming solicitor details had been captured and proposing a meeting 02/08/2026 - Email received confirming agent details 03/08/2026 - Email issued confirming agent details were held on record and provided documentation for agent review 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
The JE Lindsell Trust |  | 16/3, 16/4, 16/5, 16/6, 16/7, 16/8, 16/9, 17/1, 17/2, 17/3, 17/4, 17/5, 17/6, 17/7, 17/8, 17/9, 18/1, 18/2 | Overhead lines rights Construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post via Post. 1/10/2025 - Chaser Land Interest Questionnaire Issued 15/01/2026 - Offer letter issued via post. 21/01/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 02/02/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 17/02/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 01/04/2026 - Emails exchanged between grantor and Savills to discuss the project in further detail. 13/05/2026 - Project letter issued 09/06/2026 - CPO Notice issued to the land agent via email 10/06/2026 - Email received from agent advising who will be the new agent 23/06/2026 - Email exchanged confirming agreed agent details 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
The Notleys Golf Club Limited |  | 101/1, 101/2, 102/1, 102/4, 102/2, 102/14, 102/15 | Overhead line rights construction and operational access rights | 13/10/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser letter issued via post
The Official Custodian For Charities - The Town Estate | OBJ-035 | 22/5, 22/6, 22/8, 23/1, 23/3 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued via post 28/10/2025 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 29/10/2025 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 29/10/2025 - Site meeting booked with grantor to discuss project in further detail. 15/01/2026 - Offer letter issued via post. 29/01/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 10/02/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 23/02/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 02/03/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 05/03/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email 05/08/2026 - Letter issued to grantor and agent in response to their objection
The Scout Association Trust Corporation | OBJ077 | 63/9, 63/11, 63/12, 63/14, 63/16, 64/2 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued via post 22/10/2025 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 10/11/2025 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 15/01/2026 - Offer letter issued via post. 19/03/2026 - Chaser offer letter issued via post. 23/03/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 13/05/2026 - Project letter issued 13/05/2026 - Solicitor details and offer letter status chased via email 03/06/2026 - Email received confirming appointed acting agent 04/06/2026 - Project correspondence and requested documentation issued to agent via email 01/07/2026 - Holding email sent to grantor/agent following receipt of CPO objection 02/07/2026 - Solicitor details chased via agent on email 14/07/2026 - Email received from agent requesting a meeting to discuss the proposed works 15/07/2026 - Email issued requesting agent and client availability for a meeting 28/07/2026 - Sanitised deed issued to agent via email 05/08/2026 - Letter issued to grantor and agent in response to their objection
The Trustees Of Wickford Town Football Club | OBJ075 | 147/18, 147/19, 147/20, 148/1, 148/57, 148/60, 148/61, 149/3, 149/5 | Overhead line rights construction and operational access rights | 08/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Offer letter issued via post. 19/03/2026 - Chaser offer letter issued via post. 30/03/2026 - Phone call and email to grantor to discuss the project in further detail. 02/07/2026 - Holding email sent to grantor/agent following receipt of CPO objection 05/08/2026 - Letter issued to grantor and agent in response to their objection
The Trustees Of The Rotary Club Of Wickford Trust Fund |  | 148/57, 148/60, 148/61, 149/3, 149/5 | Overhead line rights construction and operational access rights | As Trustees of Wickford Town Football Club (above)
Thomas James Mortlock |  | 42/10, 42/11, 42/12, 42/13, 43/1, 43/2, 43/3, 43/4, 44/1, 44/2, 48/1, 48/2, 48/3, 48/4, 49/2, 49/3, 49/4, 49/5 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 25/09/2025 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 13/10/2025 - Phone call and email to grantor to discuss the project in further detail. 20/10/2025 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 19/11/2025 - Phone call and email to grantor to discuss the project in further detail. 15/01/2026 - Offer letter issued via post. 26/02/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 10/03/2026 - Summery of Key Terms issued via Email 23/04/2026 - Email issued to the appointed agent enquiring whether any further information was required to progress matters 23/04/2026 - Email received from the agent to confirm position 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email
Robert Mortlock |  | 42/10, 42/11, 42/12, 42/13, 43/1, 43/2, 43/3, 43/4, 44/1, 44/2, 48/4, 49/2, 49/3, 49/4, 48/1, 48/2, 48/3 | Overhead line rights construction and operational access rights | As Thomas James Mortlock (above)
Thomas James Mortlock |  | 42/10, 42/11, 42/12, 42/13, 43/1, 43/2, 43/3, 43/4, 44/1, 44/2, 48/1, 48/2, 48/3, 48/4, 49/2, 49/3, 49/4, 49/5 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 25/09/2025 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 13/10/2025 - Phone call and email to grantor to discuss the project in further detail. 20/10/2025 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 19/11/2025 - Phone call and email to grantor to discuss the project in further detail. 15/01/2026 - Offer letter issued via post. 19/01/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 16/02/2026 -Email received from landowner discussing Land Interest Questionnaire / project in further detail 13/05/2026 - Project letter issued 09/06/2026 - CPO Notice issued to the agent via email 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Timothy Edward Ruggles-Brise |  | 33/10, 33/11, 33/12, 34/1, 34/2, 34/4, 34/5, 34/6, 35/2, 35/3, 35/4, 35/5, 36/1, 36/3, 36/6, 36/6a, 36/7, 36/8, 37/1, 37/2, 37/3, 37/4, 37/6, 38/1 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 27/09/2025 - Phone call and email to grantor to discuss the project in further detail 27/09/2025 - Site meeting booked with grantor to discuss project in further detail 06/10/2025 - Site meeting held with land agent to discuss the project and any existing rights in further detail 28/10/2025 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 19/11/2025 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 15/01/2026 - Offer letter issued via post 21/01/2026 - Copy of offer letter issued via email to Land Agent 26/01/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 25/02/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 10/03/2026 - Summary of key terms sent via email as requested 25/03/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email 17/07/2026 - Email received regarding solicitor details and costs 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 27/07/2026 - Confirmation sent regarding solicitors queries from National Grid
Andrew William Kennedy Merriam |  | 33/10, 33/11, 33/12, 34/1, 34/2, 34/4, 34/5, 34/6, 35/2, 35/3, 35/4, 35/5, 36/1, 36/3, 36/6, 36/6a, 36/7, 36/8, 37/1, 37/2, 37/3, 37/4, 37/6, 38/1 | Overhead line rights construction and operational access rights | As Timothy Edward Ruggles- Brise (above)
Henry Michael Napier Bunbury |  | 33/10, 33/11, 33/12, 34/1, 34/2, 34/4, 34/5, 34/6, 35/2, 35/3, 35/4, 35/5, 36/1, 36/3, 36/6, 36/6a, 36/7, 36/8, 37/1, 37/2, 37/3, 37/4, 37/6, 38/1 | Overhead line rights construction and operational access rights | As Timothy Edward Ruggles- Brise (above)
Anna Clare Ruggles-Brise |  | 33/10, 33/11, 33/12, 34/1, 34/2, 34/4, 34/5, 34/6, 35/2, 35/3, 35/4, 35/5, 36/1, 36/3, 36/6, 36/6a, 36/7, 36/8, 37/1, 37/2, 37/3, 37/4, 37/6, 38/1 | Overhead line rights construction and operational access rights | As Timothy Edward Ruggles- Brise (above)
Timothy Edward Ruggles-Brise |  | 33/10, 33/11, 33/12, 34/1, 34/2, 34/4, 34/5, 34/6, 35/2, 35/3, 35/4, 35/5, 36/1, 36/3, 36/6, 36/6a, 36/7, 36/8, 37/1, 37/2, 37/3, 37/4, 37/6, 38/1 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued via post 27/09/2025 - Phone call and email to LH to discuss the project in further detail. 27/09/2025 - Site meeting booked with LH to discuss their FH part. 28/10/2025 - Email received from LH discussing Land Interest Questionnaire / project in further detail 19/11/2025 - Email received from LH discussing Land Interest Questionnaire / project in further detail 15/01/2026 - Offer letter issued via post 10/03/2026 - Summary of Key Terms issued to the appointed agent via email 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email 17/07/2026 - Email received querying solicitor fees and the project in further detail 27/07/2026 - Email issued from Savills confirming details and answering queries
Timothy George Buck |  | 78/2, 78/5 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued via post 22/10/2025 - Phone call and email to grantor to discuss the project in further detail. 19/11/2025 - Phone call and email to grantor to discuss the project in further detail. 15/01/2026 - Offer letter issued via post. 28/01/2026 - Email received from land agent discussing Land Interest Questionnaire / project in further detail 12/02/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 27/02/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 10/03/2026 - Summary of key terms issued on request via email 13/04/2026 - Email received from landowner discussing Land Interest Questionnaire / project in further detail 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email 02/07/2026 - Email received requesting an update on outstanding comments and amendments 02/07/2026 - Email issued confirming that comments and amendments had been submitted to National Grid for review and offering a site meeting to discuss the project and any potential issues 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Timothy Stewart Smith |  | 13/2, 13/4 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued 15/01/2026 - Offer letter was sent via post 19/03/2026 - Offer Letter chaser was sent via post 27/04/2026 - Site meeting with grantor to discuss project in further detail. 30/04/2026 - Email to Grantor with copy of offer letter and overview of the project 07/05/2026 - Email issued providing availability for a meeting to discuss the project 11/05/2026 - Online meeting held with the appointed agent to discuss the project and how it may affect the landowner's interests 13/05/2026 - Project letter issued 02/07/2026 - Agent correspondence received via email confirming representation of the landowner 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Tina Louise Magness |  | 19/3, 19/4, 19/13, 21/4, 21/5 | Overhead line rights construction and operational access rights | 03/09/2025 - Land interest questionnaire issued via post 24/10/2025 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 29/12/2025 Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 15/01/2026 - Offer letter was sent via post 19/03/2026 - Offer Letter chaser was sent via post 01/04/2026 - Communications on hold until query regarding ongoing easement is resolved 13/05/2026 - Project letter issued 13/05/2026 - Email issued chasing solicitor details and seeking an update on the offer letter 02/07/2026 - Chaser sent regarding solicitor details
Colin David Magness |  | 18/16, 18/17, 19/1, 19/2, 19/3, 19/4, 19/13, 21/4, 21/5 | Overhead line rights | As Tina Louise Magness (above)
Transport UK East Anglia Limited |  | 101/12, 101/16 | Not used | 08/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued via post 28/10/2025 - Email received from LH discussing Land Interest Questionnaire / project in further detail 10/11/2025 - Email received from LH discussing Land Interest Questionnaire / project in further detail 18/11/2025 - Email received from LH discussing Land Interest Questionnaire / project in further detail
Trisha Helen Lovricic |  | 45/4 | Construction and operational access rights Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/10/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 22/10/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 15/01/2026 - Offer letter was sent via post 19/03/2026 - Offer Letter chaser was sent via post 27/04/2026 - Door knock undertaken to discuss the project; no contact made and a letter was left at the property 13/05/2026 - Project letter issued 02/07/2026 - Agent correspondence received via email confirming representation of the landowner 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 29/07/2026 - Phone call made to the landowner; voicemail left requesting a call back 05/08/2026 - Phone call received from the landowner regarding the offer and advised they would review the relevant documentation and discuss further in due course
Twinstead Hall Farms Limited | OBJ-069 | 65/3, 65/6, 65/7, 65/8, 65/9, 65/10, 65/11 | Construction and operational access rights Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 1/10/2025 - Chaser Land Interest Questionnaire Issued via post 15/01/2026 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 15/01/2026 - Offer letter was sent via post 26/02/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 11/05/2026 - Teams meeting held with the appointed agent to discuss the project and how it may affect the landowner's interests 13/05/2026 - Project letter issued 14/05/2026 - Email issued to discuss project in further detail 14/05/2026 - Email received raising queries regarding consents 21/05/2026 - Email issued responding to raised queries 04/06/2026 - CPO documentation issued via email 08/06/2026 - Solicitor details received from the appointed agent via email 09/06/2026 - Email issued confirming solicitor details have been captured 02/07/2026 - Holding email sent to grantor/agent following receipt of CPO objection 30/07/2026 - Draft deed issued to the appointed agent via email 05/08/2026 - Letter issued to grantor and agent in response to their objection
Vernon Charles Nott |  | 61/2, 61/3, 61/4, 61/5, 61/6, 61/7, 61/8, 62/1, 62/3, 63/1, 63/2, 63/4, 63/5, 63/6, 63/9, 63/11, 63/15, 63/16, 64/1, 64/2 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire issued via post 09/09/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 18/09/2025 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 23/09/2025 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. Site meeting also arranged 30/09/2025 - Site meeting held with grantor to discuss the project and requirements in further detail 15/01/2026 - Offer letter issued via post 31/03/2026 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 13/05/2026 - Project letter issued 09/06/2026 - CPO Notice issued to the landowner via email 02/07/2026 - Solicitor details chased via agent on email
Walter Buckley |  | 101/2, 101/3, 101/6, 102/15 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 15/01/2026 - Offer letter was sent via post 19/03/2026 - Offer Letter chaser was sent via post 13/05/2026 - Project letter issued 02/07/2026 - Solicitor details chased via agent on email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Wilcon Homes Anglia Limited |  | 147/2 | Construction and operational access rights Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser letter issued via post 15/01/2026 - Offer letter issued via post 19/03/2026 - Chaser offer letter issued via post 29/04/2026 - Email to grantor requesting solicitor details 06/05/2026 - Signed appendix received via email from agent 06/05/2026 - Summary of Key Terms issued via email and solicitor details requested 12/05/2026 - Email issued chasing solicitor details 21/05/2026 - Email correspondence received regarding ownership 13/05/2026 - Project letter issued 16/06/2026 - Email correspondence exchanged to identify the appropriate contact and progress the matter 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 29/07/2026 - Email issued to a third party seeking details of the appropriate contact and solicitor information for the affected land interests
William Eric Drake | OBJ-051 | 68/2, 68/4, 68/7, 68/10, 68/11 | Construction and operational access rights Overhead line rights | 03/09/2025 - Land Interest Questionnaire issued via post 08/09/2025 - Phone call received from grantor with queries on the project as the assets on their land are being removed as part of another project. Grantor confirmed details of their appointed agent 08/09/2025 - Emails exchanged with agent to answer their queries in relation to both schemes over this land 15/01/2026 - Offer letter issued via post and copy sent to agent via email 20/01/2026 - Phone call with land agent to discuss their queries around easement requirements 09/02/2026 - Email sent to agent with copies of all letters issued to grantor to date 16/02/2026 - Email exchanged regarding project documentation, including clarification on the project requirements 13/05/2026 - Project letter issued 02/07/2026 - Holding email sent to grantor/agent following receipt of CPO objection 02/07/2026 - Solicitor details chased via agent on email 05/08/2026 - Letter issued to grantor and agent in response to their objection
William George Pewter |  | 53/8, 55/3, 55/4, 55/6, 55/7, 55/8 | Construction and operational access rights Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 07/10/2025 - Phone call received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 15/01/2026 - Offer letter was sent via post 19/03/2026 - Offer Letter chaser was sent via post 23/04/2026 - Phone call made to discuss the offer letter and progression of the matter; advised to call back later to speak with the relevant party 13/05/2026 - Project letter issued 02/07/2026 - Agent correspondence received via email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 29/07/2026 - Phone call held with the landowner regarding the project
Harriet Mary Jordan |  | 55/7, 55/8 | Overhead line rights | As WIlliam George Pewther (above)
William George Sheen |  | 133/6, 134/8 | Overhead line rights | 08/09/2025 - Land interest questionnaire issued via post. 13/10/2025 - Phone call received from LO to discuss the Land Interest Questionnaire / offer that has been made. 25/11/2025 - Email received from landowner to discuss the Land Interest Questionnaire / offer that has been made. 15/01/2026 - Offer letter was sent via post 19/03/2026 - Offer Letter chaser was sent via post 13/05/2026 - Project letter issued 13/05/2026 - Email issued chasing solicitor details and seeking an update on the offer letter 14/05/2026 - Email received requesting a copy of the Summary of Key Terms 21/05/2026 - Summary of Key Terms issued via email together with further information regarding access requirements 02/07/2026 - Solicitor details chased via agent on email 06/07/2026 - Email received querying project details and compensation 07/07/2026 - Email issued providing clarification and confirming key details 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 29/07/2026 - Phone call made regarding the project; voicemail left requesting a call back 06/08/2026 - Email issued regarding the project and requesting contact from the landowner
Clare Louise Sheen |  | 133/6, 134/8 | Overhead line rights | As William George Sheen (above)
Wren Renewables (Holdings) Limited |  | 93/1, 93/2, 94/7, 94/8 | Overhead line rights | 03/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Land Interest Questionnaire Issued
Maisie Blatch |  |  |  | 15/01/2026 - Offer Letter issued via post 19/03/2026 - Chaser offer letter issued via post 23/04/2026 - Email from son of grantor confirming POA and willingness to enter into an easement. Signed offer letter returned via email 13/05/2026 - Project Update Letter issued via post 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savillsx 30/07/2026 - Solicitor details provided via email
The Owner/Occupier (Christina Walther previous owner but sold this property back in November 2025) |  |  |  | 15/01/2026 - Offer Letter issued via post 19/03/2026 - Chaser offer letter issued via post 13/05/2026 - Project Update Letter issued via post 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 28/07/2026 - Confirmation received that the landowner sold this property last year
Taylor Berkeley Limited |  |  |  | 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 11/08/2026 - Company now dissolved
Jon Stalley |  |  |  | 26/03/2026 - Offer Letter issued via post 30/03.2026 - Phone call with grantor to discuss queries regarding the offer letter and requesting further information on the project. Recommendation was given for grantor to appoint a land agent. Second phone call received from grantor confirming they have now appointed an agent and provided us with their details 13/05/2026 - Project Update Letter issued via post 09/06/2026 - CPO Notice letter issued to agent via email 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 27/07/2026 - Phone call received from grantor confirming that any site meeting requests need to be booked via his agent
Gillian Foster Smith |  |  |  | 26/03/2026 - Offer Letter issued via post 11/05/2026 - Email received from grantor advising they have been out of the country and to get in touch with their agent 12/05/2026 - Email sent to grantor's agent with further information on the project and to discuss fees 13/05/2026 - Project Update Letter issued via post 04/06/2026 - Chaser Offer Letter issued via post 12/06/2026 - Email received from grantor requesting recommendations for agents who can act on their behalf 15/06/2026 - Email sent to grantor with a list of agents who may be able to represent them 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills
Bell & Godden |  |  |  | 26/03/2026 - Offer Letter issued via post 27/04/2026 - Site meeting held with grantor 13/05/2026 - Project Update Letter issued via post 04/06/2026 - Chaser offer letter issued via post 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 29/07/2026 - Phone call received from the landowner seeking clarification on the project
The Major Whitbread Charity |  |  |  | 26/03/2026 - Offer Letter issued via post 16/04/2026 - Email sent to grantor with information on the project and Summary of Key Terms was also issued via email 13/05/2026 - Project Update Letter issued via post 04/06/2026 - Chaser offer letter issued via post 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 29/07/2026 - Phone call to grantor to see if there are any further queries regarding the project, voicemail was left 31/07/2026 - Phone call received from grantor confirming willingness to enter into an agreement and next steps
Sue J Forret |  |  |  | 26/03/2026 - Offer Letter issued via post 13/05/2026 - Project Update Letter issued via post 16/06/2026 - Phone call received from grantor advising they had still not received the offer letter via post. Confirmed appointment of land agent and solicitor details provided 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 26/07/2026 - Phone call received from grantor confirming the offer letter had still not been received 31/07/2026 - Offer Letter hand delivered to grantor
Lt. Col. R P T Earle |  |  |  | 26/03/2026 - Offer Letter issued via post 01/04/2026 - Emails sent to confirm offer letter had been received and if they had any queries in relation to this 04/04/2026 - Email received from grantor advising they would call after the weekend 09/04/2026 - Chaser offer letter issued via post 27/04/2026 - Email received from grantor providing solicitor details 13/05/2026 - Project Update Letter issued via post 26/05/2026 - Email received from grantor confirming their appointment of a land agent 26/05/2026 - Email to agent requesting confirmation of agent acting on belhalf of the grantor 29/06/2026 - Emails exchanged with the agent regarding agreement of fees 02/07/2026 - Holding email sent to grantor and agent following the receipt of their objection 08/07/2026 - Email sent to agent with copies of all documents issued to date and further details regarding the project 24/07/2026 - Letter seeking them to arrange a meeting with NGET/Savills 28/07/2026 - Email received from grantor notifying us of some points regarding the property 30/07/2026 - Precedent deed issued to agent

## Sheet3
Essex County Council | 1/2, 1/3, 1/6, 1/7, 1/8, 1/9, 2/2, 3/2, 3/3, 3/4, 4/2, 4/4, 5/1, 5/2, 5/4, 5/5, 7/2, 7/7, 7/8, 8/1, 8/2, 8/3, 8/7, 9/3, 9/4, 10/2, 10/7, 10/12, 11/1, 11/3, 11/4, 12/3, 12/6, 12/7, 13/6, 14/2, 14/2a, 14/2b, 15/1, 15/2, 15/3, 15/4, 16/1, 16/2, 16/4, 16/5, 17/2, 17/4, 17/6, 17/8, 17/10, 18/2, 18/3, 18/12, 19/8, 19/9, 19/12, 20/8, 21/3, 21/6, 21/7, 21/8, 21/9, 22/5, 22/6, 22/7, 22/8, 23/6, 24/1, 25/3, 25/5, 25/6, 25/7, 26/1, 26/2, 27/3, 27/7a, 28/1, 28/3, 28/4, 28/5, 29/2, 29/4, 30/4, 30/10, 30/11, 31/3, 31/4, 31/7, 32/6, 32/10, 32/11, 32/12, 32/15, 33/7, 33/8, 33/9, 33/12, 34/1, 34/2, 34/3, 35/1, 36/2, 36/4, 36/5, 36/6a, 36/7, 37/1, 37/3, 37/4, 37/5, 37/6, 37/7, 37/8, 38/1, 38/3, 39/5, 40/2, 41/2, 42/3, 42/5, 42/8, 44/4, 44/5, 44/6, 44/8, 44/10, 44/11, 44/12, 45/1, 45/2, 45/3, 45/6, 45/7, 45/8, 45/9, 45/10, 45/11, 46/1, 46/2, 46/3, 46/4, 46/5, 46/7, 46/8, 46/9, 47/2, 48/1, 48/2, 48/3, 48/4, 49/1, 49/3, 49/4, 49/5, 49/6, 49/7, 50/1, 50/2, 50/4, 50/8, 50/9, 51/9, 51/10, 51/11, 51/13, 52/1, 52/2, 52/3, 52/4, 52/5, 52/6, 52/7a, 52/8, 52/9, 53/3, 53/7, 54/1, 54/2, 54/3, 55/1, 55/5, 55/6, 55/7, 55/8, 55/9, 55/11, 56/1, 56/2, 56/3, 57/4, 57/5, 58/3, 58/4, 58/8, 58/9, 58/10, 59/2, 59/3, 59/4, 59/6, 59/7, 59/9, 60/4, 60/5, 60/14, 61/1, 61/2, 61/3, 61/4, 61/8, 62/2, 63/3, 63/8, 63/9, 63/10, 63/11, 63/16, 64/2, 64/3, 64/4, 65/2, 65/6, 65/9, 65/10, 65/11, 65/12, 65/13, 66/1, 66/2, 67/3, 67/5, 67/7, 67/9, 67/10, 67/12, 67/13, 67/14, 68/3, 68/12, 70/2, 70/4, 70/6, 70/10, 71/3, 71/6, 71/10, 71/11, 71/15, 72/7, 73/3, 74/1, 74/4, 74/5, 75/1, 75/2, 75/6, 75/8, 76/1, 76/2, 76/3, 76/5, 76/6, 77/1, 77/4, 78/1, 78/4, 78/6, 78/7, 79/1, 79/2, 79/6, 79/8, 79/9, 80/1, 80/2, 80/3, 80/5, 80/7, 81/1, 81/2, 81/4, 81/7, 81/9, 82/2, 82/3, 82/4, 82/5, 82/6, 82/7, 82/8, 83/1, 83/7, 83/19, 84/17, 84/20, 84/23, 84/24a, 85/1, 85/2, 85/3, 85/18, 86/1, 86/3, 86/4, 87/1, 87/2, 87/3, 88/1, 88/2, 88/3, 88/4, 89/1, 89/2, 89/9, 89/10, 89/11, 89/13, 89/14, 89/15, 90/1, 90/2, 91/4, 91/5, 91/6, 91/7, 92/1, 92/2, 92/3, 92/4, 92/6, 92/7, 93/2, 93/3, 93/4, 93/6, 93/8, 94/2, 94/3, 94/4, 94/5, 94/6, 94/7, 94/8, 95/1, 95/2, 95/3, 95/4, 95/5, 95/6, 96/3, 96/6, 96/10, 96/11, 97/1, 97/2, 97/3, 97/5, 98/4, 98/5, 98/6, 98/7, 98/10, 98/11, 98/12, 98/13, 99/1, 99/2, 99/3, 99/4, 99/5, 99/6, 99/7, 99/8, 99/10, 99/11, 99/12, 99/14, 100/1, 100/2, 100/3, 100/6, 100/7, 101/1, 101/5, 101/8, 101/15, 101/19, 102/1, 102/3, 102/4, 102/5, 102/7, 102/11, 102/12, 102/14, 103/1, 103/3, 103/4, 103/6, 103/7, 103/9, 103/11, 103/13, 103/15, 103/16, 103/17, 103/19, 103/20, 104/1, 104/2, 104/3, 104/5, 105/1, 105/2, 105/3, 105/4, 105/5, 105/6, 106/1, 106/2, 106/3, 106/4, 107/1, 107/2, 107/3, 107/4, 107/5, 107/6, 108/1, 108/2, 108/3, 108/4, 108/5, 108/6, 108/7, 108/8, 109/1, 109/2, 110/1, 110/4, 110/5, 110/6, 110/7, 110/8, 111/1, 111/2, 111/3, 111/5, 111/6, 112/1, 112/3, 112/5, 113/2, 113/3, 113/4, 113/5, 113/6, 113/7, 114/1, 114/3, 114/4, 115/1, 115/5, 115/8, 115/9, 115/11, 115/16, 115/17, 115/19, 116/1, 116/2, 116/3, 117/1, 117/2, 117/6, 117/7, 117/8, 117/9, 117/10, 117/11, 117/12, 117/13, 117/14, 117/15, 117/16, 118/1, 118/4, 118/6, 119/1, 119/2, 119/4, 119/6, 119/7, 119/14, 120/1, 121/1, 121/2, 121/3, 121/4, 121/5, 122/1, 123/1, 123/2, 123/3, 123/4, 123/5, 123/6, 124/1, 125/1, 125/2, 125/3, 125/4, 125/5, 125/6, 125/7, 125/8, 125/9, 125/10, 125/11, 125/12, 126/1, 126/2, 126/3, 126/4, 127/1, 127/3, 127/4, 128/2, 128/3, 128/6, 128/7, 128/8, 129/1, 129/4, 129/5, 129/7, 129/9, 130/2, 130/3, 130/8, 130/11, 130/13, 130/14, 131/2, 131/3, 131/7, 131/9, 132/3, 132/8, 132/11, 132/12, 133/1, 133/5, 133/8, 134/3, 134/4, 134/5, 134/6, 134/7, 134/9, 134/11, 135/6, 135/8, 137/3, 137/5, 137/6, 138/1, 138/2, 138/3, 138/4, 138/5, 138/6, 138/8, 138/9, 138/10, 138/11, 138/12, 139/1, 139/2, 139/3, 139/4, 139/5, 139/6, 140/1, 140/2, 140/3, 141/1, 141/2, 141/10, 141/14, 141/16, 141/17, 142/2, 142/3, 142/6, 143/2, 143/4, 143/10, 143/11, 143/13, 144/4, 145/1, 145/3, 145/15, 146/5, 146/8, 146/9, 146/10, 146/12, 146/13, 146/15, 146/16, 146/18, 146/28, 146/29, 146/30, 146/32, 146/34, 147/5, 147/6, 147/7, 147/9, 147/10, 147/11, 147/18, 147/19, 147/20, 148/1, 148/2, 148/14, 148/21, 148/30, 148/44, 148/54, 148/62, 149/2, 149/4, 149/6, 149/7, 149/8, 149/9, 149/12, 149/13, 150/2, 150/3, 150/4, 150/5, 150/6, 150/7, 150/8, 150/9, 150/10, 151/1, 151/4, 151/5, 151/6, 151/7, 151/9, 151/10, 151/11, 152/2, 152/3, 152/4, 67/15, 67/16, 67/17, 18/6 | Overhead line rights Construction and operational | 08/09/2025 - Land interest questionnaire issued via post 01/10/2025 - Chaser Letter sent via post 19/03/2026 - Chaser offer letter sent via post 23/04/2026 - Email to grantor requesting the best department to deal with the offer letter 24/04/2026 - Email response from grantor putting us in contact with the best placed department for the offer letter

## Sheet1
Overhead line rights
Construction and operational access rights
Construction compound rights
Overhead line rights Construction and operational access rights
Overhead line rights Construction and operational access rights Construction compound rights

## Sheet2
Contact Name | PLOTNO
A.H.Philpot & Sons 2 Limited | 150/6, 150/7, 150/8, 151/1, 151/6, 151/7, 151/8, 151/11, 152/2, 152/3, 150/9
Aaron James Howlett | 148/6, 148/40
Transport UK East Anglia Limited | 101/12, 101/16
Platinum (PP) Trustees Limited | 48/1, 48/2, 48/3
The Executor of Alan Covey | 25/6, 25/7, 26/1, 26/2, 26/4, 27/1, 27/2, 27/3, 27/4, 27/5, 28/2, 28/4, 28/6, 29/1, 26/1a
Alan Payne | 148/60, 148/61, 149/5
Alan Robert Bull | 83/2, 83/5, 83/13, 83/14, 83/15, 83/16
Alison Jayne Lucas | 101/1, 101/2, 102/1, 102/3, 102/4, 102/7, 103/3, 103/5, 103/6, 102/14, 102/15, 103/8, 103/14, 103/16
Amanda Jane French | 68/8, 69/1, 100/4, 100/5, 101/13, 101/17, 101/18
Andrew Guy Speakman | 115/5, 115/8, 128/1, 128/2, 128/4, 129/1, 129/2, 129/3, 129/5, 129/6, 129/8, 131/3, 131/4, 130/7, 130/8, 130/11, 130/12, 130/13
Andrew James Buck | 75/3, 75/4, 75/5, 75/7, 75/9, 78/2, 78/3, 78/5, 79/3, 79/5
Andrew John Thorogood | 124/1, 125/1, 125/3, 125/7, 125/8, 125/9, 125/10, 125/11, 126/1, 126/2, 126/3, 127/1, 127/3, 127/4, 128/7, 128/8
Andrew Robert Hodge | 132/8, 133/1, 133/5, 134/4, 134/5, 134/9, 134/11
Andrew Simon Chapman | 115/3, 115/4, 115/6
Andrew William Kennedy Merriam | 33/10, 33/11, 33/12, 34/1, 34/2, 34/4, 34/5, 34/6, 35/2, 35/3, 35/4, 35/5, 36/1, 36/3, 36/6, 36/6a, 36/7, 36/8, 37/1, 37/2, 37/3, 37/4, 37/6, 38/1
Andrew William Morton | 98/4, 98/6, 98/7, 98/8
Angela Brock | 21/8, 21/9, 22/1, 22/3, 22/4, 22/5, 22/6, 20/4
Angela Irene Mary Mcmillan | 44/6, 45/2
Anglian Water Services Limited | 31/3, 31/8, 31/10, 31/11, 32/1, 32/2, 32/3, 32/4, 32/5, 32/6, 32/7, 45/8, 45/10, 46/2, 59/2, 59/3, 59/10, 60/2, 60/7, 64/3, 64/4, 65/1, 96/4, 96/5, 119/6, 121/2, 127/2, 128/5, 146/18, 146/30, 147/5, 147/7, 147/9, 147/10, 147/13, 147/16, 148/62, 149/13, 32/8, 32/9, 32/10
The Executor of Ann Martina Tunstall | 146/18, 146/23, 146/30, 146/31, 147/5
Ann Mary Hogsbjerg | 72/3, 73/2
Anna Clare Ruggles-Brise | 33/10, 33/11, 33/12, 34/1, 34/2, 34/4, 34/5, 34/6, 35/2, 35/3, 35/4, 35/5, 36/1, 36/3, 36/6, 36/6a, 36/7, 36/8, 37/1, 37/2, 37/3, 37/4, 37/6, 38/1
Anna Frances Wilson | 32/12, 32/13
Annabelle Clare Howard | 2026-05-19
Anne Chong Yang Tay-Smith | 141/21, 141/22
Anne Deborah Wilson | 68/2, 68/6
Anne Dora Williams | 83/14, 83/15
Anne Elizabeth Graves | 16/3, 16/5, 16/6, 16/7, 16/8, 16/9, 17/1, 17/2, 17/3, 17/5, 17/7, 17/8, 17/9, 18/1, 18/4, 18/5, 18/7, 18/10, 18/2
Anneli Mabel Frances Mann | 140/3, 141/1, 141/14, 141/18, 141/19, 141/20
Anthony John Morris | 148/10, 148/11, 148/26, 148/50
The Executor of Anthony John Walther | 81/10
Antonia Kirstin Brewster | 119/9
Antony Peter Drain | 76/8
Antony Read | 68/11
Antony Richardson | 130/3
Apt (Farming) Limited | 150/6, 150/7, 150/8, 151/1, 151/6, 151/7, 151/11, 152/2, 152/3, 150/9
On Tower UK 2 Limited | 131/2, 131/5, 131/7, 131/9, 132/3, 132/10, 132/11, 146/18, 146/30, 147/5, 147/7, 147/9, 147/10
On Tower UK Limited | 99/1, 99/2, 99/7, 99/7a, 100/1, 100/7, 130/1, 138/7
Arthur Philip Harvey Brock | 20/4, 21/8, 21/9, 22/1, 22/3, 22/4, 22/5, 22/6
The Executor of Arthur Vernon Muskett | 10/14, 11/1, 11/2, 11/3, 11/3a, 11/5, 11/6, 11/7, 11/8, 11/9, 11/10, 11/11, 11/12, 12/1, 12/2, 12/3
Ashleigh James Lambert | 111/7
Aubrey Philp | 51/7, 51/9, 51/10, 51/11, 52/1, 52/3, 52/4, 52/5, 52/7, 52/7a, 52/7b, 52/8, 52/9, 52/10, 52/11, 53/1
Barbara Ruth Greer | 58/5, 58/6
Basildon Borough Council | 147/11, 147/17, 147/18, 147/19, 147/20, 148/1, 148/2, 148/14, 148/21, 148/30, 148/44, 148/54, 148/62, 149/2, 149/4, 149/13
Begin Braintree Limited | 98/2, 98/4, 98/5, 98/6, 99/6, 99/14, 98/7, 98/8
Benjamin George Hughes | 84/1, 84/2, 84/3, 84/5, 84/7, 84/8, 84/13, 85/8, 85/9, 85/11, 85/12, 85/13, 85/17
Benjamin Thomas Twinn | 69/2, 70/1, 70/4, 71/9, 71/11, 69/3, 69/4, 70/2, 70/3, 70/5, 70/7, 70/8, 70/9, 70/11, 71/6, 71/7, 71/15
Berwick Hall Farm Limited | 39/3, 39/4, 39/5, 39/6, 39/8, 39/9, 39/10, 39/11, 39/12, 39/13, 39/14, 40/1, 40/2, 41/1, 41/2, 44/6, 44/10, 44/11, 45/1, 45/2, 45/5, 45/7, 45/9, 45/10, 46/1, 46/2, 46/3, 46/5
Betty Mortlock | 42/10, 42/11, 42/12, 42/13, 43/1, 43/2, 43/3, 43/4, 44/1, 44/2
Bollington Hall Limited | 7/3, 7/4, 8/4, 8/6, 8/9
Bower Croft Limited | 3/3, 3/4, 4/2, 4/3, 4/4, 5/1, 6/2, 6/3, 7/1
Braintree District Council | 51/3, 63/12, 63/14, 80/8, 81/6, 81/11, 81/12, 99/5, 101/1, 101/2, 101/3, 102/1, 102/4, 102/14, 102/15
Brett Group Properties Limited | 131/1, 131/2, 131/4, 131/5, 131/7, 131/9, 132/1, 132/3, 132/6, 132/9, 132/10, 132/11
Cadent Gas Limited | 23/2, 23/4, 23/5, 77/4, 78/1, 78/4, 99/3, 99/4, 99/8, 101/2, 101/3, 119/2, 119/4, 119/14, 120/1, 121/3, 121/4, 121/5, 122/1, 123/1, 123/2, 123/3, 123/4, 123/5, 123/6, 125/2, 125/4, 132/8, 133/1, 133/5, 134/9, 134/11, 144/4, 145/1, 145/3, 145/8, 145/13, 145/14, 145/15, 145/16, 146/12, 146/18, 146/30, 146/34, 147/5, 147/7, 147/10, 151/13, 152/5, 152/6, 102/15
Capital Road Safety Limited | 50/12, 50/13, 50/15, 51/1, 51/2, 51/4
Caroline Elizabeth Burchell | 43/4
Caroline Gezzele White | 19/11, 21/1, 21/3
Caroline Jane Kemp | 84/1, 84/2, 84/3, 84/5, 84/7, 84/8, 84/13, 85/8, 85/9, 85/11, 85/12, 85/13, 85/17
Caroline Rachel Boyle | 93/1, 93/2, 93/5, 93/7, 94/2, 94/4, 94/5, 94/8
Caroline Vanessa Lindsell | 31/3, 31/10, 32/1, 32/3, 32/4, 32/6, 32/7, 32/9, 32/10, 32/11
Carter & Ward Of Wickford Limited | 147/20, 148/1, 148/2, 148/6, 148/8, 148/9, 148/10, 148/11, 148/12, 148/13, 148/14, 148/15, 148/16, 148/17, 148/18, 148/19, 148/20, 148/21, 148/23, 148/24, 148/25, 148/26, 148/27, 148/28, 148/29, 148/30, 148/31, 148/32, 148/33, 148/34, 148/35, 148/36, 148/37, 148/38, 148/39, 148/40, 148/41, 148/42, 148/43, 148/44, 148/45, 148/46, 148/48, 148/49, 148/50, 148/51, 148/52, 148/53, 148/55
Cedric Frank George Nott | 59/2, 59/3, 59/10, 60/2, 60/7
Cemex Uk Operations Limited | 93/1, 93/2, 94/7, 94/8, 115/4, 115/6
Charles Anthony Maurice Boileau | 33/10, 33/11, 33/12, 34/1, 34/2, 34/4, 34/5, 34/6, 35/2, 35/3
Charles Herbert Scott | 147/3
Charmian Rose Goundry | 97/1, 97/3, 97/5, 98/8, 98/10, 98/11, 98/13
Chase Loveridge | 2026-11-10
Delta Housing Limited | 98/1, 98/3, 99/1, 99/2, 99/7, 99/7a, 99/15, 100/1, 100/3, 100/7, 130/13
Runningwell Equestrian Centre Limited | 143/6, 143/8, 143/12
Christina Walther | 81/10
Christopher Ernest Dellow | 2026-08-23
Christopher Francis Edward Hill | 89/1, 89/5, 89/12, 90/1, 90/2, 91/1, 91/2, 91/3, 91/4, 91/5, 91/6, 91/8, 92/1, 92/2, 92/4, 92/5, 92/6, 93/1, 93/2, 93/3, 93/5, 93/6, 93/7, 94/2, 94/4, 94/5, 94/8, 89/3, 89/4, 89/6, 89/7, 89/8
Christopher Francis Speakman | 115/5, 115/8, 128/1, 128/2, 128/4, 129/1, 129/2, 129/3, 129/5, 129/6, 129/8, 131/3, 131/4, 130/7, 130/8, 130/11, 130/12, 130/13
Christopher John Blewett | 37/9, 37/10, 38/2, 38/4, 38/5, 38/6, 38/7, 38/8, 38/9, 38/10, 38/11, 38/13, 39/2
Christopher John Clark | 2026-07-19
Christopher Stokes | 145/2
Church Commissioners For England | 59/6, 59/9, 60/4, 60/9, 60/12, 60/13, 60/14, 61/1, 131/6, 131/8
Clare Louise Sheen | 133/6, 134/8
Clare Patricia Douglas | 32/12, 32/13
Clive Lodge | 148/60, 148/61, 149/5
Colin David Magness | 18/16, 18/17, 19/1, 19/2, 19/3, 19/4, 19/13, 21/4, 21/5
Colin Gary Tarner | 8/6, 8/8, 8/9
Colin Tunstall | 146/18, 146/23, 146/30, 146/31, 147/5
Colne Valley Railway Company Limited | 50/12, 50/15, 51/1, 51/4, 51/6, 51/8
Conor David John Black | 148/38
Cornerstone Telecommunications Infrastructure Limited | 10/14, 11/1, 11/2, 11/3, 11/3a, 11/7, 11/12, 12/1, 12/2, 51/11, 52/1, 52/5, 52/7, 52/7a, 52/7b
Countryside Properties (Uk) Limited | 144/4, 145/1, 145/3, 145/8, 145/13, 145/14, 145/15, 145/16, 146/12, 146/34
Countryside L&Q (Beaulieu) LLP | 115/1, 116/1, 116/2, 116/3, 117/1, 117/2, 117/6, 117/7, 117/8, 117/11, 117/12, 117/13, 117/14, 117/15, 117/16, 118/1, 118/4
Craig Arthur Harry Fisher | 115/1, 116/1, 116/2, 116/3, 117/1, 117/2, 117/6, 117/7, 117/8, 117/9, 117/10, 117/11, 117/12, 117/13, 117/14, 117/15, 117/16, 118/1, 118/4, 118/6
Craig Hampton | 145/5
Crossbrook Farms Limited | 39/3, 39/4, 39/5, 39/6, 39/7, 39/8, 39/9, 39/10, 39/11, 39/12, 39/13, 39/14, 40/1, 40/2, 40/3, 41/1, 41/2
Curt John Hodson | 145/6
D.A. Phillips & Co Limited | 145/5, 145/6
Daniel Lee Wilson | 146/18, 146/30, 146/31, 147/5
Daniella Michelle Conway | 49/7, 50/1, 50/2, 50/4, 50/5, 50/8
David Andrew Brewster | 119/9
David Angus Small | 48/1, 48/2, 48/3
David Clive Hedges | 10/5, 10/6
David Cooper | 44/9, 44/10, 44/11, 45/1, 45/5
David Frank Nott | 57/2, 57/3, 57/4, 57/5, 58/1, 58/2, 58/3, 58/6, 58/8, 58/9, 58/11, 58/12, 59/1, 59/6, 59/9, 60/4, 60/9, 60/12, 60/14, 61/1
The Executor of David James Anstee | 115/10, 115/13
David John Burton | 44/7
David John Grantham | 148/39
David Lawrence Bolton | 119/2, 119/4, 119/6, 119/12, 119/13, 119/14, 120/1, 120/2, 121/1, 121/2, 121/3, 121/4, 121/5, 122/1, 123/1, 123/2, 123/3, 123/4, 123/5, 123/6, 123/7, 125/2, 125/4, 125/5, 125/6, 120/4
David Martin Peasgood | 2026-10-19
David Murray Pack | 141/21
David Samuel Knox | 146/9, 146/18, 146/30, 146/31, 146/33, 147/3, 147/5, 147/7, 147/9, 147/10
Dean Gary Harper | 147/8
Dean John Bezzina | 146/25, 146/26, 146/31
Dean Lowe | 146/1, 146/4, 146/5, 146/7, 146/10, 146/15, 146/18, 146/29, 146/30, 147/5
Deborah May Ruffel | 53/8, 55/3, 55/4, 55/6
Deborah Susan Brown | 113/3, 113/6, 113/7, 113/7a, 114/1, 114/3, 114/4, 115/19
Debra Christine Scott | 147/3
The Executor of Denis Cleary | 148/28
Denise Susan Ethel Dear | 143/5
Direct Transportation Limited | 84/1, 84/3, 84/4, 84/5, 84/7, 84/8, 84/9, 84/10, 84/11, 84/12, 84/13
Donald James Dear | 143/5
Donna Marie Sommerford | 146/18, 146/21, 146/30, 146/31, 147/5
The Executor of Doris Theresa Anstee | 115/10, 115/13
Duncan George Deadman | 146/18, 146/21, 146/30, 146/31, 147/5
E. & R. Fuller Limited | 27/6, 27/7, 27/7a, 28/3, 28/5, 29/2, 29/4, 31/5, 31/6, 33/1, 33/2, 33/8, 33/9, 28/5a, 32/16, 32/17, 32/18
Eastern Power Networks plc | 1/1, 1/2, 1/3, 1/4, 3/3, 3/4, 4/2, 4/3, 4/4, 5/1, 25/6, 25/7, 26/1, 26/2, 26/4, 27/1, 27/4, 27/6, 27/7, 27/7a, 28/3, 28/5, 29/2, 29/4, 64/3, 64/4, 65/1, 67/7, 68/5, 99/3, 99/4, 99/8, 111/7, 117/1, 117/6, 117/15, 118/1, 118/6, 128/3, 128/6, 129/7, 130/1, 143/8, 143/12, 144/4, 145/1, 145/3, 145/8, 145/13, 145/14, 145/15, 145/16, 146/1, 146/3, 146/4, 146/5, 146/7, 146/10, 146/15, 146/29, 146/34, 147/4, 147/14, 148/57, 148/62, 149/3, 149/13, 150/6, 150/7, 150/8, 151/1, 151/6, 151/7, 151/8, 151/9, 151/10, 151/11, 151/12, 151/13, 152/2, 152/3, 152/4, 152/5, 152/6, 152/8, 26/1a, 28/5a, 67/15, 67/16, 150/9
Edmund Nott | 71/8, 71/13
Edward Albert Webb | 84/22
Edward Arthur Heath | 102/10, 103/12, 103/15, 103/17, 103/18, 104/6
The Executor of Edward John Lindsell | 16/3, 16/4, 16/5, 16/6, 16/7, 16/8, 16/9, 17/1, 17/2, 17/3, 17/4, 17/5, 17/6, 17/7, 17/8, 17/9, 18/1, 18/2
The Executor of Eileen Catherine Carter | 148/23, 148/33, 148/37
Eleanor Jean Levoir Harris | 148/6, 148/40
Elizabeth Caroline Lloyd | 13/5, 13/6, 14/1, 14/2, 14/2a, 14/2b, 15/1, 15/2, 15/3, 15/4, 16/1, 16/2
Elizabeth Frances Temple | 67/4, 67/6, 67/7, 67/11, 68/4, 68/5, 67/15, 67/16
Elizabeth Holly Cook | 102/10, 103/12, 103/15, 103/17, 103/18, 104/6
Elizabeth Margaret Xenakis | 80/4, 80/8, 81/5, 81/12
Elizabeth Mary Newton | 53/5, 53/6, 53/7, 54/1, 55/1, 55/2, 55/5, 55/11, 56/1, 56/2
Emily Jane Boileau | 33/10, 33/11, 33/12, 34/1, 34/2, 34/4, 34/5, 34/6, 35/2, 35/3
Emma Louise Taylor | 148/8, 148/9, 148/45
Environment Agency | 10/6, 10/9, 11/5, 11/6, 11/8, 11/10, 11/11, 12/4, 14/1, 22/3, 31/8, 31/11, 32/2, 32/5, 32/7, 39/10, 40/2, 41/2, 49/2, 51/7, 72/2, 72/4, 81/3, 93/5, 93/7, 125/5, 125/6, 131/4, 132/4, 132/6, 132/7, 136/6, 137/3, 137/5, 137/6, 138/1, 138/2, 138/5, 138/8, 147/3, 147/13, 147/16, 147/17, 147/18, 147/19, 147/20, 148/1, 32/8, 32/9, 32/11, 32/12, 32/13, 32/14
Erin Grace Hughes | 148/38
Essex County Council | 1/2, 1/3, 1/6, 1/7, 1/8, 1/9, 2/2, 3/2, 3/3, 3/4, 4/2, 4/4, 5/1, 5/2, 5/4, 5/5, 7/2, 7/7, 7/8, 8/1, 8/2, 8/3, 8/7, 9/3, 9/4, 10/2, 10/7, 10/12, 11/1, 11/3, 11/4, 12/3, 12/6, 12/7, 13/6, 14/2, 14/2a, 14/2b, 15/1, 15/2, 15/3, 15/4, 16/1, 16/2, 16/4, 16/5, 17/2, 17/4, 17/6, 17/8, 17/10, 18/2, 18/3, 18/12, 19/8, 19/9, 19/12, 20/8, 21/3, 21/6, 21/7, 21/8, 21/9, 22/5, 22/6, 22/7, 22/8, 23/6, 24/1, 25/3, 25/5, 25/6, 25/7, 26/1, 26/2, 27/3, 27/7a, 28/1, 28/3, 28/4, 28/5, 29/2, 29/4, 30/4, 30/10, 30/11, 31/3, 31/4, 31/7, 32/6, 32/10, 32/11, 32/12, 32/15, 33/7, 33/8, 33/9, 33/12, 34/1, 34/2, 34/3, 35/1, 36/2, 36/4, 36/5, 36/6a, 36/7, 37/1, 37/3, 37/4, 37/5, 37/6, 37/7, 37/8, 38/1, 38/3, 39/5, 40/2, 41/2, 42/3, 42/5, 42/8, 44/4, 44/5, 44/6, 44/8, 44/10, 44/11, 44/12, 45/1, 45/2, 45/3, 45/6, 45/7, 45/8, 45/9, 45/10, 45/11, 46/1, 46/2, 46/3, 46/4, 46/5, 46/7, 46/8, 46/9, 47/2, 48/1, 48/2, 48/3, 48/4, 49/1, 49/3, 49/4, 49/5, 49/6, 49/7, 50/1, 50/2, 50/4, 50/8, 50/9, 51/9, 51/10, 51/11, 51/13, 52/1, 52/2, 52/3, 52/4, 52/5, 52/6, 52/7a, 52/8, 52/9, 53/3, 53/7, 54/1, 54/2, 54/3, 55/1, 55/5, 55/6, 55/7, 55/8, 55/9, 55/11, 56/1, 56/2, 56/3, 57/4, 57/5, 58/3, 58/4, 58/8, 58/9, 58/10, 59/2, 59/3, 59/4, 59/6, 59/7, 59/9, 60/4, 60/5, 60/14, 61/1, 61/2, 61/3, 61/4, 61/8, 62/2, 63/3, 63/8, 63/9, 63/10, 63/11, 63/16, 64/2, 64/3, 64/4, 65/2, 65/6, 65/9, 65/10, 65/11, 65/12, 65/13, 66/1, 66/2, 67/3, 67/5, 67/7, 67/9, 67/10, 67/12, 67/13, 67/14, 68/3, 68/12, 70/2, 70/4, 70/6, 70/10, 71/3, 71/6, 71/10, 71/11, 71/15, 72/7, 73/3, 74/1, 74/4, 74/5, 75/1, 75/2, 75/6, 75/8, 76/1, 76/2, 76/3, 76/5, 76/6, 77/1, 77/4, 78/1, 78/4, 78/6, 78/7, 79/1, 79/2, 79/6, 79/8, 79/9, 80/1, 80/2, 80/3, 80/5, 80/7, 81/1, 81/2, 81/4, 81/7, 81/9, 82/2, 82/3, 82/4, 82/5, 82/6, 82/7, 82/8, 83/1, 83/7, 83/19, 84/17, 84/20, 84/23, 84/24a, 85/1, 85/2, 85/3, 85/18, 86/1, 86/3, 86/4, 87/1, 87/2, 87/3, 88/1, 88/2, 88/3, 88/4, 89/1, 89/2, 89/9, 89/10, 89/11, 89/13, 89/14, 89/15, 90/1, 90/2, 91/4, 91/5, 91/6, 91/7, 92/1, 92/2, 92/3, 92/4, 92/6, 92/7, 93/2, 93/3, 93/4, 93/6, 93/8, 94/2, 94/3, 94/4, 94/5, 94/6, 94/7, 94/8, 95/1, 95/2, 95/3, 95/4, 95/5, 95/6, 96/3, 96/6, 96/10, 96/11, 97/1, 97/2, 97/3, 97/5, 98/4, 98/5, 98/6, 98/7, 98/10, 98/11, 98/12, 98/13, 99/1, 99/2, 99/3, 99/4, 99/5, 99/6, 99/7, 99/8, 99/10, 99/11, 99/12, 99/14, 100/1, 100/2, 100/3, 100/6, 100/7, 101/1, 101/5, 101/8, 101/15, 101/19, 102/1, 102/3, 102/4, 102/5, 102/7, 102/11, 102/12, 102/14, 103/1, 103/3, 103/4, 103/6, 103/7, 103/9, 103/11, 103/13, 103/15, 103/16, 103/17, 103/19, 103/20, 104/1, 104/2, 104/3, 104/5, 105/1, 105/2, 105/3, 105/4, 105/5, 105/6, 106/1, 106/2, 106/3, 106/4, 107/1, 107/2, 107/3, 107/4, 107/5, 107/6, 108/1, 108/2, 108/3, 108/4, 108/5, 108/6, 108/7, 108/8, 109/1, 109/2, 110/1, 110/4, 110/5, 110/6, 110/7, 110/8, 111/1, 111/2, 111/3, 111/5, 111/6, 112/1, 112/3, 112/5, 113/2, 113/3, 113/4, 113/5, 113/6, 113/7, 114/1, 114/3, 114/4, 115/1, 115/5, 115/8, 115/9, 115/11, 115/16, 115/17, 115/19, 116/1, 116/2, 116/3, 117/1, 117/2, 117/6, 117/7, 117/8, 117/9, 117/10, 117/11, 117/12, 117/13, 117/14, 117/15, 117/16, 118/1, 118/4, 118/6, 119/1, 119/2, 119/4, 119/6, 119/7, 119/14, 120/1, 121/1, 121/2, 121/3, 121/4, 121/5, 122/1, 123/1, 123/2, 123/3, 123/4, 123/5, 123/6, 124/1, 125/1, 125/2, 125/3, 125/4, 125/5, 125/6, 125/7, 125/8, 125/9, 125/10, 125/11, 125/12, 126/1, 126/2, 126/3, 126/4, 127/1, 127/3, 127/4, 128/2, 128/3, 128/6, 128/7, 128/8, 129/1, 129/4, 129/5, 129/7, 129/9, 130/2, 130/3, 130/8, 130/11, 130/13, 130/14, 131/2, 131/3, 131/7, 131/9, 132/3, 132/8, 132/11, 132/12, 133/1, 133/5, 133/8, 134/3, 134/4, 134/5, 134/6, 134/7, 134/9, 134/11, 135/6, 135/8, 137/3, 137/5, 137/6, 138/1, 138/2, 138/3, 138/4, 138/5, 138/6, 138/8, 138/9, 138/10, 138/11, 138/12, 139/1, 139/2, 139/3, 139/4, 139/5, 139/6, 140/1, 140/2, 140/3, 141/1, 141/2, 141/10, 141/14, 141/16, 141/17, 142/2, 142/3, 142/6, 143/2, 143/4, 143/10, 143/11, 143/13, 144/4, 145/1, 145/3, 145/15, 146/5, 146/8, 146/9, 146/10, 146/12, 146/13, 146/15, 146/16, 146/18, 146/28, 146/29, 146/30, 146/32, 146/34, 147/5, 147/6, 147/7, 147/9, 147/10, 147/11, 147/18, 147/19, 147/20, 148/1, 148/2, 148/14, 148/21, 148/30, 148/44, 148/54, 148/62, 149/2, 149/4, 149/6, 149/7, 149/8, 149/9, 149/12, 149/13, 150/2, 150/3, 150/4, 150/5, 150/6, 150/7, 150/8, 150/9, 150/10, 151/1, 151/4, 151/5, 151/6, 151/7, 151/9, 151/10, 151/11, 152/2, 152/3, 152/4, 67/15, 67/16, 67/17, 18/6
Essex Wildlife Trust Limited | 26/3, 67/8
Fairking Limited | 79/2, 79/4, 79/7, 79/8, 79/9, 80/2, 80/3, 80/5, 80/6
Fiona Alison Shaw | 4/5, 4/6, 5/2, 5/3, 5/6, 5/7, 6/1
Fiona Lindsell | 31/3, 31/10, 32/1, 32/3, 32/4, 32/6, 32/10
Francis David Ruffel | 53/8, 55/3, 55/4, 55/6
Garry Andrews | 141/4, 141/5, 141/6, 141/7, 141/8
Gary Christopher Maseyk | 22/5, 22/6
Gary Clayton | 113/3, 113/6, 113/7, 113/7a, 114/1, 114/3, 114/4, 115/19
Gary Philip Springett | 115/2, 115/7
Gary Thomas Willats | 149/10, 149/11, 150/1
Gavin Adams | 22/3, 22/4, 22/5, 22/6
Gent Fairhead Aggregates Limited | 93/1, 93/2, 94/7, 94/8
Geoffrey Laurence Morland | 31/3, 31/10, 32/1, 32/3, 32/4, 32/6, 32/10
George Francis Caton | 23/7, 23/9, 23/11, 23/13, 24/1, 24/3, 25/3, 25/4, 25/5, 24/2
Gillian Argent | 41/3, 41/4, 42/1, 42/2
Gillian Clare Newton | 53/5, 53/6, 53/7, 54/1, 55/1, 55/2, 55/5, 55/11, 56/1, 56/2
Gillian Foster Smith | 60/13
Gillian Janet Roberts | 72/2, 72/4, 73/4, 74/3
Gillian Kathleen Hingston | 19/9, 21/6, 21/7, 22/2, 22/3, 22/4, 22/5, 22/6, 21/6a, 20/2, 20/3
Gillian Mary Read | 68/11
Gillian Rachel Brock | 20/4, 20/7, 21/8, 21/9, 22/1
Gillian Wendy Hart | 96/5
Giuliana Pina Fisher | 115/1, 116/1, 116/2, 116/3, 117/1, 117/2, 117/6, 117/7, 117/8, 117/9, 117/10, 117/11, 117/12, 117/13, 117/14, 117/15, 117/16, 118/1, 118/4, 118/6
Gordon Gray | 30/14, 31/1, 31/2
Graeme Paul Wade | 102/8
Graham Anthony Vivian | 74/1, 75/1
Graham Peter Brian Carter | 148/23, 148/26, 148/27, 148/29, 148/33
Graham Robert Anstee | 115/10, 115/13
Gray & Sons (Chelmsford) Limited | 137/3, 137/5, 137/6, 138/1, 138/2, 138/4, 138/5, 138/7, 138/8, 138/10, 138/11, 138/12, 139/1, 139/2, 139/4, 139/5, 140/2
GSH Farming Limited | 134/3, 134/6, 135/1, 135/2, 135/6, 135/8
Hammonds Estates LLP | 124/1, 125/1, 125/3, 125/5, 125/6, 125/7, 125/8, 125/9, 125/10, 125/11, 126/1, 126/2, 126/3, 127/1, 127/3, 127/4, 128/1, 128/3, 128/4, 128/6, 128/7, 128/8, 129/2, 129/7, 129/8
Hannah Lesley Harradine | 25/6, 25/7, 26/1, 26/2, 26/4, 27/1, 27/4, 26/1a
Hanson Quarry Products Europe Limited | 69/2, 70/1, 70/4, 71/9, 71/11, 115/1, 115/2, 116/1, 116/2, 116/3, 117/1, 117/2, 117/6, 117/7, 117/8, 117/9, 117/10, 117/11, 117/12, 117/13, 117/14, 117/15, 117/16, 118/1, 118/4, 118/6
Harriet Hull | 83/4, 83/7, 84/18, 84/19, 84/21, 84/23, 84/24, 84/24a, 84/25
Harriet Mary Jordan | 55/7, 55/8
Harry Edward Baines | 12/3, 12/4, 12/5, 12/6, 12/7, 12/8, 12/9, 13/1, 13/3
Hasan Salih | 146/22, 146/31
Hayley Diana Manning | 148/23, 148/33
Hayley Garner | 148/23, 148/33
Hazel Kay Lock | 140/3, 141/1, 141/14, 141/18, 141/19, 141/20, 141/21
Hazel Marion Latham | 23/2, 23/3, 23/4, 23/5
Hazel Pamela Cooper | 65/5
Helen Bryden Barr | 133/3, 133/4, 133/7, 134/1, 134/2, 134/3, 134/6, 134/7, 135/3, 135/4, 135/5, 135/6, 135/7, 135/8, 135/9, 136/10, 136/4, 136/5, 136/6, 136/9
Helen Catherine Lavender | 31/3, 31/10, 32/1, 32/3, 32/4, 32/6, 32/7, 32/9, 32/10, 32/11
Henny Holdings Limited | 64/3, 64/4, 65/1, 79/4, 79/7
Henry Andrew Heath | 102/10, 103/12, 103/15, 103/17, 103/18, 104/6
Henry Michael Napier Bunbury | 33/10, 33/11, 33/12, 34/1, 34/2, 34/4, 34/5, 34/6, 35/2, 35/3, 35/4, 35/5, 36/1, 36/3, 36/6, 36/6a, 36/7, 36/8, 37/1, 37/2, 37/3, 37/4, 37/6, 38/1
Holly Patricia Blackwell | 84/14, 84/15, 85/3, 85/5, 85/6, 85/8, 85/10, 85/11, 85/14, 85/15, 85/16, 87/1, 85/1
Homes England | 144/4, 145/1, 145/3, 145/8, 145/13, 145/14, 145/15, 145/16, 146/12, 146/34
HRG Property Investments Limited | 31/9
Hugh Richard Edwards | 19/9, 20/2, 20/3, 21/6, 21/7, 22/2, 22/3, 22/4, 22/5, 22/6, 22/8, 23/1, 21/6a
Ian Christopher Watson | 1/1, 1/2, 1/5, 1/8, 1/9, 2/1, 2/2, 2/2a, 2/3, 3/1
Ian David Coyne | 99/5
Ian David Hart | 50/12, 50/15, 51/1, 51/4, 51/6, 51/7, 51/8
Ian Stokes | 115/2, 115/7
Irene Mary Elsdon | 53/3
Jack Cameron Riddell | 148/8, 148/9, 148/45
Jack Piper Lowe | 146/4, 146/5, 146/7, 146/8, 146/11, 146/18, 146/29, 146/30, 147/5
Jack William Wright | 67/5, 67/9, 67/12
Jacqueline Anne Watson | 44/9, 44/10, 44/11, 45/1, 45/5
Jacqueline Muriel Parish | 85/17
Jacqueline Paul | 53/2
James Andrew Brown | 113/3, 113/6, 113/7, 113/7a, 114/1, 114/3, 114/4, 115/19
James George Blackie | 46/4, 46/6, 46/7, 46/8, 46/9, 47/1, 47/2, 47/3, 47/4, 49/1, 49/6
James Harry Reay | 9/4, 9/5, 10/2, 10/6, 10/8, 10/9, 10/10
James Henry Howard | 115/10, 115/15
James Paul Borges | 77/4, 78/1, 78/4
James Reginald Francis Hill | 89/1, 89/5, 89/12, 90/1, 90/2, 91/1, 91/3, 91/4, 91/5, 91/6, 91/8, 92/1, 92/2, 92/4, 92/5, 92/6, 93/3, 93/6, 89/3, 89/4, 89/6, 89/7, 89/8
James Richard Tee | 4/5, 4/6, 5/2, 5/3, 5/6, 5/7, 6/1
James Robert Bridges | 141/19, 141/20, 141/21
James Robert Loader | 148/23, 148/33
Jane Marie Wickham | 148/23, 148/33
Jane Shelagh Blewett | 37/9, 37/10, 38/2, 38/4, 38/5, 38/6, 38/7, 38/8, 38/9, 38/10, 38/11, 38/13, 39/2
Janet Ann Craft | 29/5, 30/7, 30/8, 30/10, 30/11
Janet Elizabeth Hill | 136/6, 136/8, 137/2, 137/4
Janet Elizabeth Piper | 145/10, 145/12, 146/1, 146/2, 146/3, 146/4, 146/5, 146/6, 146/7, 146/10, 146/13, 146/15, 146/16, 146/17, 146/18, 146/19, 146/29, 146/30, 146/31, 147/5
Janet Elizabeth Wiseman | 71/2, 71/4, 71/5
Jean Pauline Gould | 146/25, 146/26, 146/31
The Executor of Jennifer Louise Wade | 102/8
Jennifer May Clayton | 113/3, 113/6, 113/7, 113/7a, 114/1, 114/3, 114/4, 115/14, 115/18, 115/19
Jeremy Adrian Hill | 74/2, 74/4, 74/5, 75/2
Jeremy James Fisher | 103/10, 103/11, 104/2, 105/5, 105/6, 104/3, 104/3a, 104/4, 104/5
Jeremy Robin Sibson-Barnes | 107/2, 108/4
Jessica Alice Westrop | 54/3, 55/9, 55/10
Jill Louise Sinfield | 149/10, 149/11, 150/1
Jill Margaret Burton | 44/7
Jillian Mary Hope | 65/12, 65/14, 65/15, 66/2, 67/2, 67/3, 67/4
Joanna Lucinda Griffith | 22/3, 22/4, 22/5, 22/6
Joanne Gaught | 25/6, 25/7, 26/1, 26/2, 26/4, 27/1, 27/4, 26/1a
John Alec Mcmurtrie | 42/6, 42/7, 42/9
John Angus Crowther | 49/7, 50/1, 50/2, 50/4, 50/8, 50/10, 50/12, 50/13, 50/15, 51/1, 51/2, 51/4, 51/5, 51/7, 50/11
John Drysdale | 132/13, 133/2
John Everett | 114/2, 115/12
John Fraser Mcglashan | 73/1
John Hoole | 42/6, 42/7
John Joseph Murphy | 141/2, 141/6, 141/13
John Michael Crowther | 49/7, 50/1, 50/2, 50/4, 50/8, 50/12, 50/13, 50/15, 51/1, 51/2, 51/4, 51/6, 51/8
John Philp | 51/7, 51/9, 51/10, 51/11, 52/1, 52/3, 52/4, 52/5, 52/7, 52/7a, 52/7b, 52/8, 52/9, 52/10, 52/11, 53/1
John Richard Puddefoot | 22/3, 22/4, 22/5, 22/6
John Sidney Blackwell | 84/14, 84/15, 85/3, 85/5, 85/6, 85/8, 85/10, 85/11, 85/12, 85/13, 85/14, 85/15, 85/16, 87/1, 85/1
John Winston Argent | 41/3, 41/4, 42/1, 42/2
Jonathan Charles Burchell | 43/4
Jonathan Dixon Smith | 96/1, 96/2, 96/7, 96/8, 96/9, 97/1, 97/3, 97/5, 97/6, 97/7, 98/10, 98/11, 98/13
Jonathan Peter Douglas-Hughes | 117/2, 117/6, 117/7, 117/8, 117/12, 117/14, 117/15, 118/4, 118/6
Jonathan Richard Craft | 29/5, 30/7, 30/8, 30/10, 30/11
Josephine Greta Adams | 71/12, 72/1, 72/5, 72/8
Julia Frances Lampshire | 72/2, 72/4
Julia Verity Hughes | 84/1, 84/3, 84/4, 84/5, 84/7, 84/8, 84/9, 84/10, 84/11, 84/12, 84/13
Julian Barry Paul | 53/2
Julian Philip Newton | 53/5, 53/6, 53/7, 54/1, 55/1, 55/2, 55/5, 55/11, 56/1, 56/2
Julie Ann Hoole | 42/6, 42/7
The Executor of June Beatrice Drysdale | 132/13, 133/2
Justin Hart | 141/4, 141/5, 141/7, 141/8, 141/11, 141/13, 141/15, 141/17, 142/1, 142/5, 142/6, 141/22, 143/13
Karen Suzanne Lowe | 146/1, 146/4, 146/5, 146/7, 146/10, 146/15, 146/18, 146/29, 146/30, 147/5
Kate Alexandra Ramsey | 83/2, 83/5, 83/6, 83/8, 83/10, 83/11, 83/13, 83/14, 83/15, 83/16, 84/26
Katherine Girdwood Muskett | 10/14, 11/1, 11/2, 11/3, 11/3a, 11/5, 11/6, 11/7, 11/8, 11/9, 11/10, 11/11, 11/12, 12/1, 12/2, 12/3
Katy Emily Shadbolt | 76/5
Kay Andrews | 141/4, 141/5, 141/6, 141/7, 141/8
Keith Trevor Ripper | 45/7, 45/9, 45/10, 46/1, 46/2, 46/3, 46/4, 46/5, 46/6, 46/7, 47/3, 47/4, 49/1, 49/2, 49/6, 49/7, 50/1, 50/2, 50/4, 50/8
Kellie Jane Longman | 148/35
Kent & Sussex Properties Limited | 145/12, 146/6, 146/13, 146/14, 146/16, 146/31
Kerry Jane Foy | 101/9, 101/11
Kerstine Tina Callis | 96/5
Laura Ellen Morris | 148/10, 148/11, 148/26, 148/50
Laura Kathleen Wilson | 146/18, 146/30, 146/31, 147/5
Laura Thorogood | 124/1, 125/1, 125/3, 125/7, 125/8, 125/9, 125/10, 125/11, 126/1, 126/2, 126/3, 127/1, 127/3, 127/4, 128/7, 128/8
Lauren Catherine Hawker | 119/9
Laurence John Hull | 83/4, 84/25
Leeann Claire Burridge | 45/10, 46/2
Lee David Carter | 148/23, 148/33
Lee Martin Callis | 96/5
Leila Dawn Smithers | 148/17, 148/24, 148/26, 148/31, 148/48
Lesley Ann Rush | 41/5, 42/4
Lesley Caroline Willats | 149/10, 149/11, 150/1
Liam Lynam | 143/1, 143/3
Linda Joy Hardisty | 148/19, 148/31, 148/41, 148/49
Linda Kadesh | 148/39
Lindsay Dawn Bush | 146/31
Links Solar Farm Limited | 94/2, 94/4, 93/1, 94/5
Lord Rayleigh's Farms Limited | 105/1, 105/2, 105/4, 106/1, 106/2, 106/3, 107/1, 107/3, 107/4, 107/5, 107/6, 108/1, 108/2, 108/5, 108/6, 108/8, 109/1, 109/2, 109/2a, 110/1, 110/2, 110/3, 110/4, 110/5, 110/6, 110/7, 111/2, 111/3, 111/4, 111/5, 111/8, 112/1, 112/2, 112/3, 112/4, 112/5, 113/2, 113/3, 113/4, 113/5, 113/6, 113/7, 113/7a, 114/1, 114/3, 114/4, 115/19
Louise Suzanne Humphreys | 101/1, 101/2, 102/1, 102/3, 102/4, 102/7, 103/3, 103/5, 103/6, 103/8, 103/14, 102/14, 102/15, 103/16
Lynda Margaret Latchford | 22/5, 22/6
Malcolm Keith Mckenzie | 145/9, 145/11
The Executor of Margaret Cleary | 148/28
Mark Anthony Lindsell | 31/3, 31/10, 32/1, 32/3, 32/4, 32/6, 32/7, 32/9, 32/10, 32/11
Mark Anthony Sinfield | 149/10, 149/11, 150/1
Mark Cannon | 30/2, 30/3
Mark Neller | 148/60, 148/61, 149/5
Mark Treanor Thomasin-Foster | 132/4, 132/6, 132/7
Martin Grant (Holdings) Limited | 148/57, 148/60, 148/61, 149/3, 149/5
Martin Julian Gilbert | 72/2, 72/4
Mary Christine Earey | 101/1, 101/2, 101/3, 102/1, 102/4, 102/2, 102/14, 102/15
Mary Christine Kemp | 107/2, 108/4
Mary June Mortlock | 42/10, 42/11, 42/12, 42/13, 43/1, 43/2, 43/3, 43/4, 44/1, 44/2
Mary Roberta Wright | 83/2, 83/3, 83/5, 83/14, 83/15
Mary Teresa Kendal | 101/4
Mary-Anne Louise Barron | 77/4, 78/1, 78/4
Matthew Benjamin Blackwell | 68/8, 69/1
Matthew Philip Pearson | 64/3, 64/4, 65/1, 65/12, 65/14, 65/15, 66/2, 67/2, 67/3
Maureen Joyce Edwards | 19/9, 20/2, 20/3, 21/6, 21/7, 22/2, 22/3, 22/4, 22/5, 22/6, 22/8, 23/1, 21/6a
Maureen Sonia Carter | 148/23, 148/26, 148/27, 148/28, 148/29, 148/31, 148/32, 148/33, 148/41
Mavis June Vivian | 74/1, 75/1
Maxine Eva Fox | 2026-05-19
Melissa Elizabeth Robinson | 32/12, 32/13
Northern Trust Land Limited | 128/1, 128/4, 129/2, 129/8
Michael Anthony Hope | 65/12, 65/14, 65/15, 66/2, 67/2, 67/3, 67/4
Michael David Harradine | 25/6, 25/7, 26/1, 26/2, 26/4, 27/1, 27/4, 26/1a
Michael George Hutley | 145/12, 146/6, 146/13, 146/16, 146/31
Michael George Watson | 1/1, 1/2, 1/5, 1/8, 1/9, 2/1, 2/2, 2/2a, 2/3, 3/1
Michael Gordon Lindsell | 29/5, 30/7, 30/8, 30/10, 30/11, 30/13
Michael Ivan Andrew Goodbody | 60/6, 60/8, 60/10, 60/11
Michael James Hodge | 132/8, 133/1, 133/5, 134/4, 134/5, 134/9, 134/11
Michael John Graham | 147/12
Michael John Sayer | 103/10, 103/11, 104/2, 105/5, 105/6, 104/4, 104/5
Michael Peter Foy | 101/9, 101/11
Michael Robert John Staines | 89/1, 89/5, 89/12, 90/1, 90/2, 91/4, 91/5, 91/6, 92/1, 92/2, 92/4, 92/6, 93/3, 93/6, 89/3, 89/6, 89/7, 89/8
Michael Robert Moser | 101/10
Miles William Roberts | 72/2, 72/4, 73/4, 74/3
Miriam Graves | 16/3, 16/5, 16/6, 16/7, 16/8, 16/9, 17/1, 17/2, 17/3, 17/5, 17/7, 17/8, 17/9, 18/1, 18/4, 18/5, 18/7, 18/10, 18/2
Moira Jane Bull | 83/2, 83/5, 83/13
Monica Jane Wilkinson | 132/4, 132/6, 132/7
Mortlock Brothers (Toppesfield) Limited | 42/10, 42/11, 42/12, 42/13, 43/1, 43/2, 43/3, 43/4, 44/1, 44/2, 44/10, 44/11, 45/1, 45/5
Mountview Estates plc | 119/9
National Grid Electricity Transmission plc | 70/3, 1/1, 1/2, 1/3, 1/4, 1/5, 1/6, 1/7, 1/8, 1/9, 2/2, 2/2a, 2/3, 3/1, 3/2, 3/3, 4/4, 4/5, 4/6, 5/1, 5/2, 5/4, 5/7, 6/1, 6/2, 7/1, 7/3, 7/4, 7/5, 7/6, 7/7, 7/8, 7/9, 8/2, 8/3, 8/4, 8/5, 8/6, 8/7, 8/9, 8/11, 9/1, 9/2, 9/3, 9/4, 9/5, 10/1, 10/2, 10/3, 10/4, 10/5, 10/6, 10/8, 10/9, 10/10, 10/11, 10/12, 10/13, 10/14, 11/1, 11/2, 11/3, 11/3a, 11/4, 11/5, 11/6, 11/7, 11/8, 11/9, 11/10, 11/12, 12/1, 12/2, 12/3, 12/5, 12/6, 12/7, 13/1, 13/3, 13/4, 13/5, 13/6, 14/2, 14/2b, 15/3, 16/2, 16/3, 16/4, 16/5, 16/8, 17/3, 17/4, 17/8, 17/10, 18/2, 18/3, 18/4, 18/6, 18/9, 18/12, 18/16, 19/1, 19/4, 19/7, 19/8, 19/9, 19/10, 19/11, 20/2, 20/3, 21/1, 21/3, 21/5, 21/6, 21/7, 21/9, 22/1, 22/2, 22/3, 22/4, 22/5, 22/6, 22/8, 23/1, 23/3, 23/4, 23/6, 23/7, 23/9, 23/11, 23/12, 23/13, 24/1, 25/1, 25/3, 25/4, 25/5, 25/6, 26/2, 26/3, 26/4, 27/1, 27/3, 27/6, 27/7, 27/7a, 28/3, 28/4, 28/5, 29/1, 29/2, 29/3, 29/4, 29/5, 30/1, 30/2, 30/3, 30/4, 30/7, 30/10, 30/11, 30/12, 30/14, 31/2, 31/3, 31/4, 31/5, 31/7, 31/8, 31/9, 31/10, 31/11, 32/1, 32/2, 32/3, 32/4, 32/5, 32/6, 32/7, 33/1, 33/2, 33/3, 33/4, 33/5, 33/6, 33/8, 33/9, 33/10, 33/11, 33/12, 34/1, 34/2, 34/3, 34/4, 34/5, 34/6, 35/2, 35/3, 35/5, 36/1, 36/2, 36/7, 37/1, 37/2, 37/4, 37/8, 37/9, 37/10, 38/2, 38/3, 38/4, 38/8, 38/10, 38/12, 38/13, 38/14, 39/1, 39/2, 39/3, 39/4, 39/5, 39/8, 39/9, 39/10, 39/11, 39/12, 39/13, 39/14, 40/1, 40/2, 41/1, 41/2, 41/3, 41/5, 42/1, 42/4, 42/5, 42/6, 42/7, 42/9, 42/10, 42/11, 42/12, 42/13, 43/1, 43/2, 43/3, 44/1, 44/2, 44/4, 44/5, 44/6, 44/7, 44/8, 44/9, 44/10, 44/11, 45/1, 45/2, 45/3, 45/4, 45/5, 45/6, 45/7, 46/1, 46/4, 46/5, 46/6, 46/7, 46/8, 46/9, 47/1, 47/2, 47/3, 47/4, 48/4, 49/1, 49/2, 49/3, 49/4, 49/6, 49/7, 50/1, 50/2, 50/4, 50/8, 50/9, 50/10, 50/11, 50/12, 50/13, 50/15, 51/1, 51/2, 51/3, 51/4, 51/5, 51/6, 51/7, 51/8, 51/9, 51/10, 51/11, 51/13, 52/1, 52/2, 52/3, 52/4, 52/5, 52/7, 52/7a, 52/7b, 52/8, 52/9, 52/10, 52/11, 53/1, 53/2, 53/3, 53/4, 53/5, 53/6, 53/7, 53/8, 54/1, 54/3, 55/1, 55/2, 55/3, 55/4, 55/5, 55/6, 55/7, 55/8, 55/9, 55/10, 55/11, 56/1, 56/2, 56/3, 56/4, 56/5, 56/6, 57/1, 57/2, 57/3, 57/4, 57/5, 58/1, 58/2, 58/3, 58/4, 58/5, 58/6, 58/8, 58/9, 58/10, 58/11, 58/12, 59/1, 59/2, 59/3, 59/6, 59/7, 59/9, 59/10, 60/2, 60/4, 60/7, 60/8, 60/9, 60/10, 60/11, 60/12, 60/14, 61/1, 61/2, 61/3, 61/5, 61/6, 61/7, 61/8, 62/1, 62/2, 62/3, 63/1, 63/2, 63/3, 63/4, 63/5, 63/6, 63/8, 63/9, 63/11, 63/12, 63/15, 63/16, 64/1, 64/3, 64/4, 65/1, 65/2, 65/13, 65/15, 66/2, 67/1, 67/3, 67/4, 67/5, 67/6, 67/7, 67/8, 67/9, 67/10, 67/11, 67/12, 67/14, 68/2, 68/3, 68/4, 68/5, 68/6, 68/7, 68/8, 69/1, 69/2, 69/3, 70/1, 70/2, 70/4, 70/5, 70/6, 70/7, 70/8, 70/9, 71/1, 71/2, 71/3, 71/4, 71/5, 71/6, 71/7, 71/8, 71/9, 71/10, 71/11, 71/12, 71/13, 71/15, 72/1, 72/2, 72/3, 72/4, 72/5, 73/1, 73/2, 73/3, 73/4, 74/1, 74/2, 74/3, 74/4, 75/1, 75/2, 75/3, 75/4, 75/5, 75/6, 75/7, 75/8, 75/9, 76/2, 76/3, 76/4, 76/5, 76/6, 76/7, 76/8, 77/2, 77/3, 77/4, 78/1, 78/2, 78/3, 78/5, 79/2, 79/4, 79/5, 79/6, 79/7, 79/8, 79/9, 80/2, 80/3, 80/4, 80/5, 80/6, 80/7, 80/8, 81/1, 81/2, 81/3, 81/4, 81/6, 81/7, 81/9, 81/10, 81/12, 82/1, 82/2, 82/3, 82/4, 82/5, 82/6, 82/7, 82/8, 83/4, 83/6, 83/7, 83/8, 83/9, 83/10, 83/11, 83/12, 83/13, 83/14, 83/15, 83/17, 83/18, 83/19, 84/1, 84/2, 84/5, 84/7, 84/8, 84/12, 84/14, 84/15, 84/17, 84/18, 84/19, 84/21, 84/23, 84/24, 84/24a, 84/25, 84/26, 85/2, 85/3, 85/6, 85/8, 86/1, 86/2, 87/2, 88/1, 88/2, 88/3, 89/1, 89/5, 89/12, 90/1, 90/2, 91/1, 91/2, 91/4, 91/5, 91/6, 92/1, 92/2, 92/3, 92/4, 92/5, 92/6, 93/1, 93/2, 93/3, 93/4, 93/5, 93/6, 93/7, 93/8, 94/1, 94/2, 94/4, 94/5, 94/6, 94/7, 94/8, 95/1, 95/2, 95/3, 95/5, 95/6, 95/7, 95/8, 96/1, 96/2, 96/3, 96/4, 96/5, 96/6, 96/7, 96/8, 96/9, 96/10, 96/11, 97/1, 97/2, 97/3, 97/5, 97/6, 97/7, 98/1, 98/2, 98/3, 98/4, 98/5, 98/6, 98/10, 98/13, 99/3, 99/4, 99/5, 99/6, 99/8, 99/9, 99/11, 99/12, 99/14, 99/15, 100/1, 100/4, 100/5, 101/1, 101/2, 101/3, 101/4, 101/5, 101/6, 101/7, 101/8, 101/9, 101/10, 101/13, 101/17, 102/1, 102/2, 102/4, 102/7, 102/8, 103/10, 103/11, 103/12, 103/13, 103/14, 104/2, 105/1, 105/2, 105/3, 105/4, 105/5, 105/6, 106/1, 106/2, 106/3, 107/1, 107/2, 107/3, 107/4, 107/6, 108/1, 108/3, 108/4, 108/5, 108/6, 108/8, 109/1, 109/2, 109/2a, 110/1, 110/2, 110/3, 110/4, 110/5, 110/6, 110/7, 111/2, 111/3, 111/4, 111/5, 111/6, 111/7, 111/8, 112/1, 112/2, 112/3, 112/4, 112/5, 113/2, 113/3, 113/4, 113/5, 113/6, 113/7, 113/7a, 114/1, 114/2, 114/3, 114/4, 115/1, 115/2, 115/4, 115/5, 115/6, 115/7, 115/8, 115/9, 115/10, 115/11, 115/12, 115/13, 115/14, 115/15, 115/16, 115/17, 115/18, 115/19, 116/1, 116/2, 116/3, 117/1, 117/2, 117/3, 117/4, 117/5, 117/6, 117/7, 117/8, 117/9, 117/10, 117/11, 117/12, 117/13, 117/14, 117/15, 117/16, 118/1, 118/4, 118/6, 119/1, 119/2, 119/3, 119/4, 119/5, 119/6, 119/7, 119/8, 119/9, 119/10, 119/13, 119/14, 120/1, 121/1, 121/2, 121/3, 121/4, 121/5, 122/1, 123/1, 123/2, 123/3, 123/4, 123/5, 123/6, 124/1, 125/1, 125/2, 125/3, 125/4, 125/5, 125/6, 125/7, 125/8, 125/9, 125/10, 126/1, 126/2, 126/3, 127/1, 127/2, 127/3, 127/4, 128/1, 128/2, 128/3, 128/4, 128/5, 128/6, 128/7, 128/8, 129/1, 129/2, 129/3, 129/4, 129/5, 129/6, 129/7, 129/8, 130/1, 131/2, 131/3, 131/4, 131/5, 131/6, 131/7, 131/9, 132/3, 132/4, 132/5, 132/6, 132/7, 132/8, 132/10, 132/11, 132/12, 132/13, 133/1, 133/2, 133/3, 133/4, 133/5, 133/6, 133/7, 134/1, 134/2, 134/3, 134/4, 134/5, 134/6, 134/7, 134/8, 134/9, 134/11, 135/1, 135/2, 135/3, 135/4, 135/5, 135/6, 135/7, 135/8, 136/4, 136/5, 136/6, 136/7, 136/8, 136/9, 137/1, 137/2, 137/3, 137/4, 137/5, 137/6, 138/1, 138/2, 138/3, 138/4, 138/5, 138/6, 138/7, 138/8, 138/9, 138/10, 138/11, 138/12, 139/1, 139/2, 139/3, 139/4, 139/5, 140/1, 140/2, 140/3, 141/1, 141/2, 141/4, 141/5, 141/6, 141/7, 141/8, 141/11, 141/13, 142/1, 142/2, 142/3, 142/4, 142/5, 142/6, 143/1, 143/2, 143/3, 143/4, 143/9, 143/11, 143/12, 143/14, 144/1, 144/2, 144/3, 144/4, 144/5, 145/3, 145/7, 145/9, 145/10, 145/11, 145/12, 146/1, 146/2, 146/3, 146/4, 146/5, 146/6, 146/7, 146/8, 146/9, 146/10, 146/11, 146/18, 146/21, 146/22, 146/23, 146/24, 146/25, 146/26, 146/27, 146/28, 146/32, 147/5, 147/6, 147/7, 147/8, 147/9, 147/10, 147/12, 147/13, 147/14, 147/15, 147/16, 147/17, 147/18, 147/19, 147/20, 148/1, 148/10, 148/11, 148/12, 148/15, 148/16, 148/17, 148/18, 148/19, 148/24, 148/26, 148/29, 148/31, 148/37, 148/38, 148/39, 148/41, 148/43, 148/44, 148/46, 148/48, 148/49, 148/50, 148/51, 148/52, 148/54, 148/55, 148/56, 148/57, 148/60, 148/61, 149/2, 149/3, 149/4, 149/5, 149/6, 149/7, 149/8, 149/9, 149/10, 149/11, 150/1, 150/2, 150/3, 150/4, 150/6, 150/7, 150/8, 150/10, 151/1, 151/4, 151/5, 151/6, 151/7, 151/8, 151/9, 151/10, 151/12, 151/13, 152/2, 152/3, 152/4, 152/5, 152/6, 152/8, 21/6a, 26/1a, 28/5a, 72/8, 32/8, 32/9, 32/10, 32/11, 32/12, 32/13, 32/14, 32/15, 32/16, 32/17, 32/18, 85/1, 85/10, 85/11, 85/12, 85/14, 85/15, 85/18, 86/3, 86/4, 87/3, 88/4, 89/2, 89/3, 89/4, 89/6, 89/7, 89/8, 89/9, 89/11, 89/14, 89/15, 102/9, 102/10, 102/11, 102/12, 102/13, 102/14, 102/15, 103/15, 103/16, 103/17, 103/18, 104/5, 104/6, 130/2, 130/3, 130/4, 130/5, 130/6, 130/7, 130/8, 130/11, 130/12, 141/9, 141/10, 143/13
National Highways Limited | 10/3, 10/4, 117/4, 119/3, 119/5, 120/2, 127/2, 128/5, 132/1, 132/2, 132/5, 132/6, 120/3, 120/4
Neil Cleary | 148/28
Neil Peter Gaught | 25/6, 25/7, 26/1, 26/2, 26/4, 27/1, 27/4, 26/1a
New Street Inv Co Limited | 2026-03-21
Nicholas James Gray Robinson | 32/12, 32/13
Nicholas John Cousins | 98/1, 98/3, 99/1, 99/2, 99/6, 99/7, 99/7a, 99/10, 99/13, 99/15, 100/1, 100/2, 100/3, 100/7
Nicholas John Karmy | 130/3
Nicholas Owen Thomas Temple | 67/4, 67/6, 67/7, 67/11, 68/4, 68/5, 67/15, 67/16
Nicholas Stephen Debnam | 38/12, 38/14, 39/1
Nicola Christine Dellow | 2026-08-23
Nicola Jane Heath | 102/10, 103/12, 103/15, 103/17, 103/18, 104/6
Nigel Alfred Barnes | 115/2, 115/7
Northumbrian Water Limited | 139/3, 140/1
Oaks Croft Limited | 3/3, 3/4, 4/2, 4/3, 4/4, 5/1, 6/2, 6/3, 7/1
Oliver Harold Wass | 83/7, 84/18, 84/19, 84/21, 84/23, 84/24, 84/24a
Pamela Margaret Wright | 67/5, 67/9, 67/12
Patrick James Thirkell Cooper | 65/5
Paul Brown | 148/60, 148/61, 149/5
Paul Edward Hardisty | 148/19, 148/31, 148/41, 148/49
Paul Frederic Bentley | 115/10, 115/13
Paul George Deakin | 93/1, 93/2, 93/5, 93/7, 94/2, 94/4, 94/5, 94/8
Paul John Shadbolt | 75/8, 76/2, 76/3, 76/5
Paul Jonathan Fosh | 93/1, 93/2, 93/5, 93/7, 94/2, 94/4, 94/5, 94/8
Pauline Kay Davies | 146/18, 146/24, 146/30, 146/31, 147/5
Pegasi Limited | 7/5, 7/7, 7/9, 8/1, 8/2, 8/3, 8/5, 9/3, 10/1
Penelope Ann Fairs | 79/2, 79/4, 79/7, 79/8, 79/9, 80/2, 80/5, 80/6
Persimmon Homes Limited | 98/2, 98/4, 98/5, 98/6, 99/14, 99/16, 99/17, 101/17
Peter Brian Silver Carter | 148/23, 148/27, 148/28, 148/32, 148/33, 148/37
Peter David Lindsell | 31/3, 31/10, 32/1, 32/3, 32/4, 32/6, 32/7, 32/9, 32/10, 32/11
Peter Davies | 146/18, 146/24, 146/30, 146/31, 147/5
Peter Edmund Arthur Latchford | 22/5, 22/6, 31/3, 31/10, 32/1, 32/3, 32/4, 32/6, 32/10
Peter Edmund Gross Wheeler | 63/7, 63/8, 63/9, 63/10, 63/11, 63/16, 64/2, 63/13
Peter John Fairs | 79/2, 79/4, 79/7, 79/8, 79/9, 80/2, 80/5, 80/6
Peter John French | 100/4, 100/5, 101/13, 101/17, 101/18
Peter John Nott | 71/1, 71/8, 71/13
Peter Jonathan Graves | 16/3, 16/5, 16/6, 16/7, 16/8, 16/9, 17/1, 17/2, 17/3, 17/5, 17/7, 17/8, 17/9, 18/1, 18/4, 18/5, 18/7, 18/10, 18/2
Peter Mads Hogsbjerg | 72/3, 73/2
Peter Mcmillan | 44/6, 45/2
Peter Scantlebury Philp | 51/7, 51/9, 51/10, 51/11, 52/1, 52/3, 52/4, 52/5, 52/7, 52/7a, 52/7b, 52/8, 52/9, 52/10, 52/11, 53/1
Philip George Stone | 117/5, 119/8, 119/10
Philip James Hutley | 103/10, 103/11, 104/2, 105/5, 105/6, 104/3, 104/3a, 104/4, 104/5
Philip John Parish | 85/17
Philip William Henry Speakman | 115/5, 115/8, 128/1, 128/2, 128/4, 129/1, 129/2, 129/3, 129/5, 129/6, 129/8, 131/3, 131/4, 130/7, 130/8, 130/11, 130/12, 130/13
Philp Farm Contracts Limited | 53/7, 54/1, 55/1, 55/5, 55/11, 56/1, 56/2, 56/4, 56/5, 56/6, 57/1
Pivoted Power LlP | 99/3, 99/4, 99/8
Principality Properties Limited (Incorporated In Jersey) | 76/4, 76/7, 77/2, 77/3
The Executor of Reginald John Foster Smith | 60/13
Richard Alan French | 100/4, 100/5, 101/13, 101/17, 101/18
Richard Arthur Ramsey | 83/2, 83/5, 83/6, 83/8, 83/10, 83/11, 83/13, 83/14, 83/15, 83/16, 84/26
The Executor of Richard David Fordham | 68/2, 68/7, 68/10, 75/8, 76/2, 76/3
Richard George Boland | 146/18, 146/24, 146/26, 146/27, 146/30, 146/31, 147/5, 150/9, 150/6, 150/7, 150/8, 151/1, 151/6, 151/7, 151/8, 151/9, 151/10, 151/11, 152/2, 152/3, 152/4
Richard Hermon | 83/3, 83/9, 83/10, 83/11, 83/12
Richard Holmsted Speakman | 115/1, 115/5, 115/8, 116/1, 116/2, 116/3, 117/1, 117/2, 117/6, 117/7, 117/8, 117/11, 117/12, 117/13, 117/14, 117/15, 117/16, 118/4, 118/6, 128/1, 128/2, 128/4, 129/1, 129/2, 129/3, 129/5, 129/6, 129/8, 131/3, 131/4, 130/7, 130/8, 130/11, 130/12, 130/13
Richard Peter Hingston | 19/9, 20/2, 20/3, 21/6, 21/7, 22/2, 22/3, 22/4, 22/5, 22/6, 21/6a
Richard Robert Browning | 80/4, 80/8, 81/5, 81/12
Richard Rutherford Maynard | 148/20, 148/25, 148/29, 148/46
Rita Cleary | 148/28
RJL Properties Limited | 148/15, 148/16, 148/52, 148/55
Robert Andrew Barr | 133/3, 133/4, 133/7
Robert Bridge | 115/2, 115/7
Robert Charles Gerard Foster | 115/10, 115/15
Robert Draper Caton | 23/7, 23/9, 23/11, 23/12, 23/13, 24/1, 24/2, 24/3, 25/1, 25/2, 25/3, 25/4, 25/5
Robert Edward Jones | 30/12, 30/13
Robert Howard Wilson | 68/2, 68/6
Robert James Hodge | 132/8, 133/1, 133/5, 134/4, 134/5, 134/9, 134/11
Robert John Stacey | 136/6, 136/7, 137/1
Robert Michael Prestney | 81/1, 81/2, 81/3, 82/4, 82/7, 82/8
Robert Mortlock | 42/10, 42/11, 42/12, 42/13, 43/1, 43/2, 43/3, 43/4, 44/1, 44/2, 48/4, 49/2, 49/3, 49/4, 48/1, 48/2, 48/3
Robert Peter Bolton | 132/6, 132/7, 132/9
Robert Thomas Speakman | 94/1, 95/1, 95/2, 95/3, 95/7, 95/8, 96/10, 96/11
Robina Sandeman Gray | 32/14
The Executor of Ronald Edward Allworthy | 10/5, 10/6
Rosemarie Samantha Mattin | 115/14, 115/18
Rosemary Lawrie | 2026-07-19
Roy Howard Hart | 141/4, 141/5, 141/7, 141/8, 141/11, 141/13, 141/15, 141/17, 142/1, 142/5, 142/6, 141/22, 143/13
Roy John Brett | 96/5
The Executor of Roy Leslie Carter | 148/23, 148/27, 148/31, 148/33, 148/41
Roy Philip Chapman | 28/7, 29/3, 30/1
Russel John Fone | 148/12, 148/13, 148/53
Ruth Mavis Tatam | 83/2, 83/3, 83/5, 83/14, 83/15
S & M Contractors Limited | 50/12, 50/15, 51/1, 51/4
S J R Farming Limited | 143/14, 143/15, 144/1, 144/2, 144/3, 144/5, 149/10, 149/11, 150/1, 150/2, 150/3, 150/4, 150/5, 150/6, 150/7, 150/8, 150/10, 151/1, 151/4, 151/5, 151/6, 151/7, 151/8, 151/9, 151/10, 151/11, 151/13, 152/2, 152/3, 152/4, 152/5, 152/6, 150/9
Sally Louise Staines | 89/1, 89/5, 89/12, 90/1, 90/2, 91/4, 91/5, 91/6, 92/1, 92/2, 92/4, 92/6, 93/3, 93/6, 89/3, 89/6, 89/7, 89/8
Sally-Ann Maseyk | 22/5, 22/6
Samantha Jayne Graham | 147/12
Samuel John Blackwell | 84/14, 84/15, 85/3, 85/5, 85/6, 85/8, 85/10, 85/11, 85/14, 85/15, 85/16, 87/1, 85/1
Sandon Parish Council | 130/3, 130/4
Sandra Elizabeth Boland | 146/18, 146/24, 146/26, 146/27, 146/30, 146/31, 147/5
Sarah Elizabeth Coleman | 80/1, 81/3, 81/4, 81/6, 81/7, 81/9, 81/11
Sarah Jane Jones | 30/12, 30/13
Sarah Swanson | 49/7, 50/1, 50/2, 50/4, 50/8
Sean Peter Conway | 49/7, 50/1, 50/2, 50/4, 50/5, 50/8
Sharron Louise Nichols | 73/1
The Executor of Sheila Kathleen Cannon | 30/2, 30/3
The Executor of Silva Lesley Carter | 148/27
Simon Francis Latham | 23/2, 23/3, 23/4, 23/5
Sir Timothy Edward Ruggles-Brise | 33/10, 33/11, 33/12, 34/1, 34/2, 34/4, 34/5, 34/6, 35/2, 35/3, 35/4, 35/5, 36/1, 36/3, 36/6, 36/6a, 36/7, 36/8, 37/1, 37/2, 37/3, 37/4, 37/6, 38/1
Sonya Mitchell | 148/18, 148/37, 148/41, 148/51
Sophia Annabel Moser | 101/10
Stacey Marie Pearson | 64/3, 64/4, 65/1, 65/12, 65/14, 65/15, 66/2, 67/2, 67/3
Stella Denise Bridges | 141/19, 141/20, 141/21
Stephen James Kendal | 101/4
Stephen John Bolton | 119/2, 119/4, 119/6, 119/12, 119/13, 119/14, 120/1, 120/2, 121/1, 121/2, 121/3, 121/4, 121/5, 122/1, 123/1, 123/2, 123/3, 123/4, 123/5, 123/6, 123/7, 125/2, 125/4, 125/5, 125/6, 120/4
Stephen John Taylor | 148/36, 148/43
Stephen Richard Fox | 2026-05-19
Places for People Homes Limited | 119/2, 119/4, 119/9, 119/10, 119/13, 119/14, 120/1, 121/3, 121/4, 121/5, 122/1, 123/1, 123/2, 123/3, 123/4, 123/5, 123/6, 125/2, 125/4, 117/5, 119/8
Steven Frederick Fagioli | 146/18, 146/30, 146/31, 147/5
Stuart Hermon | 83/2, 83/5
Stuart Walter Brock | 20/4, 20/7, 21/8, 21/9, 22/1, 22/3, 22/4, 22/5, 22/6
Susan Elizabeth Wheeler | 63/7, 63/8, 63/9, 63/10, 63/11, 63/16, 64/2, 63/13
Susan Emma Morland | 31/3, 31/10, 32/1, 32/3, 32/4, 32/6, 32/10
Susan James Properties Limited | 58/2
Susan Rosalinde Blackie | 46/4, 46/6, 46/7, 46/8, 46/9, 47/1, 47/2, 47/3, 47/4, 49/1, 49/6
Susannah Elizabeth Goodbody | 60/6, 60/8, 60/10, 60/11
Suzanne Baines | 12/3, 12/4, 12/5, 12/6, 12/7, 12/8, 12/9, 13/1, 13/3
Suzanne Janet Nott | 57/2, 57/3, 57/4, 57/5, 58/1, 58/2, 58/3, 58/6, 58/8, 58/9, 58/11, 58/12, 59/1, 59/6, 59/9, 60/4, 60/9, 60/12, 60/14, 61/1
Sylvia Mary Allworthy | 10/5, 10/6
Tara Elisa Marian Sherlock | 101/9, 101/11
Telefonica UK Limited | 2026-10-10
Telmara Farm Limited | 17/10, 18/3, 18/6
Teresa Barbara Fone | 148/12, 148/13, 148/53
Teresa Jane Peasgood | 2026-10-19
Tesco Stores Limited | 142/2, 142/3, 143/2, 143/4
The Chelmsford Diocesan Board Of Finance | 8/11, 9/1, 25/6, 25/7, 26/1, 26/2, 26/4, 27/1, 27/4, 33/5, 33/6, 57/2, 60/6, 60/8, 60/11, 131/4, 131/6, 131/8, 147/3, 26/1a, 130/3, 130/4, 130/5
The Governing Body Of Beauchamps | 147/20, 148/1
The Honourable John Frederick Strutt | 107/1, 107/3, 107/4, 107/5, 108/1, 108/2, 108/5, 108/6, 108/8, 109/1, 109/2, 109/2a, 110/1, 110/2, 110/3, 110/4, 110/5, 110/6, 110/7, 111/2, 111/3, 111/4, 111/5, 111/8, 112/1, 112/2, 112/3, 112/4, 112/5, 113/2, 113/3, 113/4, 113/5, 113/6, 113/7, 113/7a, 114/1, 114/3, 114/4, 115/19
The Notleys Golf Club Limited | 101/1, 101/2, 102/1, 102/4, 102/2, 102/14, 102/15
The Official Custodian For Charities on behalf of the trustees of the Marks Hall Estate | 84/14, 84/15, 85/1, 85/2, 85/3, 85/4, 85/5, 85/6, 85/8, 86/1, 86/2, 86/3, 87/1, 87/2, 88/1, 88/2, 88/3, 85/10, 85/11, 85/14, 85/15, 85/16, 86/4, 87/3, 88/4, 89/14, 89/15
The Official Custodian For Charities on behalf of The Town Estate (Estate Trustees) | 22/5, 22/6, 22/8, 23/1, 23/3
The Scout Association Trust Corporation | 63/9, 63/11, 63/12, 63/14, 63/16, 64/2
The Trustees Of The Rotary Club Of Wickford Trust Fund | 148/57, 148/60, 148/61, 149/3, 149/5
The Trustees Of Wickford Town Football Club | 147/18, 147/19, 147/20, 148/1, 148/57, 148/60, 148/61, 149/3, 149/5
Thomas Darwin | 119/9
Thomas James Mortlock | 42/10, 42/11, 42/12, 42/13, 43/1, 43/2, 43/3, 43/4, 44/1, 44/2, 48/1, 48/2, 48/3, 48/4, 49/2, 49/3, 49/4, 49/5
Thomas William Speakman | 94/1, 95/1, 95/2, 95/3, 95/7, 95/8, 96/10, 96/11
Timothy George Buck | 78/2, 78/5
Timothy Stewart Smith | 13/2, 13/4
Tina Louise Magness | 19/3, 19/4, 19/13, 21/4, 21/5
Tommy Piper Lowe | 146/4, 146/5, 146/7, 146/8, 146/11, 146/18, 146/29, 146/30, 147/5
Tony Damion Hicks | 148/23, 148/33
Trisha Helen Lovricic | 45/4
Twinstead Hall Farms Limited | 65/3, 65/6, 65/7, 65/8, 65/9, 65/10, 65/11
Valerie Susan Timmons | 16/3, 16/4, 16/5, 16/6, 16/7, 16/8, 16/9, 17/1, 17/2, 17/3, 17/4, 17/5, 17/6, 17/7, 17/8, 17/9, 18/1, 18/2
Vernon Charles Nott | 61/2, 61/3, 61/4, 61/5, 61/6, 61/7, 61/8, 62/1, 62/3, 63/1, 63/2, 63/4, 63/5, 63/6, 63/9, 63/11, 63/15, 63/16, 64/1, 64/2
Vicki Ann Kohler | 130/3
Victoria Joy Kirby | 146/18, 146/30, 146/31, 147/5
Virginia Ann Hill | 74/2, 74/4, 74/5, 75/2
The Executor of Walter Buckley | 101/2, 101/3, 101/6, 102/15
Wilcon Homes Anglia Limited | 147/2
William Eric Drake | 68/2, 68/4, 68/7, 68/10, 68/11
William George Pewter | 53/8, 55/3, 55/4, 55/6, 55/7, 55/8
William George Sheen | 133/6, 134/8
William Greer | 58/5, 58/6
William John Brock | 20/4, 21/8, 21/9, 22/1, 22/3, 22/4, 22/5, 22/6
William Mark Ambrose | 148/42
Wren Renewables (Holdings) Limited | 93/1, 93/2, 94/7, 94/8
Accord Mortgages Limited | 55/7, 55/8, 148/36, 148/43
Aviva Equity Release UK Limited | 58/5, 58/6, 85/17
Bank of Scotland plc | 75/8, 76/2, 76/3, 133/6, 134/8, 146/22, 148/35
Barclays Bank UK plc | 65/5
Barclays Security Trustee Limited | 13/2, 13/4, 51/9, 51/10, 51/11, 52/1, 52/3, 52/4, 52/5, 52/7, 52/7a, 52/7b, 52/8, 52/9, 61/2, 61/3, 61/7, 61/8, 63/1, 83/8, 85/2, 85/3, 85/5, 85/6, 85/10, 86/1, 86/2, 86/3, 86/4, 87/1, 87/2, 87/3, 88/1, 88/2, 88/3, 88/4, 143/8, 143/12, 85/1, 85/14, 89/14, 89/15
C. Hoare & CO. | 89/1, 89/5, 89/6, 89/7, 89/8, 89/12, 90/1, 90/2, 91/1, 91/3, 91/4, 91/5, 91/6, 92/1, 92/2, 92/4, 92/5, 92/6, 93/3, 93/6, 89/3
Cambridge & Counties Bank Limited | 58/2
Cambridge Building Society | 101/9
CBRE Loan Services Limited | 98/4, 98/6
Clydesdale Bank plc | 146/21, 148/12, 148/13, 148/39, 148/53
Cumhur Gonul | 145/12, 146/6, 146/13, 146/14, 146/16
Natalie Tuulaa Gonul | 145/12, 146/6, 146/13, 146/14, 146/16
E-Money Capital Ltd | 111/7
Handelsbanken plc | 84/4, 84/9, 84/10, 84/11, 84/12
Holdfirm Limited | 7/5, 7/7, 7/9, 8/2, 8/3, 8/5, 9/3, 10/1
HSBC UK Bank plc | 1/8, 1/9, 2/2, 2/2a, 2/3, 3/1, 76/8, 79/2, 79/4, 79/7, 79/8, 79/9, 80/2, 80/5, 80/6, 93/1, 93/2, 94/7, 94/8, 148/38
Industrial And Commercial Bank Of China Limited London Branch | 99/5
Leeds Building Society | 83/8
Lloyds Bank plc | 4/5, 4/6, 5/2, 5/3, 5/6, 5/7, 6/1, 33/11, 43/4, 44/10, 44/11, 45/1, 45/5, 48/4, 49/3, 49/4, 136/7, 137/1
Lucy Elizabeth Block | 46/8, 46/9, 47/1, 47/2
Nicholas Kenton Wright | 46/8, 46/9, 47/1, 47/2
M&G Trustee Company Limited | 130/13
Marsden Building Society | 2026-10-19
National Westminster Bank plc | 8/6, 8/8, 8/9, 19/9, 20/2, 20/3, 21/6, 21/7, 22/2, 30/12, 54/3, 55/9, 55/10, 64/3, 64/4, 65/1, 84/19, 84/21, 150/2, 150/3, 150/4, 150/6, 150/7, 150/8, 150/10, 151/1, 151/4, 151/6, 151/7, 151/11, 152/2, 152/3, 21/6a, 150/9
Nationwide Building Society | 148/6, 148/8, 148/9, 148/40, 148/42, 148/45
Santander UK plc | 42/9, 148/17, 148/24, 148/48
Simon Rupert Brennan Brown | 115/14, 115/18
Lucinda Kate Brennan Brown | 115/14, 115/18
Tiffany Sue Brennan Brown | 115/14, 115/18
Step One Finance Limited | 42/9
The Agricultural Mortgage Corporation plc | 13/2, 13/4, 54/3, 55/9, 55/10, 65/3, 65/7, 65/8, 80/4, 80/8, 81/5, 81/12, 84/14, 84/15, 85/2, 85/3, 85/5, 85/6, 86/1, 86/2, 86/3, 86/4, 87/1, 87/2, 87/3, 88/1, 88/2, 88/3, 88/4, 132/8, 133/1, 133/5, 134/9, 134/11, 85/1, 85/10, 85/14, 85/15, 85/16, 89/14, 89/15
The Football Foundation | 148/60, 148/61, 149/5
The Mortgage Lender Limited | 148/15, 148/16, 148/52, 148/55
TSB Bank plc | 23/12, 25/1, 25/2
Yorkshire Building Society | 102/8
Unknown 1 | 9/4, 9/5, 10/2, 10/8, 10/9, 10/10, 64/3, 65/1, 67/8, 74/5, 75/6, 76/4, 76/7, 77/2, 77/3, 80/4, 81/5, 83/7, 84/2, 84/3, 84/13, 84/19, 84/21, 84/23, 84/24, 84/24a, 85/9, 87/1, 87/2, 88/1, 88/2, 88/3, 96/7, 96/8, 115/7, 115/15, 117/4, 119/3, 119/12, 146/20, 148/37
Longfield Solar Energy Farm Limited | 105/1, 105/2, 105/4, 106/1, 106/2, 106/3, 107/1, 107/3, 107/4, 107/5, 107/6, 108/1, 108/2, 108/5, 108/6, 108/8, 109/1, 109/2, 109/2a, 110/1, 110/2, 110/3, 110/4, 110/5, 110/6, 110/7, 111/2, 111/3, 111/4, 111/5, 111/8, 112/1, 112/2, 112/3, 112/4, 112/5, 113/2, 113/3, 113/4, 113/5, 113/6, 113/7, 113/7a, 114/1, 114/3, 114/4, 115/19
Ashley Golding | 145/8, 145/13
Ashleigh-Marie Golding | 145/8, 145/13
Andrew Harold Michael Wray | 145/8, 145/13
Justine Brown | 145/8, 145/13
Ryan Daniel Lincoln | 145/8, 145/13
Holly Julie Ailey | 145/8, 145/13
Statera Energy Limited | 150/6, 150/7, 150/8, 151/1, 151/6, 151/7, 151/11, 152/2, 152/3, 150/9
CSE22 Limited | 98/1, 98/3, 99/1, 99/2, 99/3, 99/4, 99/7, 99/7a, 99/8, 99/15, 100/1, 100/2, 100/3, 100/7
Gearston Limited | 119/2, 119/4, 119/13, 119/14, 120/1, 121/3, 121/4, 121/5, 122/1, 123/1, 123/2, 123/3, 123/4, 123/5, 123/6, 125/2, 125/4, 120/4
Bellway Homes Limited | 100/4, 100/5, 101/13, 101/17, 101/18, 117/1, 117/6, 117/15, 118/1, 118/6
Go Traffic Management Limited | 51/3
Conrad Energy (Developments) II Limited | 131/3, 130/8, 130/11
Nightingale Joinery Limited | 85/2, 85/3, 85/5, 85/6, 86/1, 86/2, 87/1, 87/2, 88/1, 88/2, 88/3, 85/1, 85/10, 85/14, 86/3, 86/4, 87/3, 88/4, 89/14, 89/15
Connectix Limited | 85/2, 85/3, 85/5, 85/6, 86/1, 86/2, 87/1, 87/2, 88/1, 88/2, 88/3, 85/1, 85/10, 85/14, 86/3, 86/4, 87/3, 88/4, 89/14, 89/15
B&Q plc | 99/5
Aldi Stores Limited | 99/5
Sandon Brooks Solar Farm Limited | 137/3, 137/5, 137/6, 138/1, 138/4, 138/5, 138/7, 138/8, 138/10, 138/11, 138/12, 139/1, 139/2, 139/4, 139/5, 140/2
Low Carbon Solar Park 6 Limited | 2/2, 2/2a, 2/3, 3/1, 3/3, 3/4, 4/2, 4/3, 4/4, 5/1, 1/8, 1/9
Pelham Power Limited | 2/2, 2/2a, 2/3, 3/1, 1/8, 1/9
Pelham Storage Limited | 1/1, 1/2, 1/3, 1/4
Threadneedle Pensions Limited | 115/1, 116/1, 116/2, 116/3, 117/1, 117/2, 117/6, 117/7, 117/8, 117/11, 117/12, 117/13, 117/14, 117/15, 117/16, 118/1, 118/4, 118/6
Timothy Read | 68/11
This Land Development Limited | 119/2, 119/4, 119/13, 119/14, 120/1, 121/3, 121/4, 121/5, 122/1, 123/1, 123/2, 123/3, 123/4, 123/5, 123/6, 125/2, 125/4
Gladman Developments Limited | 98/8
M Scott Properties Limited | 94/1, 95/1, 95/2, 95/3, 95/7, 95/8, 96/10, 96/11, 100/4, 100/5, 101/13, 101/17, 101/18
James Barr & Sons (Farmers) Limited | 133/3, 133/4, 133/7, 134/1, 134/2, 134/7, 135/1, 135/2, 135/3, 135/4, 135/5, 135/7, 136/4, 136/5, 136/9
Wates Developments Limited | 124/1, 125/1, 125/3, 125/7, 125/8, 125/10, 126/1, 126/2, 126/3, 127/1, 127/3, 127/4, 128/3, 128/6, 128/7, 128/8, 129/7
Peggy Patricia Dixon Smith | 96/1, 96/2, 96/7, 96/8, 96/9, 97/6, 97/7
Simon Dixon Smith | 96/1, 96/2, 96/7, 96/8, 96/9, 97/6, 97/7
PJH Farming Limited | 150/2, 150/3, 150/4, 150/6, 150/7, 150/8, 150/10, 151/1, 151/4, 151/6, 151/7, 151/11, 152/2, 152/3, 150/9
Chelmsford Angling Association | 115/7
Martin Grant Homes Limited | 148/60, 148/61, 149/4, 149/5
Peter David Webster | 150/2, 150/3, 150/4, 150/10, 151/4
James Michael Webster | 150/2, 150/3, 150/4, 150/10, 151/4
Clare Elizabeth Vernon | 150/2, 150/3, 150/4, 150/10, 151/4
John Little | 144/1, 144/3
Richard John Little | 144/1, 144/3
Greystoke CB Limited | 131/2, 131/5, 131/7, 131/9, 132/3, 132/10, 132/11
Paul Edward Spencer | 65/3, 65/7, 65/8
Essex Partnership University NHS Foundation Trust | 144/4, 145/1, 145/3, 145/8, 145/13, 145/14, 145/15, 145/16, 146/12, 146/34
The Secretary of State for Housing, Communities and Local Government | 147/20, 148/1
Bloor Homes Limited | 149/10, 149/11, 150/1, 150/2, 150/3, 150/4, 150/6, 150/7, 150/8, 150/10, 151/1, 151/4, 151/6, 151/7, 151/11, 152/2, 152/3, 150/9
Chelmsford City Council | 117/9, 117/10, 136/7, 137/1, 144/4, 145/1, 145/3, 145/8, 145/13, 145/14, 145/15, 145/16, 146/18, 146/30, 146/34, 147/5, 147/7, 147/9, 147/10
Lightwood Strategic Braintree Limited | 89/1, 89/5, 89/12, 90/1, 90/2, 91/1, 91/3, 91/4, 91/5, 91/6, 92/1, 92/2, 92/4, 92/5, 92/6, 93/3, 93/6, 89/3, 89/6, 89/7, 89/8
Redrow Homes Limited | 128/2, 129/1, 129/3, 129/5, 129/6, 130/7, 130/12
CALA Management Limited | 117/1, 117/6, 117/15, 118/1, 118/6
The Land Restoration Trust | 117/1, 117/6, 117/15, 118/1, 118/6
Rainier Developments Limited | 98/1, 98/3, 99/1, 99/2, 99/7, 99/7a, 99/15, 100/1, 100/2, 100/3, 100/7
Barclays Bank plc | 39/9, 39/10, 39/11, 40/1
Unknown 131 | 84/3, 84/13
Norcros Developments Limited | 99/3, 99/4, 99/5, 99/8
Felicity Ann Hewison | 132/8, 133/1, 133/5, 134/9, 134/11
Ian David Hodge | 132/8, 133/1, 133/5, 134/9, 134/11
Unknown 133 | 84/3, 84/13, 120/2
Unknown 112 | 84/3, 84/13
Gent Fairhead & Co. Limited | 93/1, 93/5, 93/7, 94/5
Stanley John Tatam | 83/2, 83/3, 83/5
Energis Communications Limited | 2/2, 2/2a, 2/3, 3/1, 7/3, 7/4, 8/4, 8/6, 8/9, 8/11, 9/1, 10/14, 11/1, 11/2, 11/3, 11/3a, 11/5, 11/7, 11/9, 11/12, 12/1, 12/2, 12/5, 12/6, 12/7, 13/1, 13/2, 13/3, 13/4, 16/5, 16/6, 16/7, 16/9, 17/2, 19/11, 21/1, 21/3, 22/8, 23/1, 23/2, 23/4, 23/5, 23/7, 23/9, 23/12, 23/13, 24/1, 25/1, 25/2, 25/3, 25/4, 25/5, 33/1, 33/2, 33/5, 33/6, 33/8, 33/9, 37/9, 37/10, 38/2, 38/4, 38/8, 38/10, 38/13, 39/2, 41/5, 42/4, 42/10, 42/11, 42/12, 42/13, 43/1, 43/2, 43/3, 44/1, 44/2, 44/10, 44/11, 45/1, 45/5, 45/7, 45/9, 45/10, 46/1, 46/2, 46/3, 46/8, 46/9, 47/1, 47/2, 53/8, 55/3, 55/4, 55/6, 60/6, 60/8, 60/11, 1/8, 1/9, 32/12, 32/13, 32/16, 32/17, 32/18
Unknown 144 | 84/18
UK Power Networks (Operations) Limited | 2/2, 2/2a, 2/3, 3/1, 115/7, 147/11, 148/2, 148/14, 148/21, 148/30, 148/44, 150/6, 150/7, 150/8, 151/1, 151/6, 151/7, 151/11, 152/2, 152/3, 1/8, 1/9, 150/9
The King's Most Excellent Majesty in Right of His Crown | 99/5, 145/7, 145/10, 146/2, 147/16, 147/18, 147/19, 147/20, 148/1
Howard William Sears | 19/11, 21/1
Karen Joan Sears | 19/11, 21/1
St. Bartholomew's Hospital | 148/2, 148/14, 148/21, 148/30, 148/44
Simon Kivotos | 89/1, 89/5, 89/12, 90/1, 90/2, 91/4, 91/5, 91/6, 92/1, 92/2, 92/4, 92/6, 93/3, 93/6, 89/3, 89/6, 89/7, 89/8
Nicole Kivotos | 89/1, 89/5, 89/12, 90/1, 90/2, 91/4, 91/5, 91/6, 92/1, 92/2, 92/4, 92/6, 93/3, 93/6, 89/3, 89/6, 89/7, 89/8
Unknown 142 | 69/2, 70/1, 70/4, 71/9, 71/11
Unknown 158 | 98/8
Unknown 140 | 114/2, 115/12
Unknown 169 | 121/1
Unknown 180 | 25/6, 26/2, 26/4, 27/1, 27/4, 26/1a
The Incumbent of the Benefice of Thaxted (Vacant) | 25/6, 25/7, 26/1, 26/2, 26/4, 27/1, 27/4, 26/1a
Network Rail Infrastructure Limited | 10/13, 101/1, 101/2, 101/3, 101/8, 101/9, 101/12, 101/16, 102/1, 102/4, 117/1, 117/3, 117/6, 117/15, 118/1, 118/6, 148/54, 148/56, 102/14, 102/15
Unknown 146 | 83/9, 83/12, 83/13
Andrew William Thornton | 80/6
Jacqueline Mary Thornton | 80/6
Unknown 202 | 117/9, 117/10
Unknown 213 | 117/9, 117/10
Unknown 224 | 70/7
Unknown 2 | 84/1, 84/5, 84/7, 84/8
Unknown 13 | 70/2, 70/7, 71/6
Reginald Duke Hill | 80/1, 81/7, 81/9
Christopher Hugo David Bawtree | 76/4, 76/7, 77/2, 77/3
Philippa Jane Blair Bawtree | 76/4, 76/7, 77/2, 77/3
Nesa Tech Ltd | 84/1, 84/5, 84/7, 84/8
Bruce Philip Bartell | 105/1, 105/2, 105/4, 106/1, 106/2, 106/3, 107/6
Amanda Jane Bartell | 105/1, 105/2, 105/4, 106/1, 106/2, 106/3, 107/6
Nicola Gaye Barrett | 117/5, 119/8
Steven David Clifford Hicks | 117/5, 119/8
Annie O'Donnell | 117/5, 119/8
Crown Castle UK Limited | 64/3, 64/4, 65/1
Sandra Urwin | 22/3, 22/4, 22/5, 22/6
British Gas Limited | 98/2, 98/5, 99/14, 100/4, 100/5, 101/13, 101/17, 101/18, 124/1, 125/1, 125/3, 125/7, 125/8, 125/10, 126/1, 126/2, 126/3, 127/1, 127/3, 127/4, 128/7, 128/8, 134/4, 134/5, 145/12, 146/6, 146/13, 146/16
National Gas Transmission plc | 13/5, 13/6, 14/2a, 15/1, 15/2, 15/3, 15/4, 16/1, 16/2, 57/3, 57/4, 57/5, 58/3, 58/8, 58/9, 58/11, 58/12, 59/1, 76/4, 76/7, 77/2, 77/3
Cable & Wireless UK Limited | 60/6, 60/8, 60/11
The Occupier 1 | 117/5, 119/8
The Occupier 2 | 117/5, 119/8
The Occupier 3 | 117/5, 119/8
Unknown 24 | 7/7, 7/9, 8/2, 8/3, 8/5, 9/3, 10/1
Charles Edmund Maurice Martineau | 9/4, 9/5, 10/2, 10/8, 10/9, 10/10
Susan Gwladys Martineau | 9/4, 9/5, 10/2, 10/8, 10/9, 10/10
Mining Remediation Authority | 117/7, 117/8, 117/12, 117/14, 118/4, 117/2, 117/6, 117/15, 118/6, 115/1, 116/1, 116/2, 116/3, 117/11, 117/13, 117/16
The Occupier 4 | 117/5, 119/8
The Occupier 5 | 117/5, 119/8
The Occupier 6 | 117/5, 119/8
The Occupier 7 | 117/5, 119/8
The Occupier 8 | 117/5, 119/8
The Occupier 9 | 117/5, 119/8
The Occupier 10 | 117/5, 119/8
The Occupier 11 | 117/5, 119/8
The Occupier 12 | 117/5, 119/8
The Occupier 13 | 117/5, 119/8
The Occupier 14 | 117/5, 119/8
The Occupier 15 | 117/5, 119/8
The Occupier 16 | 117/5, 119/8
The Occupier 17 | 117/5, 119/8
The Occupier 18 | 117/5, 119/8
The Occupier 19 | 117/5, 119/8
The Occupier 20 | 117/5, 119/8
Unknown 46 | 115/1, 116/1, 116/2, 116/3, 117/2, 117/7, 117/8, 117/11, 117/12, 117/13, 117/14, 117/16, 118/4
Ministry of Defence | 19/9, 19/11, 20/2, 20/3, 21/1, 21/6, 21/7, 22/2, 21/6a
Unknown 57 | 2026-08-08
Unknown 68 | 49/7, 50/1, 50/2, 50/4, 50/8
Unknown 79 | 115/10
Unknown 90 | 146/4
Unknown 101 | 101/10
Unknown 113 | 99/3, 99/4, 99/8
The Executor of Frederick George Bentley | 113/3, 113/6, 113/7, 113/7a, 114/1, 114/3, 114/4, 115/19
Jean Violet Bentley | 113/3, 113/6, 113/7, 113/7a, 114/1, 114/3, 114/4, 115/19
Unknown 124 | 99/4
Unknown 151 | 119/6, 121/2
Arthur James Sargeant | 96/1, 96/2, 96/9, 97/6, 97/7
Unknown 152 | 99/3, 99/4, 99/8
George Robert Buck | 74/2, 74/4, 75/2, 75/3, 75/4, 75/5, 75/7, 75/9
James Edward Brown | 74/2, 74/4, 75/2, 75/3, 75/4, 75/5, 75/7, 75/9
Unknown 153 | 119/2, 119/4, 119/13, 119/14, 120/1, 121/3, 121/4, 121/5, 122/1, 123/1, 123/2, 123/3, 123/4, 123/5, 123/6, 125/2, 125/4
Redcat Inns Limited | 119/2, 119/4, 119/13, 119/14, 120/1, 121/3, 121/4, 121/5, 122/1, 123/1, 123/2, 123/3, 123/4, 123/5, 123/6, 125/2, 125/4
Unknown 154 | 119/2, 119/4, 119/13, 119/14, 120/1, 121/3, 121/4, 121/5, 122/1, 123/1, 123/2, 123/3, 123/4, 123/5, 123/6, 125/2, 125/4
Unknown 155 | 119/2, 119/4, 119/13, 119/14, 120/1, 121/3, 121/4, 121/5, 122/1, 123/1, 123/2, 123/3, 123/4, 123/5, 123/6, 125/2, 125/4
Michael Gary Hurst | 119/2, 119/4
Amy Bryant | 119/2, 119/4
David Alexander Bell | 119/2, 119/4
Shanna Marta Ercolano-Bell | 119/2, 119/4
Unknown 156 | 119/2, 119/4, 119/14, 120/1, 121/3, 121/4, 121/5, 122/1, 123/1, 123/2, 123/3, 123/4, 123/5, 123/6, 125/2, 125/4
Unknown 157 | 115/5, 115/8
Unknown 159 | 131/2, 131/5, 131/7, 131/9, 132/3, 132/10, 132/11
Unknown 160 | 131/2, 131/5, 131/7, 131/9, 132/3, 132/10, 132/11
John Frederick Hockley | 115/5, 115/8
Shirley May Hockley | 115/5, 115/8
Hugo George Wilson | 115/5, 115/8
Lauren Stacey Smith | 115/5, 115/8
Unknown 161 | 141/6
Unknown 138 | 41/3, 41/4, 42/1, 42/2
John Cousins | 99/3, 99/4, 99/8
Alistair James Black | 102/10, 103/12, 103/15, 103/17, 103/18, 104/6
Rebecca Ann Black | 102/10, 103/12, 103/15, 103/17, 103/18, 104/6
Unknown 163 | 98/1, 98/3, 99/1, 99/2, 99/7, 99/7a, 99/15, 100/1, 100/2, 100/3, 100/7
Anthony Raymond Kocher | 25/6, 25/7, 26/1, 26/2, 26/4, 27/1, 27/4, 26/1a
Sarah Margaret Kocher | 25/6, 25/7, 26/1, 26/2, 26/4, 27/1, 27/4, 26/1a
Paterson Reino Lehtonen-Riley | 25/6, 25/7, 26/1, 26/2, 26/4, 27/1, 27/4, 26/1a
Danielle Patricia Lehtonen-Riley | 25/6, 25/7, 26/1, 26/2, 26/4, 27/1, 27/4, 26/1a
Dawn Maria Fordham | 75/8, 76/2, 76/3
Unknown 165 | 7/7, 7/9, 8/2, 8/3, 8/5, 9/3, 10/1
Unknown 166 | 44/10, 44/11, 45/1, 45/5, 45/7, 45/9, 46/1, 46/3
Claire Louise Wright | 33/11
Malcolm Patrick Wright | 33/11
Unknown 167 | 94/1, 95/1, 95/2, 95/3, 95/7, 95/8, 96/10, 96/11
Unknown 168 | 76/8
Unknown 170 | 80/1, 81/7, 81/9
Unknown 171 | 80/1, 81/7, 81/9
David Eric Tooth | 65/5
Susan Eileen Tooth | 65/5
Unknown 173 | 117/1, 118/1, 118/6
Christopher Patrick Robinson | 32/12, 32/13
Unknown 174 | 117/1, 117/6, 117/15, 118/1, 118/6
Unknown 175 | 115/1, 116/1, 116/2, 116/3, 117/2, 117/7, 117/8, 117/11, 117/12, 117/13, 117/14, 117/16, 118/4
James Edward Joyce | 80/8, 81/12
Dawn Kathleen Moffat | 80/8, 81/12
Mark James Urwin | 22/3, 22/4, 22/5, 22/6
Unknown 176 | 146/7
Unknown 177 | 99/5
Unknown 178 | 99/5
Sanctuary Affordable Housing Limited | 94/1, 95/1, 95/2, 95/3, 95/7, 95/8, 96/10, 96/11
Ralph Arthur Watkinson | 2026-03-26
Douglas Bernard Watkinson | 2026-03-26
John Randel Norman | 53/5, 53/6, 53/7, 54/1, 55/1, 55/2, 55/5, 55/7, 55/8, 55/11, 56/1, 56/2
Katherine Mary Norman | 53/7, 54/1, 55/1, 55/5, 55/11, 56/1, 56/2
Unknown 181 | 44/7
Brian McCelland | 50/12, 50/15, 51/1, 51/4
Charlotte Luckhurst | 50/12, 50/15, 51/1, 51/4
Francis Renouf | 50/12, 50/15, 51/1, 51/4
Edward Finnerty | 50/12, 50/15, 51/1, 51/4
Unknown 183 | 83/8
Unknown 184 | 80/4, 81/5
Unknown 185 | 146/33
Unknown 186 | 146/33
Unknown 187 | 146/33
Unknown 188 | 146/33
Unknown 189 | 146/33
Unknown 190 | 146/33
Unknown 192 | 146/7
Unknown 194 | 146/11
Unknown 195 | 146/11
Betty May Crowther | 50/10, 51/5
Unknown 199 | 146/24
Unknown 200 | 146/24
Unknown 201 | 146/23
Unknown 203 | 146/22
Unknown 204 | 125/9, 125/11, 146/21
Unknown 206 | 147/7, 147/9
Unknown 207 | 147/7, 147/9
Unknown 208 | 147/7, 147/9
Unknown 209 | 147/7, 147/9
Unknown 210 | 147/7, 147/9
Unknown 212 | 146/27
Unknown 214 | 146/27
Unknown 215 | 146/27
Unknown 216 | 146/27
Unknown 217 | 146/27
Unknown 218 | 145/6
Unknown 219 | 145/7
Unknown 220 | 145/7
Unknown 221 | 145/7
Unknown 222 | 145/7
Unknown 223 | 145/7
Unknown 225 | 145/5
Unknown 226 | 145/9, 145/11
Unknown 227 | 143/14, 143/15, 144/2, 144/5
Department of Health and Social Care | 143/14, 143/15, 144/2, 144/5
Carlton J Bird | 148/62, 149/13
Trevor Malcolm Pharaoh | 39/3, 39/4, 39/5, 39/8, 39/12, 39/13, 39/14, 40/2, 41/1, 41/2
Beverley Gay Pharaoh | 39/3, 39/4, 39/5, 39/8, 39/12, 39/13, 39/14, 40/2, 41/1, 41/2
Unknown 230 | 148/29
Unknown 231 | 148/31
Unknown 232 | 148/32
Unknown 233 | 148/28
Unknown 3 | 146/27
Unknown 4 | 148/37
Unknown 5 | 148/41
Unknown 6 | 148/26
Unknown 7 | 99/3, 99/4, 99/8
Unknown 8 | 132/8, 133/1, 133/5, 134/9, 134/11
Unknown 9 | 148/27
Dollymans Storage Limited | 150/2, 150/3, 150/4, 150/10, 151/4, 151/8
Unknown 10 | 148/23, 148/33
Unknown 11 | 148/25
Unknown 14 | 147/8
Unknown 15 | 148/57, 149/3
Unknown 16 | 148/24
Unknown 18 | 145/10, 146/2
Alan David Wisdom | 98/8
Julie Anne Wisdom | 98/8
Unknown 19 | 2026-10-10
Adam James Carter | 46/4, 46/6, 46/7, 47/3, 47/4, 49/1, 49/6
Amanda June Carter | 46/4, 46/6, 46/7, 47/3, 47/4, 49/1, 49/6
Unknown 20 | 27/6, 27/7, 27/7a, 28/3, 28/5, 29/2, 29/4, 28/5a
Louise Gaye Wright | 67/5, 67/9
Unknown 21 | 145/7
Ann Moore | 27/2, 27/3, 27/5, 28/2, 28/4
Arthur James Moore | 27/2, 27/3, 27/5, 28/2, 28/4
Lorna Ann Sara Burrett | 27/2, 27/3, 27/5, 28/2, 28/4
Unknown 22 | 4/5, 4/6, 5/2, 5/3, 5/6, 5/7, 6/1
Unknown 23 | 147/11
Unknown 26 | 71/1
Unknown 29 | 99/5
Hobbs Estates Limited | 84/1, 84/5, 84/7, 84/8, 85/2, 85/3, 85/5, 85/6, 86/1, 86/2, 87/1, 87/2, 88/1, 88/2, 88/3, 85/1, 85/10, 85/14, 86/3, 86/4, 87/3, 88/4, 89/14, 89/15
James Robert Drinnan | 86/1, 87/3
Catherine Elizabeth Drinnan | 86/1, 87/3
Elizabeth Sarah Follows | 13/5, 13/6, 14/2, 14/2a, 14/2b, 15/1, 15/2, 15/3, 15/4, 16/1, 16/2
Unknown 31 | 60/9, 60/12
Unknown 32 | 35/5, 36/1
Unknown 33 | 52/3, 52/4, 52/8, 52/9
Unknown 34 | 129/3, 129/6
Jeffrey Alan James Phillips | 4/5, 4/6, 5/2, 5/3, 5/6, 5/7, 6/1
Rosemary Helen Phillips | 4/5, 4/6, 5/2, 5/3, 5/6, 5/7, 6/1
Unknown 36 | 2026-09-08
Mark William Lloyd Follows | 13/5, 13/6, 14/2, 14/2a, 14/2b, 15/1, 15/2, 15/3, 15/4, 16/1, 16/2
Unknown 37 | 39/3, 39/4, 39/5, 39/8, 39/12, 39/13, 39/14, 40/2, 41/1, 41/2
Secretary of State for Environment, Food and Rural Affairs | 81/1, 81/2, 82/7, 82/8, 146/18, 146/30, 147/5, 147/7, 147/9, 147/10
Kevin Andrew Collins | 81/1, 81/2, 82/7, 82/8
Heather Kim Taylor | 81/1, 81/2, 82/7, 82/8
John Peter Brace | 80/4, 81/5
Nadina Edmonson | 80/4, 81/5
Unknown 39 | 22/8, 23/1
Unknown 40 | 2026-01-29
Unknown 41 | 12/5, 12/6, 13/1, 13/3
Lauren Sky Sweeney | 146/18, 146/30, 146/33, 147/5
Ben Oliver Wortley | 146/18, 146/30, 146/33, 147/5
Louise Marie Clark-Aarons | 146/18, 146/30, 146/33, 147/5
Andrew Paul Aarons | 146/18, 146/30, 146/33, 147/5
Stacey Louise Crudgington | 146/18, 146/30, 146/33, 147/5
Callum John Bunn | 146/18, 146/30, 146/33, 147/5
Madeleine Nicole Gibson | 146/18, 146/30, 146/33, 147/5
Harry John Wylie | 146/18, 146/30, 146/33, 147/5
Unknown 42 | 146/18, 146/30, 147/5, 147/7, 147/9, 147/10
Derek John Horner | 145/12, 146/6, 146/13, 146/16, 146/18, 146/30, 147/5
Peter Raymond Sherwin | 146/18, 146/30, 146/31, 147/5
Christine Sherwin | 146/18, 146/30, 146/31, 147/5
Kelvin Christopher Higgs | 146/18, 146/30, 146/31, 147/5
Emma Jayne Higgs | 146/18, 146/30, 146/31, 147/5
Andrea Jane Strelley-Upton | 146/18, 146/30, 146/31, 147/5
The Owner/Occupier 1 | 146/18, 146/30, 146/31, 147/5
Jacqueline Ann Joyner | 146/18, 146/30, 146/31, 147/5
Ivan Yorick Magner Painter | 146/18, 146/30, 146/31, 147/5
The Owner/Occupier 2 | 146/18, 146/30, 146/31, 147/5
Benjamin Michael Riddell | 146/18, 146/30, 146/31, 147/5
Ann Martina Tunstall | 146/18, 146/30, 147/5
BP P.L.C | 148/2, 148/14, 148/21, 148/30, 148/44
Unknown 43 | 119/6, 121/2
Essex and Suffolk Water Limited | 33/1, 33/2, 33/8, 33/9, 125/9, 125/11, 128/3, 128/6, 129/7, 136/7, 137/1, 145/2, 147/12, 32/16, 32/17, 32/18
Linda Anne Delpine | 102/3, 102/7, 103/3, 103/5, 103/8, 103/16
Clive William Collins | 33/10, 33/12, 34/1, 34/2, 34/4, 34/5, 34/6, 35/2, 35/3
Unknown 44 | 8/6, 8/9
Unknown 45 | 8/6, 8/9
Unknown 47 | 148/57, 149/3
Unknown 48 | 144/4, 145/1, 145/3, 145/14, 145/15, 145/16, 146/5, 146/15, 146/29, 146/34
Unknown 49 | 83/10, 83/11, 145/14, 145/16, 146/34
Unknown 50 | 144/4, 145/1, 145/3, 145/8, 145/13, 145/14, 145/15, 145/16, 146/34
Unknown 51 | 145/14, 145/16, 146/34
Unknown 52 | 145/14, 145/16, 146/34
Unknown 53 | 145/14, 145/16, 146/34
Unknown 54 | 145/8, 145/13, 145/14, 145/16, 146/34
Unknown 55 | 144/4, 145/1, 145/3, 145/8, 145/13, 145/14, 145/15, 145/16, 146/34
Unknown 56 | 115/1, 116/1, 116/2, 116/3, 117/2, 117/7, 117/8, 117/11, 117/12, 117/13, 117/14, 117/16, 118/4
Unknown 58 | 150/6, 150/7, 150/8, 151/1, 151/6, 151/7, 151/11, 152/2, 152/3
Unknown 59 | 124/1, 125/1, 125/3, 125/7, 125/8, 125/10, 126/1, 126/2, 126/3, 127/1, 127/3, 127/4, 128/7, 128/8
Unknown 61 | 149/2
Unknown 62 | 147/13, 147/16
South East Water Limited | 124/1, 125/1, 125/3, 125/7, 125/8, 125/10, 126/1, 126/2, 126/3, 127/1, 127/3, 127/4, 128/7, 128/8
Unknown 63 | 149/4
Unknown 64 | 149/4
Unknown 65 | 36/7, 37/1, 37/3, 37/4, 37/6, 38/1
Unknown 67 | 148/2, 148/14, 148/21, 148/30, 148/44
Unknown 70 | 124/1, 125/1, 125/3, 125/7, 125/8, 125/10, 126/1, 126/2, 126/3, 127/1, 127/3, 127/4, 128/7, 128/8
Unknown 71 | 124/1, 125/1, 125/3, 125/7, 125/8, 125/10, 126/1, 126/2, 126/3, 127/1, 127/3, 127/4, 128/7, 128/8
Unknown 72 | 124/1, 125/1, 125/3, 125/7, 125/8, 125/10, 126/1, 126/2, 126/3, 127/1, 127/3, 127/4, 128/7, 128/8
Unknown 73 | 124/1, 125/1, 125/3, 125/7, 125/8, 125/10, 126/1, 126/2, 126/3, 127/1, 127/3, 127/4, 128/7, 128/8
Unknown 74 | 124/1, 125/1, 125/3, 125/7, 125/8, 125/10, 126/1, 126/2, 126/3, 127/1, 127/3, 127/4, 128/7, 128/8
Unknown 75 | 124/1, 125/1, 125/3, 125/7, 125/8, 125/10, 126/1, 126/2, 126/3, 127/1, 127/3, 127/4, 128/7, 128/8
Unknown 76 | 124/1, 125/1, 125/3, 125/7, 125/8, 125/10, 126/1, 126/2, 126/3, 127/1, 127/3, 127/4, 128/7, 128/8
Unknown 77 | 124/1, 125/1, 125/3, 125/7, 125/8, 125/10, 126/1, 126/2, 126/3, 127/1, 127/3, 127/4, 128/7, 128/8
Unknown 78 | 124/1, 125/1, 125/3, 125/7, 125/8, 125/10, 126/1, 126/2, 126/3, 127/1, 127/3, 127/4, 128/7, 128/8
Unknown 80 | 146/14
Unknown 81 | 124/1, 125/1, 125/3, 125/7, 125/8, 125/10, 126/1, 126/2, 126/3, 127/1, 127/3, 127/4, 128/7, 128/8
Unknown 82 | 151/8
Unknown 84 | 151/9, 151/10, 152/4
Unknown 85 | 124/1, 125/1, 125/3, 125/7, 125/8, 125/10, 126/1, 126/2, 126/3, 127/1, 127/3, 127/4, 128/7, 128/8
Unknown 86 | 146/19
Andrew Philip Peters | 150/6, 150/7, 150/8, 151/1, 151/6, 151/7, 151/11, 152/2, 152/3, 150/9
Unknown 91 | 148/62, 149/13
Unknown 94 | 146/25
Unknown 95 | 69/2, 70/1, 70/4, 71/9, 71/11
Unknown 96 | 146/9
Unknown 97 | 146/9
Unknown 98 | 146/9
Unknown 102 | 146/26
Forestry Commission | 107/1, 107/3, 107/4, 107/5, 108/1, 108/2, 108/5, 108/6, 108/8, 109/1, 109/2, 109/2a, 110/1, 110/4
Unknown 103 | 115/13
Unknown 104 | 146/9
Unknown 106 | 146/7
Unknown 107 | 146/1, 146/10
Unknown 108 | 146/1, 146/10
Unknown 109 | 146/3
Unknown 110 | 145/2
Unknown 114 | 3/3, 3/4, 4/2, 4/3, 4/4, 5/1
Unknown 115 | 148/2, 148/14, 148/30, 148/44
Unknown 116 | 3/3, 3/4, 4/2, 4/3, 4/4, 5/1
Amy Mehers | 145/12
Unknown 117 | 103/10, 104/2, 105/5, 105/6, 104/5
LDN Associates Limited | 145/12, 146/6, 146/13, 146/16
Unknown 118 | 146/18, 146/30, 147/5, 147/7, 147/9, 147/10
Unknown 120 | 145/12, 146/6, 146/13, 146/16
Unknown 121 | 145/12, 146/6, 146/13, 146/16
Unknown 122 | 145/12, 146/6, 146/13, 146/16
Unknown 123 | 145/12, 146/6, 146/13, 146/16
Unknown 125 | 146/18, 146/30, 147/5, 147/7, 147/9, 147/10
Unknown 126 | 145/12, 146/6, 146/13, 146/16
Unknown 127 | 145/12, 146/6, 146/13, 146/16
Unknown 128 | 141/2, 141/13
Unknown 130 | 141/2, 141/13
Unknown 132 | 141/6
Unknown 136 | 3/3, 3/4, 4/2, 4/3, 4/4, 5/1
Unknown 139 | 134/1, 134/2, 134/7, 135/3, 135/4, 135/5, 135/7, 136/4, 136/5, 136/9
Unknown 141 | 59/6, 59/9, 60/4, 60/9, 60/12, 60/14, 61/1
Unknown 143 | 146/8
Unknown 145 | 146/8
Nigel David Seager | 125/9, 125/11
Sarah Anne Seager | 125/9, 125/11
Unknown 149 | 145/12, 146/6, 146/13, 146/16
Unknown 150 | 53/5, 53/6, 55/2
Timothy Austen Bird | 148/62, 149/13
Martin Grant Homes Land Limited | 149/4
Unknown 235 | 59/6, 59/9, 60/4, 60/9, 60/12, 60/14, 61/1
Unknown 236 | 48/3
Unknown 237 | 2026-06-18
Unknown 238 | 75/8, 76/2, 76/3
Unknown 254 | 94/7
Unknown 275 | 146/31
Unknown 279 | 147/2
Unknown 280 | 147/4
Unknown 281 | 147/14
Unknown 285 | 63/3
Unknown 286 | 62/2, 63/9, 63/11, 63/16
Unknown 290 | 65/6, 65/9
Unknown 292 | 65/4
Unknown 294 | 67/10
Unknown 295 | 67/14
Unknown 297 | 67/13
Unknown 299 | 67/4
Unknown 300 | 67/6
Unknown 301 | 59/7
Unknown 302 | 67/11
Unknown 303 | 58/10
Unknown 304 | 52/6
Unknown 306 | 58/4
Unknown 307 | 42/3, 42/5, 42/8
Unknown 310 | 60/5
Unknown 311 | 58/7
Unknown 312 | 56/3
Unknown 314 | 68/1
Unknown 315 | 44/4, 44/5, 44/8, 44/12
Unknown 316 | 45/3, 45/6, 45/11
Unknown 317 | 50/6
Unknown 321 | 50/5
Unknown 322 | 51/13, 52/2
Unknown 323 | 68/4
Unknown 324 | 49/2
Unknown 326 | 51/7
Unknown 327 | 50/11
Unknown 328 | 50/9
Unknown 329 | 48/1, 49/5
Unknown 330 | 48/2
Unknown 331 | 45/8
Unknown 332 | 68/3
Unknown 334 | 38/7
Unknown 336 | 39/7
Unknown 338 | 37/8, 38/3
Unknown 339 | 34/3
Unknown 340 | 36/2
Unknown 342 | 70/6
Unknown 343 | 33/3, 33/4
Unknown 347 | 85/8
Unknown 355 | 99/13
Unknown 356 | 99/10
Unknown 357 | 99/9
Unknown 358 | 99/11
Unknown 360 | 101/8
Unknown 361 | 101/11
Unknown 362 | 101/5
Unknown 363 | 101/15
Unknown 365 | 102/5
Unknown 366 | 115/2
Unknown 372 | 131/4
Unknown 373 | 132/6
Unknown 374 | 132/1
Unknown 376 | 143/6
Unknown 379 | 143/10, 143/11
Unknown 381 | 147/17
Unknown 385 | 2026-04-30
Unknown 386 | 2026-08-30
Unknown 388 | 2026-01-28
Unknown 390 | 2026-06-23
Unknown 391 | 2026-03-23
Unknown 392 | 2026-08-19
Unknown 397 | 2026-09-18
Unknown 398 | 2026-12-18
Unknown 399 | 76/1
Unknown 400 | 99/6
Unknown 402 | 141/12
Unknown 403 | 146/17
Unknown 404 | 2026-06-10
Unknown 405 | 2013-10-01
Unknown 407 | 2026-06-07
Unknown 409 | 83/16
Unknown 411 | 105/3
Unknown 413 | 98/7
Unknown 414 | 99/12
Unknown 415 | 81/3
Unknown 417 | 82/3, 83/19
Unknown 419 | 82/1, 83/17, 83/18
Unknown 420 | 134/10
Unknown 424 | 149/7
Unknown 425 | 146/31
Unknown 427 | 136/6
Unknown 429 | 132/9
Unknown 430 | 125/5, 125/6
Unknown 433 | 91/2
Unknown 434 | 148/56
Unknown 438 | 141/19
Unknown 439 | 141/21
Unknown 440 | 2026-11-23
Unknown 441 | 133/8
Unknown 442 | 71/10
Unknown 443 | 73/3
Unknown 444 | 76/6
Unknown 445 | 79/6
Unknown 446 | 80/7
Unknown 448 | 84/17
Unknown 449 | 91/8
Unknown 451 | 93/4, 93/8
Unknown 453 | 95/5, 95/6
Unknown 454 | 95/4
Unknown 455 | 96/6
Unknown 456 | 96/3
Unknown 458 | 101/7
Unknown 459 | 103/19
Unknown 460 | 103/6
Unknown 461 | 108/3, 108/7
Unknown 462 | 111/6
Unknown 463 | 111/1
Unknown 464 | 115/11, 115/17
Unknown 465 | 119/1, 119/7
Unknown 481 | 125/12
Unknown 482 | 126/4
Unknown 487 | 146/28, 146/32, 147/6
Unknown 488 | 2026-02-07
Unknown 489 | 2026-01-08
Unknown 490 | 2026-02-09
Unknown 491 | 2026-08-07
Unknown 492 | 2026-07-08
Unknown 494 | 11/8, 11/10
Unknown 495 | 2026-04-11
Unknown 496 | 2026-11-11
Unknown 497 | 2026-03-12
Unknown 499 | 2026-04-12
Unknown 500 | 2026-04-16
Unknown 507 | 31/4
Unknown 508 | 2026-07-31
Unknown 509 | 40/3
Unknown 510 | 2026-01-02
Unknown 511 | 54/2
Unknown 514 | 63/13
Unknown 515 | 2026-04-05
Andrew Wisbey | 32/12, 32/13
H J Fairs & Son | 79/2, 79/4, 79/7, 79/8, 79/9
Hogsbjerg Farms | 71/12, 72/1, 72/5, 72/8
Tewes Farm Renewables Limited | 27/6, 27/7, 27/7a, 28/3, 28/5, 29/2, 29/4, 28/5a
Kalli Robinson | 148/42
Richard J Elsdon | 53/3
Runningwell Equestrian Centre | 142/2, 142/3, 142/4, 143/1, 143/2, 143/3, 143/4, 143/7, 143/9
G & J Barron | 77/4, 78/1, 78/4
JR Crayston & Sons Limited | 76/4, 76/7, 77/2, 77/3
Clare Sharp | 38/12, 38/14, 39/1
Hamish Debnam-Sharp | 38/12, 38/14, 39/1
French Partners | 100/4, 100/5, 101/13, 101/17, 101/18
Brett Aggregates Limited | 131/2
Frankie Jabez Fone | 148/12, 148/13, 148/53
Justin David John Argent | 41/3, 41/4, 42/1, 42/2
George Wright | 63/7, 63/8, 63/10
K. R. Gray & Sons | 30/14, 31/1, 31/2
R.W Middleton | 119/9
Chantal Pinney | 60/6, 60/8, 60/10, 60/11
Unknown Unknown 12907 | 148/49
L M Ruffel | 53/7, 54/1, 55/1, 55/5, 55/11, 56/1, 56/2, 56/4, 56/5, 56/6, 57/1
Joan Flower | 65/2, 65/10, 65/11, 65/13, 67/1, 65/9
H B Hughes & Son | 22/8, 23/1
Ann Cromack | 81/4
The Bark Park Woodlands Adventure | 143/14, 143/15, 144/2, 144/5
C J Dear | 142/4, 143/7, 143/9
Tony Laing | 134/1, 134/2, 134/7, 135/3, 135/4, 135/5, 135/7, 136/4, 136/5, 136/9
R J Hodge & Son | 131/2, 131/6, 131/7, 131/8, 131/9, 132/3, 132/11, 132/13, 133/2
Peter Philpot | 132/10
Helen Willsmer | 130/5
FB & AH Speakman | 115/1, 116/1, 116/2, 116/3, 117/1, 117/2, 117/6, 117/7, 117/11, 117/12, 117/13, 117/14, 117/15, 117/16, 118/4, 118/6, 129/3, 129/6, 130/7, 130/8, 130/11, 130/12, 130/13
The Occupier | 148/15, 148/16
The Occupier | 148/18
Charles White | 21/3, 19/11, 21/1
J W Smith & Co | 13/2, 13/4
Sue J Forret | 53/4
Superbia Automotive | 115/15
Terri Cannon | 30/2, 30/3
White Brothers | 41/5, 42/4
Lord Anthony William Vernon | 18/8, 18/9
Lady Cherry Stanhope Vernon | 18/8, 18/9
J L A Webster | 8/11, 9/1
Lt. Col. Richard P T Earle | 2026-02-03
J M Ruffel | 53/7, 54/1, 55/1, 55/5, 55/11, 56/1, 56/2, 56/4, 56/5, 56/6, 57/1
Drane Brothers | 38/10
Roger Stewart Foulds | 3/3, 3/4, 4/2, 4/3, 4/4, 5/1, 6/2, 6/3, 7/1
J Donald & Son | 4/5, 4/6, 5/2, 5/3, 5/7, 6/1
Jon Stalley | 2026-09-30
The Occupier | 31/9
Chris Chamlay | 74/1, 75/1
John Blackwell | 84/2, 85/9
Messrs Bell & Godden | 82/2, 82/3, 83/19
S Kelly Farms Limited | 83/10, 83/11
Steve Hernaman | 147/10
Oliver Wass | 84/22
Katharine Louise Crowther | 49/7, 50/1, 50/2, 50/4, 50/8, 50/10, 51/5
Lucy Newton | 53/5, 53/6, 53/7, 54/1, 55/1, 55/2, 55/5, 55/11, 56/1, 56/2
Andrew Newton | 53/5, 53/6, 53/7, 54/1, 55/1, 55/2, 55/5, 55/11, 56/1, 56/2
Nicola Newton | 53/5, 53/6, 53/7, 54/1, 55/1, 55/2, 55/5, 55/11, 56/1, 56/2
Speakman Brothers Limited | 115/5, 115/8, 128/2, 129/1, 129/3, 129/5, 129/6, 131/3, 130/7, 130/8, 130/11, 130/12, 130/13
Teresa Clark | 2026-07-19
Charles R Wright | 67/12, 67/9
Andrew Davies | 33/10, 33/12, 34/1, 34/2, 34/4, 34/5, 34/6, 35/2, 35/3, 37/3, 37/4, 37/6, 38/1
Justin Ramsey | 35/4, 35/5, 36/1, 36/3
John Ramsey | 35/4, 35/5, 36/1, 36/3
Edgar Burchell | 43/4
Humphrey Burchell | 43/4
Andrew Westrop | 54/3, 55/9, 55/10
Madeline Westrop | 54/3, 55/9, 55/10
Sandon Village Hall Management Committee | 130/3, 130/4
N S Lindsell & Sons | 29/5, 30/7, 30/10, 30/11, 31/3, 31/10, 32/1, 32/3, 32/4, 32/6, 31/8, 32/2, 32/5, 32/7, 32/9, 32/10
Pauline Sally Philp | 51/9, 51/10, 51/11, 52/1, 52/3, 52/4, 52/5, 52/7, 52/7a, 52/7b, 52/8, 52/9, 52/10, 52/11, 53/1
SJP Rural Ltd | 12/7, 12/8, 12/9, 12/5, 13/1, 13/3
James Reay | 12/6, 13/1, 13/3
Elizabeth Reay | 12/6, 13/1, 13/3
Ralph Chapman | 107/2, 108/4
Kerry Ann Salih | 146/22
Edward Watson | 4/5, 4/6, 5/2, 5/3, 5/6, 5/7, 6/1
The Occupier | 146/22, 146/31
The Occupier | 148/36, 148/43
Claire Fisher | 103/10, 103/11, 104/2, 105/5, 105/6, 104/3, 104/3a, 104/4, 104/5
Gigaclear Limited | 22/5, 22/6
Charles William Blatch | 102/6, 102/9, 102/11, 102/13
Gemma's Farm | 102/6, 102/11
Unknown | 5/5, 37/5, 84/20, 91/7, 94/3, 103/1, 130/14, 144/1, 144/3, 10/7, 10/12, 12/7, 17/4, 17/6, 32/11, 32/15, 61/4, 63/13, 64/2, 64/4, 70/9, 71/15, 82/2, 82/5, 82/6, 85/1, 85/3, 85/5, 85/6, 85/10, 85/11, 85/12, 85/13, 85/14, 85/18, 86/3, 86/4, 87/3, 88/4, 89/2, 89/9, 89/10, 89/11, 89/13, 89/14, 89/15, 100/6, 101/19, 102/2, 102/10, 102/12, 103/4, 103/7, 103/9, 103/11, 103/12, 103/13, 103/14, 103/15, 103/17, 103/18, 103/20, 104/1, 104/6, 130/2, 130/3, 130/4, 130/7, 130/9, 130/12, 130/13, 141/9, 141/22, 143/13, 150/9
Colin Lindsell | 16/8, 16/9, 17/1, 17/3, 17/4, 18/1
Neil Pottrill | 16/3, 16/4, 16/5, 16/6, 16/7, 16/8, 16/9, 17/1, 17/2, 17/3, 17/4, 17/5, 17/6, 17/7, 17/8, 17/9, 18/1, 18/2
Joanne Hughes | 16/3, 16/4, 16/5, 16/8, 17/1, 17/2, 17/4, 17/5, 17/6, 17/7, 17/8, 17/9, 18/1, 18/2, 16/6, 16/7
James Luis Philip Sayell | 16/5, 16/6, 16/7, 16/9, 17/2, 17/4
Unknown X | 123/7, 128/1, 128/4, 129/2, 129/8, 132/5
Unknown 600 | 2026-01-14
Paul David Fraser | 66/1
Caroline Jane Fraser | 66/1
Unknown 601 | 148/47
Unknown 602 | 149/12
The Oil and Pipelines Agency | 19/9, 19/11, 20/2, 21/1, 21/6, 21/7, 22/2, 21/6a
Exolum Pipeline System Limited | 19/9, 19/11, 20/2, 21/1, 21/6, 21/7, 22/2, 21/6a
Unknown 603 | 145/9
Unknown 604 | 145/5
Unknown 605 | 145/6
Unknown 606 | 145/11
Unknown 607 | 93/1, 93/2, 93/5, 93/7, 94/5, 94/8
Unknown 608 | 144/1, 144/3
Simon Lindsell | 32/11
Ingrid Brock | 20/7, 21/8, 21/9, 22/1
Percy Brock | 20/7, 21/8, 21/9, 22/1
The Owners and Occupiers of 21 - 61 Royal Oak Drive | 148/23, 148/25, 148/26, 148/27, 148/28, 148/29, 148/31, 148/32, 148/33, 148/34, 148/35, 148/36, 148/37, 148/38, 148/39, 148/40, 148/41, 148/42, 148/43, 148/45, 148/46, 148/48, 148/49, 148/50, 148/51, 148/53, 148/55
Unknown 609 | 115/9
Unknown 610 | 115/16
Unknown 611 | 106/4
Unknown 612 | 92/3
Unknown 613 | 94/6
Unknown 614 | 71/3
Unknown 615 | 78/6, 78/7
Unknown 617 | 110/8
Unknown 618 | 132/12
Michael Anthony Zabell | 130/6
The Rolling Bean | 141/19
Samuel John Henry Knight | 146/18, 146/30, 146/31, 147/5
Harriet May Knight | 146/18, 146/30, 146/31, 147/5
Maddison Alarna Merritt | 146/31
Begin Braintree (AF) Limited | 97/1, 97/3, 97/5, 98/10, 98/11, 98/13
Fastned UK Limited | 119/2, 119/4, 119/13, 119/14, 120/1, 121/3, 121/4, 121/5, 122/1, 123/1, 123/2, 123/3, 123/4, 123/5, 123/6, 125/2, 125/4
EE Limited | 62/1, 62/3, 63/5, 63/6, 63/15, 64/1
Bryden Farming Limited | 134/1, 134/2, 134/7, 135/1, 135/2, 135/3, 135/4, 135/5, 135/7, 136/4, 136/5, 136/9
EDF Energy Renewables Limited | 96/1, 96/2, 96/9, 97/6, 97/7
The Major Whitbread Charity | 102/6, 102/9, 102/11, 102/13
Essex Union Hunt Pony Club | 134/1, 134/2, 135/3, 135/4, 135/5, 135/7, 136/4, 136/5, 136/9
Thomas Loeber | 141/11, 141/15, 141/17, 142/1, 142/5, 142/6
Lynda Karen Zabell | 130/6
The Woodland Trust | 147/15
Joanne Lisa Bevan | 2026-05-07
Anna Hill | 89/1, 89/5, 89/12, 90/1, 90/2, 91/1, 91/3, 91/4, 91/5, 91/6, 92/1, 92/2, 92/4, 92/5, 92/6, 93/3, 93/6, 89/3, 89/4, 89/6, 89/7, 89/8
Nicholas Drane | 36/6, 36/6a, 36/7, 37/1
Anthony Lyster | 60/13
Diana Peterson | 82/1, 83/17, 83/18
Katherine Godden | 82/1, 83/17, 83/18
Jayden Kenneth Dellow | 2026-08-23
Kathryn Ruby Mallindine | 2026-08-23
H P Smith & Sons | 93/2, 94/8
Berden Parish Council | 1/6, 1/7
Mary Lynne Earle | 2026-02-03
Howard Blackwell | 86/1, 87/1, 87/3, 88/1, 88/2, 88/3, 85/1, 85/3, 85/4, 86/4, 88/4, 89/14, 89/15
Binjans Farming | 20/1, 20/4, 20/7, 21/8, 21/9, 22/1
Anthony Flower | 65/2, 65/10, 65/11, 65/13, 67/1, 65/9
Gary Paul Sharp | 131/1
Julie Sharp | 131/1
Adrian Michael Olver | 19/11, 21/1, 21/3
Sage Homes RP Limited | 99/16, 99/17
Samantha Jane Chumbley | 135/9, 136/10
Stuart Peter Ross | 135/9, 136/10
Hertfordshire County Council | 2/1, 2/2
Maces Farm | 7/7, 8/2, 7/9, 8/1, 8/3, 8/5, 9/3, 10/1
Wild Duck Farming Limited | 20/1, 20/4, 20/2, 20/3
Sharon Margaret Caton | 24/2, 24/3
Janet Lepley | 141/22
LSU Utility Solutions Limited | 150/9
The Occupier | 148/52, 148/55
The Maples (Cressing) Residents Management Company Limited | 99/16, 99/17
Vivienne Elizabeth Linda Wilkin | 141/22
Service on Site Limited | 115/13
Robert Philip Thomas Wilkin | 141/22