## Actions
GC0091 Demand Connection Code - Workgroup Issue Tracker
NGET Owner: |  | Franklin Rodrick
Action/Risk Management:
Item No. | Meeting Date | Meeting No. | Topic | Workgroup Discussion Point | Category | Raised by | Status | Owner | Target Completion Date | Updates
1 | 2015-11-20 | 1 | Representation | Update on Smart Energy Code | Action |  | Resolved | DECC |  | Julian Goldsack provided an update
2 | 2015-11-20 | 1 | Representation | Update on Smart Grid Forum / Workstream 6 | Action |  | Resolved | Ofgem
3 | 2015-11-20 | 1 | Representation | Engage with Demand Users / seek representation on the Workgroup | Action |  | Active | FR
4 | 2015-11-20 | 1 | Workgroup | Circulate updated version of the Terms of Reference | Action |  | Resolved | FR
5 | 2015-11-20 | 1 | Representation | Seek representation from SHE Transmission | Action |  | Resolved | NGET
6 | 2015-11-20 | 1 | Workgroup | Circulate final version of the DCC Code to the Workgroup members | Action |  | Resolved | FR
7 | 2015-11-20 | 1 | Workgroup | Define scope of applicability of the Demand Connection Code | Action |  | Resolved | Ofgem
8 | 2015-12-14 | 2 | Workgroup | Seek GC0091 membership nomination from Major Energy User Council | Action |  | Active | FR
9 | 2015-12-14 | 2 | Workgroup | Seek more DNO commercial representation for the Workgroup and speak to COG | Action |  | Resolved | ENA
10 | 2015-12-14 | 2 | Workgroup | Update the 2016 meeting plan | Action |  | Resolved | FR
11 | 2015-12-14 | 2 | Workgroup | Send the Code Mapping spreadsheet to the JESG mailing list for comments | Action |  | Active | FR
12 | 2015-12-14 | 2 | Workgroup | Provide comments on the Workgroup Terms of Reference | Action |  | Resolved | ENA
13 | 2015-12-14 | 2 | Workgroup | NGET to provide combined code mapping spreadsheet | Action |  | Active | NGET |  | Escalate to GC0048
14 | 2016-01-13 | 3 | Workgroup | Send eventbrite invite 3 weeks before to highlight DCC technical workgroup commencing work again | Action |  | Resolved | FR
15 | 2016-01-13 | 3 | Scope | Continued engagement with Power Responsive | Action |  | Active | FR |  | Representation sought from Power Responsive
16 | 2016-01-13 | 3 | Scope | Clarification on role of aggregator for the Flexibility work | Action |  | Active | Ofgem
17 | 2016-01-13 | 3 | Workgroup | Find a contact for Radio Telemetry Switching | Action |  | Resolved | MK |  | No risk on this from DCC
18 | 2016-01-13 | 3 | Scope | Define the scope of the code | Action |  | Resolved | AJ
19 | 2016-01-13 | 3 | Scope | Define the scope of applicability of the code to DSR providers | Action |  | Active | FR
20 | 2016-07-06 | 4 | DSR | Seek representation from Ofgem Flexibility project | Action | GG | Active | Ofgem
21 | 2016-07-06 | 4 | Technical Requirements | Speak to NGET CAMs about sending email to Network Rail / Tata Steel etc.to give an update on the Code/seek representation | Action | GG | Active | FR
22 | 2016-07-06 | 4 | DSR | DSR requirements only apply to demand but there should be a framework setout for the Aggregators (if they use generation to provide this service) | Point to note | MK | Active
23 | 2016-07-06 | 4 | DSR | Garth to circulate letter sent to Ofgem on voltage control demand reduction | Action | MK | Resolved | GG
24 | 2016-07-06 | 4 | Definitions | Check with NGET legal team the interpretation of distibution facility and distribution system. | Action | AJ | Active | FR
25 | 2016-07-06 | 4 | Scope | Liaise with GTC asking for representation on the workgroup to understand whether the code applies to them | Action | FR | Active | FR |  | MK has provided a contact
26 | 2016-07-06 | 4 | Scope | Isle of Man - check with Ofgem if it is covered by DCC or RfG as it is synchronously connected | Action | FR | Active | FR
27 | 2016-07-06 | 4 | Scope | Eurelectric presented the issue of lack of clarity of demand unit / substantial modification at the last EU Connection Codes Stakeholder Committee Meeting.More update will be provided at the September meeting. This would help define the scope of DSR. https://www.entsoe.eu/Documents/Network%20codes%20documents/Implementation/stakeholder_committees/GSC/06_06_2016/ESC_20160606_4.pdf | Action | GG | Active | GG
29 | 2016-07-06 | 4 | Scope | Further discussion within the workgroup or with Ofgem needs to be held in relation to substantial modification following on from update from Stakeholder Committee | Action | GG | Active | All
30 | 2016-07-06 | 4 | Short Circuit Requirment | Short circuit requirements are not well worded in DCC but GB has a very well defined requirement which can be carried on to be used and doesn’t conflict with DCC. | Point to note | AJ | Resolved
31 | 2016-07-06 | 4 | Reactive Power Requirement | Article 15(1) - Provide more examples on Reactive Power requirementsfor different scenarios at the connection points. | Action | AJ | Active | AJ
32 | 2016-07-06 | 4 | Reactive Power Requirement | Discuss with ENA on the material changes to DNO equipment which would lead to a change in contractual agreement. Legal interpretation needs to clear on this for the DNOs | Action | MK | Active | MK/AJ
33 | 2016-07-06 | 4 | Reactive Power Requirement | Check with GC0048 workgroup if any work has been done to understand the materiality aspect for contract changes | Action | FR | Active | FR
34 | 2016-07-06 | 4 | Information Exchange | Article 18 Information Exchange - look at the template that exist currently | Action | AJ | Active | AJ
35 | 2016-07-06 | 4 |  | Look at system defence plan in E&R to ensure both DCC and E&R requirements are in line | Action | FR | Active | FR
36 | 2016-07-06 | 4 | LVDD | Confirm with DECC/Ofgem on the LVDD / other non-mandatory requirements, whether any legal text needs to be included in the GB codes to show compliance with the EU Connection Codes. | Action | FR | Active | FR
37
38
22
23
24
26
27
28
29
30
31
32
33
34
35

## Decision Tracker
GC0048-T RfG Technical Group - Decision Tracker
NGET Owner: | Honor Hynes
Meeting Date | Meeting No. | Decision Point
Workgroup Preference:
Name | Organisation | Vote
Rob Wilson | NGET
Honor Hynes | NGET
Greg Middleton | Deep Sea Electronics Plc
Tim Moore | UKPN
Dave Draper | Horizon Nuclear Power
Alastair Frew | Scottishpower
Chris Whitworth | AMPS
Mike Kay | ENA
Razvan Pabat-Stroe | SPT
Yash Audichya | SSE
Anne Kensall | NGET
Frank Martin | Siemens
Peter Woodcock | RWE Generation UK
Amir Dahresobh | Nordex
Mick Barlow | S&C Electric Company
Campbell McDonald | SSE Generation
Sridhar Sahukari | Dong Energy
Antony Johnson | National Grid
Ben Marshall | National Grid
Chandu Bapatu | Siemens
Richard Woodward | NGET
Franklin Rodrick | NGET
Matt White | UKPN
Alan Creighton | NGET
Hayden Scott-Dye | Tidal Lagoon Power
David Griffiths | RWE
Damian Jackman | SSE Generation

## Sheet1 (hidden)
Active | Point to note | Yes
On Hold | Risk | No
Urgent | Action | Abstain
Resolved | Decision

## Attendance Tracker
GC0048-T RfG Technical Group - Workgroup Attendance Tracker
NGET Owner: | Honor Hynes
Name | Organisation | Role | Meeting 1 - 09/03/16 | Meeting 2 06/04/16 | Meeting 3 - 11/05/2016 | Meeting 4 - 14/06/2016 | Meeting 5 | Meeting 6 | Meeting 7 | Meeting 8 | Meeting 9 | Meeting 10
Rob Wilson | NGET | Chair | Y | Y |  | Y
Honor Hynes | NGET | Technical Secretary | Y | Y
Greg Middleton | Deep Sea Electronics Plc | Attendee | Y | Y |  | Y
Tim Moore | UKPN | Attendee | Y | Y
Dave Draper | Horizon Nuclear Power | Attendee | Y | Y |  | Y
Alastair Frew | Scottishpower | Attendee | Y | Y |  | Y
Chris Whitworth | AMPS | Attendee | Y | Y |  | Y
Mike Kay | ENA | Attendee | Y | Y | Y | Y
Razvan Pabat-Stroe | SPT | Attendee | Y | N |  | Y
Yash Audichya | SSE | Attendee | Y | N
Anne Kensall | NGET | Attendee | Y | Y | Y | Y
Frank Martin | Siemens | Attendee | Y | Y |  | Y
Peter Woodcock | RWE Generation UK | Attendee | Y | N |  | Y
Amir Dahresobh | Nordex | Attendee | Y | Y
Mick Barlow | S&C Electric Company | Attendee | Y | N |  | Y
Campbell McDonald | SSE Generation | Attendee | Y | Y
Sridhar Sahukari | Dong Energy | Attendee | Y | N |  | Y
Antony Johnson | National Grid | Attendee | Y | Y | Y | Y
Ben Marshall | National Grid | Attendee | Y | Y |  | Y
Chandu Bapatu | Siemens | Attendee | N | Y |  | Y
Richard Woodward | NGET | Chair/Tec.Sec. | N | N | Y | Y
Franklin Rodrick | NGET | Technical Secretary | N | N | Y
Matt White | UKPN | Attendee |  |  | Y
Alan Creighton | NGET | Attendee
Hayden Scott-Dye | Tidal Lagoon Power | Attendee |  |  |  | Y
David Griffiths | RWE | Attendee |  |  |  | Y
Damian Jackman | SSE Generation | Attendee |  |  |  | Y